## Slide 1: MVTX Status Report
Ming Liu
LANL
1/9/2020
sPHENIX L2 Meeting

## Slide 2: Budget Distribution
BNL has opened MVTX budget account
  MVTX PMP has been approved and signed by BNL
  Detailed budget for each institution done, 12/3/2019
    Plan presented in July 2019 MVTX review
Paperwork submitted to BNL for fund transfer
  SOW, detailed budget sheet and cover letter from each institute
  LANL, LBNL, MIT, UT-A

## Slide 3: One-day MVTX Final Design Review Scheduled 1/29/2020 @BNL
Final review charge available tomorrow (Fri)
  Focus on the mechanical design readiness for carbon structure production
    Design
    Pre-production
    Vendor selection
  Also production readiness
    Power Units(PU)
    Electronics RU and PU cooling plates
Draft agenda page: https://indico.bnl.gov/event/7165/

## Slide 4: Stave Production at CERN
In good progress, on schedule
  ~10 HICs/month, used up all good chips in December
  3 wafers delivered in mid December, 45 chips available now, expect 10 more chips
  Next chips delivery expected in late January, 8 wafers,
    ~120 gold chips, good for 13 weeks of assembly, last wafers by April 2020
  23 FPCs available for assembly
Plan
  Resume HIC production in week 2 of 2020
  Bond 4 HICs as soon as the bond lab available in January
  1st set of 10~12 staves ready for shipping to LBNL in mid Feb
    Are we ready? Shipping – a batch of ~10 staves or ~20?
Bi-weekly meeting with CERN
  Last meeting, 12/19/2020
  Next one, 1/16/2020