## Slide 1: MVTX Status and Plan
Ming Liu
For the MVTX Group
05/21/2020
sPHENIX L2 Meeting

## Slide 2: Project Status - Mechanics
Design
  One-piece EndWheel (change from ALICE/ITS):
    prototype in hand – looks good!
    now in shop for CMM x-check
  Nose roller-assembly (Jan. review suggestion):
    designed
    prototyping (end of May back from shop)
  Left to do (end of May)
    Finish FEA (next week)– all good so far
    Finish drawings (end of this week)
    CF layup (LBL input)
Vendor selection:
  Ready to contact ~June (P6 was March-April)
  Started preparing the SOW
Final design review ~ Fall 2020
  was planned for 7/2020
Short term (after finishing design):
  Prototyping & preparing the mega mock-up
  X-wing, design installation tools, cooling, …
Nice work by
MIT, LANL and LBNL

## Slide 3: Project Status: Readout and Electrical System
Readout system integration
  RU firmware/software updated (synced to ALICE 3/2020)
  FELIX firmware/software
    software/driver update (synced to ATLAS)
    firmware design in progress for GBT slow control
    readout firmware work next
  8-stave telescope under development
    Possible test beam later in 2020
    Online decoder & monitor updated
Power boards submitted for fabrication
    Delivery ~ late June 2020
RU board test
  60 RUs waiting to be tested at CERN
    Re-planning under discussion
  Cold plates production at UT-A
    Fund being transferred to UT-A
    use UT-A machine shop
Cosmic data from a set up of:
4-satve/4-RU + 1-FELIX + 1-PU + 1-FELIX/Server + 1 GTM
Online Monitoring Plots

## Slide 4
IBSTAVE IDc | HIC assembly | Insp. after glue | Bonding | Insp. after bonding | HIC PWR test | Qualif. test | HIC+SF -> Stave | Stave PWR test | Stave test | Stave test (with long PWR extn.) | Final test (with PT100 and metrology)
TOTAL | 24 | 23 | 20 | 20 | 20 | 18 | 5 | 5 | 5 | 3 | 3
A201 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
A202* | 1 | Damag. | chip |  |  |  |  |  |  |  | 
A203 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
A204 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
A205 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 
A206 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 
B201 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
B202* | 1 | 1 | 1 | 1 | 1 | * | Damag. chip |  |  |  | 
B203 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
B204 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
B205 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
B206 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
F201* | 1 | 1 | 1 | 1 | 1 | * | Damag. chip |  |  |  | 
F202 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
F204 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
G202 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
G203 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
F203 | dummy |  |  |  |  |  |  |  |  |  | 
H202 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
H203 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
H204 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
H206 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 
E204 | 1 | 1 |  |  |  |  |  |  |  |  | 
E201 | 1 | 1 |  |  |  |  |  |  |  |  | 
E202 | 1 | 1 |  |  |  |  |  |  |  |  | 
Stave Status
Stave production re-start plan discussed with CERN, 5/14/2020
3 STAVEs ready for shipment
2 STAVEs ready for final tests
12 HICs are ready to be glued on STAVEs
3 HICs have to be bonded
Potentially ~20/84 available soon
Antonello, 5/14/2020
Plan: to produce remaining 84-20 =64 staves
- MVTX: 48 staves for the full detector
Possible restart date at CERN: June 2
29 wks left until the end of 2020;
64 golden modules to be produced:
  with 80% yield -> 80 modules
  2.75 / wk , completed by Jan/Feb 2021 seems within reach!
(Origin plan: complete by the end of 2020)

## Slide 5: Preparation for Staves Test and Detector Assembly at LBNL
Funding received at LBNL
Stave reception and testing (currently on schedule)
  ½ postdoc (Hanseul) on the project already.
  Transportation box design started.
    A default option, 10 staves/trip, is nearly ready.
    Working on better custom boxes to carry 12~14 staves/trip.
  Uncertainty: when can we fly to CERN in-person?
Issue with the assembly/metrology space
  ALICE ITS clean tent @ LBNL will most likely be reclaimed by engineering for other purposes.
  Will have to rearrange/find new space for stave testing and detector assembly.
  We have almost a year to prepare. Schedule risk is low but requires extra work.
ALICE Clean Tent @LBNL

## Slide 6: MVTX Services: Racks and Power
2E3: 2.32 kW
2E1:~0 kW
Power for individual
components
Several meetings with BNL integration team recently,
finalized the preliminary design for MVTX

## Slide 7: backup

## Slide 8: Where do we stand - PMP(12/2019)
Delays in FY-20:
Mechanical design & prototyping
  Final design review
Carbon structure fabrication
  Most facilities closed due to COVID-19
Insertion system design, beam pipe
  Active discussions with BNL CAD and sPHENIX OSI
  Final beam pipe design completed and reviewed recently
Power system
  Power boards fabrication – ordered
  CAEN power – ready to order
  Cables – waiting for final layout for length
Stave production &RU test
  CERN schedule
  International shipping
Today
5/8/20
Final design review -> late Fall 2020?

## Slide 9: Staves – QA plan inspections/test records
    The MVTX will receive fully tested staves from ALICE.
    The full history including testing results and measurements of all of the parts of the stave are preserved in the ITS databases.
    This data is available for download.
    For simplicity, we will continue using the ALICE database for the testing that happens at LBNL. The software is already set up for this interface.
    After completion of all testing, the full set of data for the MVTX staves could then be pulled from the ALICE server.
    In any case, a full record of building and testing results will be preserved.

## Slide 10: Detector Assembly - Procedure
Assembly: Staves 🡪 Layers 🡪 Half-Barrels
QA: Functional test at each step
Metrology: Map the sensitive volume positions
Tested
Staves
Sized
End wheels
Assembly tooling
Half-layer assembly
Sized
CYSS
Half-layer metrology
Half-barrel assembly
Half-barrel metrology
Tested
Power/RDO
Functional test
Functional test
Final validation test
Half-barrel full chain
Half-barrel delivered