## Slide 1: MVTX Upgrade Status: 09/02/2020
Detector mechanical design completed, vendor selection in progress
  Received 3 bids, under review, will make decision soon
  Within the estimated budget in the MVTX project
Readout system firmware and software updated
  RU and FELIX firmware synced to the latest versions in ALICE and ATLAS
  Implemented and tested slow control low-level interface to the readout system, user software underdevelopment
    SC through FELIX
    SC through CANBUS
Power board assembly and test in progress at LBNL
  All hardware received
Readout board test in preparation at ORNL
  Received RU and cooling plates
Stave production in good progress at CERN
  Transport box designed and produced, shipping options under discussion
Recent reviews
  MVTX (sPHENIX) AC/DC system reviewed
  MVTX cooling system design discussed with BNL engineers, initial system test planned at BNL
On-going study of possible reuse of MVTX for EIC
Two production staves

## Slide 2: 100 RU and PU Cooling Plates Produced and Delivered to LBNL and ORNL
All cooling plates for electronics produced at UT-A and LANL
Power board assembly and test in progress at LBNL
Readout Units and Cooling plates received at ORNL
  RU test in preparation
Cooling plate production at UT-Austin Machine shop

## Slide 3
 | STAVE-production summary table |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
IBSTAVE ID | HIC assembly | Ins. after glue | Bonding | Pull test (>=2 lifts + F <7g) | Ins. after bonding | HIC PWR test | Qualification test | Threshold cluster | HIC Matrix | HIC DTU | HIC+SF+C -> Stave | Stave PWR test | Stave test | STAVE metrology | Stave PWR test (long PWR extn.) | STAVE final test (PT100)
TOTAL | 48 | 48 | 46 |  | 46 | 46 | 36 |  |  |  | 26 | 26 | 26 | 25 | 22 | 19
A201 (326) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
A202* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK |  |  |  |  |  | 
A203 (144) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
A204 (158) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
A205 (167) | 1 | 1 | 1 | 4 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
A206 (204) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 2 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B201 (352) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B202* | 1 | 1 | 1 | 0 | 1 | 1 | 0 |  | Broken |  |  |  |  |  |  | 
B203 (114) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B204 (116) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | SILVER | CAN | 1 | 1 | 1 |  | 1 | 
B205 (115) | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
B206 (295) | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
F201* | 1 | 1 | 1 | 1 | 1 | 1 | 0 | ?? | PARTIAL | OK |  |  |  |  |  | 
F202 (230) | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
F204 | 1 | 1 | 1 | 5 | 1 | 1 | 1 | 2 | GOLD | CAN |  |  |  |  |  | 
G202 (234) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
G203 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN |  |  |  |  |  | 
F203* | dummy |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H202 (294) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H203 (302) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H204 (354) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H206 | 1 | 1 | 1 | 0 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
E204 (110) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
E201* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 3 | PARTIAL | CAN |  |  |  |  |  | 
E202 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | GOLD | CAN (bad driver) |  |  |  |  |  | 
E206 (101) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
H205 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | SILVER | OK |  |  |  |  |  | 
I202 (175) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
I203 (187) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 | 1 | 1
I204* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | OK |  |  |  |  |  | 
I205 (266) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 1
J201* | 1 | 1 | 1 | 0 | 1 | 1 | 0 | ?? | PARTIAL | OK |  |  |  |  |  | 
J202 (207) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 |  | 
J203 (245) 345 right | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN | 1 | 1 | 1 | 1 |  | 
J204 (252) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 |  | 
J206 (260) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 |  | 
K202 (122) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 
K203 (125) | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK | 1 | 1 | 1 | 1 | 1 | 
K204 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN |  |  |  |  |  | 
K205 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | GOLD | CAN |  |  |  |  |  | 
K206 | 1 | 1 | 1 | 0 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
L202 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN |  |  |  |  |  | 
L203 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN |  |  |  |  |  | 
L204 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | CAN |  |  |  |  |  | 
L205 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | GOLD | OK |  |  |  |  |  | 
J205 | 1 | 1 | 1 | 0 | 1 | 1 | 1 stuck pix in Chip6 unstable |  |  |  |  |  |  |  |  | 
I201 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | PARTIAL | CAN |  |  |  |  |  | 
L206 | 1 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |  | 
L201 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
From Stave Production meeting with CERN 08/27/20202
19 golden staves ready for shipping;
2nd batch of metrology done for 6 STAVEs. Ready for final tests in next week or two
6 HICs ready to STAVE gluing.
Expectations:
- production rate ~10 staves/month
- CERN can hold ~40 staves for ~5 weeks;
- We need to get them to US soon.

## Slide 4: COVID-19 Impacts on Schedule
Pre-COVID19 Schedule
Mechanical support design and production
  2~3 months delay in detector design and prototyping
  FDR(7/2020) postponed to a later time this year(TBD)
Readout electronics production
  Power boards, ~1 month dealy, but no impact on other schedules
  RU boards, 1~2 months delay, but no impact on other schedules
  Readout cables, designed and tested, waiting for the final mechanical design to fix the length

## Slide 5: More loog looking photos
Add photos of people working on hardware, testing etc.