## Slide 1: MVTX Readout and Control System
Power Board
Filtering Board
(Capacitors)
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Regulated Power
FELIX (or CRU)
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5 m
GBT Optical Links
9-sensor Stave
FELIX v1.5:
Arrived June
RUv1 prototype:
available: ~Aug/Sep.
Available:
~August
Prototype stave:
Arrived: June
sPHENIX GL-1 & GTM
DCS
CAN bus
Power supplies
Power
Trigger & Clock

## Slide 2: LDRD – MVTX Key Tasks/Milestones
RUv1.0/FELIX1.5 Integration
40MHz, 7/17-12/17
RUv1.x/FELIX2.0, 10MHz,
10/17 – 6/18
MVTX Design Review 7/6/2018
System test, cosmic & source
6/18 - 1/19
LDRD
MVTX: 1/1/2018 – 1/1/2022
Stave Production, procure FPGA, GBT etc.
8/18-4/19
7/17
10/17
10/18
10/19
Electronics Production
1/19-8/19
Test Beam, tracking performance
analysis, physics sim, NIM paper etc.
1/19 – 9/19
Today
BNL Director Review
7/10-11, 2017

## Slide 3: Experimental Tasks and Assignments
Interface to sPHENIX – Sho, Cesar, Ming
  Data format, trigger etc.
  Online monitoring and analysis
Readout firmware - Alex T., Sho, Mark
  RU and FELIX firmware development & test – Alex, Mark, Sho, Kun
  FELIX and sPHENIX DAQ, offline code - Sho, Alex T., Ming
  Evaluation test boards – Andi, Kun, Mark
Detector Control System (DCS) – Sho, Sanghoon, Xuan
  Slow control and monitoring of sensor status
  PS control and monitor, offline code
Single chip/stave evaluation w/ MOSAIC – Xuan, Alex W. Elena
  Chip performance, noise, threshold, gain, timing etc
  Stave performance
  Data analysis
  Cosmic telescope - Xuan
FireFly cable test w/ MOSAIC - Xuan, Ming
  Extension cable test
Mechanical system: Chris, Walt, a visiting student?
  Telescope frame
  Cooling
  sPHENIX integration conceptual design – Walt, Chris, Ming
Physics simulation : Sanghoon, Darren, Xuan, Alex W.
  Vertex finding
  B-reconstruction
  Full physics simulations
Stave production and test – Cesar, new hire? Collaborators
  Stave production
  Test staves, DAQ operation