## Slide 1: MVTX Telescope Update – 4/15/2019
4-stave readout is ready
  AlexT, Sho, Gerd, Cameron, Ming worked through the weekend and confirmed the 4-stave telescope setup is working properly
  Hardware
    2 RU v1.1
    1 Felix v.2.0
    sPHENIX GTM v0
    1 8-m (2.6 + 5.3m) new cable (sPHENIX config.), (1.2+8.8m cables will come later)
    3 5-m SamTec blue cable
    Updated firmware and software
  Raw PRDF files available for software development and test
    Sho and Sanghoon are uploading the data files and the updated decoder to RCF
    Online decoder is ready (Sho)
Telescope box mechanical parts arrived – to do’s
  assembly work started
  Test cooling with dummy staves
  Telescope assembly
Alternative TB plan later at LBNL – in August
  50MeV proton beam
  Asked for about 24 hrs beam time

## Slide 2
sPHENIX GTM,
integrated into FELIX
8-m sPHENIX Readout Cable: AWG30
sPHENIX GTM v0.1

## Slide 3
4 staves
4 staves:
one 8-m sPHENIX cable
Three 5m SamTec default
1st RU: connected to 8-m sPHENIX cable
2nd RU: connected to 3 5-m cables
10m sPHENIX cables will be tested when available
2 RUs
PU

## Slide 4
System demo
Telescope parts
arrived at LANL

## Slide 5: BNL sPHENIX Review Summary
Here is a brief summary of my discussion with Ed this afternoon. Also, Flemming kindly sent me a copy of iTPC PMP doc as an example for MVTX, attached.
1. prepare for a MVTX cost & schedule review (sPHENIX internal or at a higher level) in ~mid June after the PD2/3 review (5/29-31), update the P6 with the latest C&S developed after the MVTX/HF workshop at LBNL in March.
2. update project management plan (PMP), risk registry, WBS dictionary and BoE documents. sPHENIX project team will help to enter them into P-6
3. submit funding breakout to sPHENIX/BNL management for FY19, for LANL, MIT, LBNL, UT-A et al, including design and test/QA efforts etc. Ed will work with BNL management to get fund transferred as soon as possible for FY19.
4. wire bonds – why ALICE has decided not encapsulating the wire bonds? I know the intrinsic vibration is NOT an issue for ALICE and sPHENIX.
5. MVTX C&S review~ Mid/late of June
BoE:
https://docs.google.com/document/d/1l-xytelgTuUtmABSQHs9fd1e5e8LQ-vFhSFk0qhM2Z4/edit?usp=sharing
Risk Registry:
https://docs.google.com/spreadsheets/d/1UzIOnXfAwbjxUcnrQVnFLN20niq43x2v2J2epF10bjg/edit?usp=sharing

## Slide 6: MVTX TB @Fermilab May 22 – 29, 2019 03/19/2019
Essential goals for LDRD:
  Demonstrate full readout chain with new “final” hardware at high rate (~15kHz)
    4 staves + 2 RUs + 1 PU + 1 FELIX + RCDAQ
  New “final” hardware
    Production staves, RU(1.1), FELIX(2.0), PU, readout cables, stave cooling
  Reproduce last TB results on tracking efficiency and spatial resolution
    Offline simulation and analysis
Stretch goals for sPHENIX:
  sPHENIX GTM (v0) integration (LANL+BNL/DAQ)
  Online monitoring and slow control (via USB, MIT/GSU et al)
  Scan stave material budget (requires low E beam, sPHENIX, ALICE/ITS, later at LBNL?)
  Exercise “Continue Readout” mode and offline data decoding (sPHENIX/DAQ)
Summary of timeline
  Ship telescope to Ferimlab, by 5/10(Friday). It will take 1 week to get them there
  Travel to Fermilab. 5/19 (Sunday)
  Preinstallation test and setup, training, ORC review etc. 5/20-21(Mon-Tue)
  Installation at TB facility beam line 5/22 (Wed, day time)
  Operation and data taking 5/22 – 5/28 (all evenings)
    Online monitoring & offline data analysis 5/22-28
  Disassemble setup 5/29(Wed), and ship the detectors to LANL
    Possible extension for more data taking with TPC/INTT if needed, June 12 - July 8
2 shifts per evening
- 6PM - midnight
- Midnight - 6AM
~3 people per shift

## Slide 7: Preparation for Test Beam in May
Firmware & software update:
  2x (2-stave + 1 RU) -> 1 FELIX - AlexT, Sho, in progress, to finish by ~ 4/7/2017;
  PU integration, controls and monitoring via USB - Sho, Cameron, Ming, GSU/Xu et al
  GTM integration - Sho, Alex, Gerd + BNL, done!
  8m SamTec cables & transition boards – Gerd, Cameron, Sho, Ming … ; plan-B ready (5m cables)
  VME cage hosting 2RU + 1 PU, almost done!, Sho
Telescope box & cooling -
  Box design and fabrication - Abel, Hubert, Matt; Chris sent request for quote (3/19)
  4 stave installation - Hubert, Abel, Ming
  Cooling test & evaluation - Matt, Sho, Abel, Ming
System integration & test at LANL in April/May. -- training for operation, debugging etc.
  Setup cosmic trigger – Matt, Xuan et al
  System test – Cameron, Yasser, Sho, Gerd, Ming… all
Offline analysis -- can use more help from sPHENIX
  4-stave telescope geometry & simulation – Yasser, Ming, (Sanghoon, Darren)
  Offline analysis – Yasser, Cameron, Sanghoon et al
  Use old TB data for analysis – training for all
    4-stave decoder is ready (Sho)
  2018 TB data analysis:
    https://wiki.bnl.gov/sPHENIX/index.php/Test_beam_in_2018_at_FNAL
Online monitoring & slow control
  GSU & MIT, Sho/Ming, Jo’s - help
  (V,I,T) of staves and PU/RU via USB
ORC docs --- Sho
Shipping, training, schedule, travel, installation --- Ming et al

## Slide 8: Manpower & Schedule
Activities
  Ship telescope setup to Fermilab, latest 5/10(Fri),
    Hand-carry 4 staves and electronics boards (RU, FELIX etc)
    Travel to Fermilab on 5/19 (Sunday) or earlier
  Preinstallation test and setup 5/20-21(Mon-Tue) – mostly LANL folks
    Full time: Yasser, Hubert, Cameron, Walt, Ming, Xu(GSU), Gerd …
    Part time: Xuan, Kun, Matt
  Installation at TB facility beam line 5/22 (Wed):
    LANL folks + sPHENIX helpers
  Operation and data taking 5/22 – 5/28 (all evening): LANL + sPHENIX helper
    Full time: Yasser, Hubert, new PD/Cameron, Ming, Walt, Xu (GSU), Gerd
    Part time: Xuan, Kun, Matt, Cesar, Darren(TBD), Sanghoon, other sPHENIX folks?
  Online monitoring & offline data analysis 5/22-28: LANL + sPHENIX helpers
    Full time: Yasser, Hubert, Cameron, Xu (GSU), Ming …
    Part time: Xuan, Kun, Matt, Other sPHENIX helpers
  Disassemble setup 5/29(Wed), and ship the detectors to LANL: - mostly LANL folks
    Yasser, Hubert, Cameron, Ming, Kun et al
“Remote” helpers:
  Alex T., Sho, Jo et al
  sPHENIX offline/online analysis
Preparation work & training at LANL
  Build 4-stave telescope in Feb/Mar
  Test cooling system, evaluate
  Operate telescope with cosmic rays in April
  Offline data analysis
  Detector online monitoring, V, I, T etc.
  Lab training for operation and analysis, RU/FELIX, RCDAQ etc

## Slide 9: TM6.2 Room Layout
MVTX Telescope setup on the motion table:
MVTX telescope
MVTX crate (2-RU + 1 PU)
3.3V HP PS
One Linux server/RCDAQ in CH

## Slide 10: System overview
Power Board
Data (9x1.2Gbps), Clock, Control/Trigger
Regulated power
Readout Unit
Front End
FELIX
Back End
Data (3x3.2 Gbps)
Control
Trigger
ALPIDE Sensors
FPC
Cold Plate
~8m twinax
GBT Optical Links
9-sensor stave
Power supplies
Power
Clock/Trigger
Interaction Region
Experimental Hall
Counting House
DAQ and Slow Control
PCIe
sPHENIX GTM
USB

## Slide 11: More information

## Slide 12: 2019 test beam: 4-stave telescope
Scheduled for May 22-29, at Fermilab
Additions compared to the 2018 test beam:
  Staves (from single chips)
  Full-length MVTX signal cables (from 5 m off-the-shelf cables)
  FELIX v2.0 (from v1.5)
  Cooling system
  Power board
  sPHENIX GTM
Full test of all components of the MVTX detector - LDRD “stretch goal”
Sho’s talk

## Slide 13: Mechanical design
Telescope box design completed, sent for fabrication
  One stave can be offset by (0.5,0.5)cm for material scanning

## Slide 14: ALICE/ITS Signal cable design
The Samtec twinax cables carry clock (40 MHz), control (40 Mbps bidirectional), data (9x1.2 Gbps)
ALICE is using halogen-free cables (32 AWG, LDPE dielectric) due to CERN LSZH requirement; 2.65 + 5.3 m cables have been tested and are now in production
Stave
Stave
RU
RU

## Slide 15: sPHENIX MVTX Cable testing
BNL has approved non-halogen-free cables (30 AWG, FEP dielectric); improved signal integrity
sPHENIX cable run estimates are converging: 1.4 + 6.5 m
We have Samtec quotes for 1.2/2.65 + 5.3/8.8 m (total length 6.5 - 11.45 m), will order soon
We will qualify these cables using stave and RU (bit error rates, statistical eye), and scope/network analyzer
We will test full-length MVTX cables in the next months