## Slide 1: FY18 LDRD Achievements: a Brief Summary
Experimental progress:
  MVTX full proposal submitted, Feb 2018
  Built a 4-MAPS telescope, Feb, 2018
  Fermilab test beam confirmed performance, Feb – Mar, 2018
  MVTX accepted by BNL/ALD for baseline, May, 2018
  BNL Director’s MVTX Stave/RU Production Readiness Review, July 19-20, 2018
  Mechanical system integration MVTX + INTT + sPHENIX
  Updated MVTX GEANT geometry, MVTX + INTT tracking optimization
Theoretical progress:
  Papers published/submitted
  Simulation packages developed, preliminary results

## Slide 2: sPHENIX LDRD FY19 Plan – Experimental Work
Key R&D Tasks and deliverables
Manpower & FTE
Procurement
Transition plan

## Slide 3: Experimental Milestones
RU behind
Schedule;
Replacement for CRU
MVTX/INTT
Test Beam

## Slide 4: Experimental activities & deliverables
LDRD deliverables
R&D of extended HICs/staves with long power cables
  CERN and LANL, by ~10/2019 (before stave production)
Complete a 4-stave telescope construction
  Readout and controls
  Mechanical support frame
  Cooling system test
  Cosmic ray test
Full telescope system test with test beam
  Test beam at Fermilab (or other facility), ~Mar 2019
  Complete test beam data analysis, ~2 months after the run (May 2019)
  NIM paper submitted 9/2019
ALPIDE operation optimization
  run laser scanning system, by summer 2019
Transition into sPHENIX project
  Trainings on sensor detector construction and QA at CERN, develop MAPS detector expertise
  sPHENIX RU and Staves production planning
Extended goals – things like to do
Full readout and control system integration
  8 RUs(Fibers) + 1 FELIX + RCDAQ + PU
Feasibility study for open heavy flavor trigger (new extended goals)
  Physics and detector simulations
  Initial R&D on trigger system development based on RU and FELIX
Run the full CAEN power system

## Slide 5: Timeline: LDRD Deliverables and Extended Goals
10/19
12/19
2/19
8/19
10/19
6/19
4/19
Stave production;
Extended FPC PWR
Assemble 4-stave
Telescope w/ cooling
Fermilab Beam Test, data analysis
ALIPIDE operation optimization, LANL/CERN
NIM paper
submitted
Telescope firmware/software development
RU v1.1 + FELIX v2.0 + PU integration
(8) RUv2 + (1) FELIX v2 + RU integration
CAEN power system + RU integration
develop MAPS detector expertise, detector/physics simulations, B-tagging, preparing for transition to sPHENIX MVTX project
Test cooling system
Open HF Trigger simulation + Firmware Development, RU + FELIX v.20

## Slide 6: MVTX Readout Electronics
Power Board
Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Front End Electronics
Regulated Power
Back End Electronics
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5-10 m
GBT Optical Links
9-sensor Stave
sPHENIX GL-1 & GTM
DCS
CAN bus
Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
RUv1.0: ~10/2017
FELIXv1.5:
6/2017
Stave: 06/2017

## Slide 7: MVTX 4-stave telescope

## Slide 8: Experimental FTE
Ming – 0.3
Cesar – 0.1
Sho – 0.5
Yasser – 1.0
Xuan – 0.1 (0.2?)
Walt/Chris – 0.1
Mark – 0.2
  A visiting student?
Alex T. – 0.1~0.2
Alex W. ~0.5
0.5 staff + 1.5PD + 0.1 ME + 0.2+ EE

## Slide 9: Procurements Plan
From CERN
  10 final RUs: $40K
  5 final staves: $70K
  Fiber/Control cables and other misc. items: $10K
  1 final PU and cables: $10K
Other vendors
  CAEN cables and controls + DCS computer: $10K
  Other test equipment: $10K
  FPC power extension cables etc.: $10K
  Trigger boards/FELIX: $20K
  Linux server for trigger system: $10K
Other contract
  UT-Austin: $30K
  Visitors/student/postdoc: $30K
Travel to CERN
  $50K
Femrilab test beam
  $20K
MVTX mechanical mockup
  $10K
FPGA and other Licenses:
  $10K
~$130K
~$100K
Total M&S: ~$300K
~$60K

## Slide 10: FY19 Budget
Ming – 0.3
Mark – 0.2 (student?)
Cesar+Xuan – 0.2
Yasser – 1.0
Sho - 0.5
Alex T. - 0.2
Walt/Chris – 0.1
M&S: 300K
Travel to CERN: $50K
FY18 carry over: $90K
- 0.1 Xuan
0.1 Cesar
0.1 Walt/Chris
Student

## Slide 11: sPHENIX LDRD FY19 Plan – Theoretical Work
Key R&D Tasks and deliverables
  Update LDRD project file
Personnel & FTE
Procurement plan
Transition plan

## Slide 12: Theoretical Milestones