## Slide 1: To DO List & Timeline
sPHENIX Integration issues
  “5m” SamTec Cable study @LANL
    Signal & noise vs length
  FPC extension R&D @CERN
    Additional ~<10cm, September?
  FPC Power extensions R&D @LANL
    Total length ~50-100 cm, now ~ Summer
    Blank 50cm FPC from CERN
  MVTX/INTT integration CERN/LANL
    Mechanical and electrical
    Extended goals
Stave production and ITS/IB detector test @CERN
    May – Dec, 2018
    Postdoc identified, starting ~July 1, 2018
    ~3 staves in May/June?
RU production & Test
  June ?
Readout and Controls
  3 Ruv.1. arrived
    3+ RU readout per FELIX
  3 stave readout per RU
    Summer
  Scrubbing
  Slow control and monitoring
    V, I, T …
ALPIDE optimization
  Laser scan
  Cosmic/source
  HF trigger study
Cooling test
  Negative pressure system

## Slide 2: Timeline: FY18
9/2018
4/2018
------ ALPIDE OP, Laser ------------------------------------------ Sho/Alex/Ming
----------- 3RUv1.1 + FELIXv2.0 ------- Slow Control ---------------------
----------------RU+FELIX Firmware update -------
------ MVTX Funding & Schedule ---Ming/Dave---
---- FELIX v2.0 (1) (2) ---
--------- FPC PWR extension & MVTX/INTT integration ------------------------------
---60cm FPC?
----------------- RU v2.0/final test & QA/all ---------- sPHENIX Stave Production ----
--------- CANE PS integration test --------
6/2018
7/2018
5/2018
8/2018
------ cooling test --------------Chris/Darren/Xuan-------------------
--------~3 staves --------------------------------

## Slide 3: FY18+ LDRD+MVTX/sPHENIX Schedule & Goals: Updated 4/2/2018, after meeting with ALD and CERN visit (ALICE Production)
Readout:
  10/1: ALPIDE + KC705 + FELIX1,5 + RCDAQ, establish communication chain
  11/30: ALPIDE + RUv1.0, set config and readout data
  12/30: ALPIDE+RUv1.0 + FELIX1.5 + RCDAQ, stable operation @15kHz
  1/2018-6/2018: RUv1.x + FELIX2.0 + RCDAQ, stable operation @15kHz
  Sho, Alex, Mark, Kun, Ming
Sensor production, evaluation and optimization for sPHENIX
  5/2018-9/2018: stave production at CERN
  3/2018-5/2018: setup laser system and optimize ALPIDE operating parameters
  Xuan, Sho, Cesar, Ming
Telescope:
  1-3/2018: mechanical frame assembly,
  3-6/2018: cooling system test
  5-9/2018: 4-staves and 4 RUv1.x installation and readout integration
  6-9/2018: full system assembly and cooling integration
  6/2018-1/2019: cosmic run, system test, data analysis
  Chris/Walt, Ming, Darren, Sho, Alex, Kun, Cesar and all
MVTX technical readiness reviews (sPHENIX internal?)
  Pre-review in early 6/2017?
  7/2018: stave production
    <- tied to MVTX stave production at CERN, ~ Aug 2018+
  4/2018: electronics production : moved to 4/2018! Bridging fund required!
    <- tied to ALICE RU production schedule, ~Jan 2019
  Ming, Cesar and all
Test beam and analysis at FERMILab: 1/2019 – 9/2019
  Test beam I @Fermilab and analysis: 3-5/2018
  Test beam-II @Fermilab, 1-3/2019
  Data analysis and NIM paper 4-9/2019
  Ming, Sho, Kun and all
MVTX goals
  MVTX proposal ready for submission 1/2018
  Ready for MVTX DOE review, ~8/2018
  MVTX stave production, 8+/2018, 9 months
  MVTX electronics production, 4+/2018, 6 months
  Ready for installation: 4/2022
  Installation starts in sPHENIX: 6/2022 [per GY]
  Installation completed: 9/2022
  Ready for beam : 1/202
sPHENIX milestones
  CD-1 Review: 5/2018
  CD-1 authorization: 7/2018
  CD-2/CD-3b: summer 2019 (define the baseline)
  Ready for installation 4/2022 (MVTX 6/2022, the last one)
  Installation completed: 7/2022
  1st beam: 1/2023
  CD-4: 1/2024
  INTT ready for installatino: 4/2022
FPC extension R&D and MVTX/INTT integration: 4-9/2018
  FPC extension at CERN: ~9/2018 (can do early in May?)
  FPC power extension at LANL: 4-9/2018
  MVTX/INTT mechanical integration
  Ming, Sho, Alex, Walt et al
LDRD/MVTX Simulation and analysis
  GEANT detector response and simulation
  Physics sim and analysis, b-jet tagging
  Sanghoon, Darren, Alex W. et al

## Slide 4: LDRD – MVTX/sPHENIX Key Tasks/Milestones (from July 2017)
RUKC705)/FELIX1.5 Integration
40MHz, 7/17-12/17
RUv1.x/FELIX2.0, 10MHz,
11/17 – 6/18
MVTX Design Review 7/2018
System test, cosmic & source
6/18 - 1/19
LDRD
MVTX: 2018 – 2023
Stave Production, procure FPGA, GBT etc.
8/18-4/19
7/17
10/17
10/18
10/19
Electronics Production
1/19-8/19
Test Beam, tracking performance
analysis, physics sim, NIM paper etc.
1/19 – 9/19
Today
BNL Director Review
7/10-11, 2017