## Sheet1
MVTX LDRD Tasks and Schedule
| Key Tasks | targeted completion date | who | FTE effort etc
MOSAIC Test Bench
| setup 2nd MOSAIC test bench | by 08/2017 | Elena, Sho, Xuan
| Long FireFly cable test, 7, 10m; Eye diagram; BNL safety code etc., SPICE sim | by 09/2017 | Xuan, Cesar, Pat, Sho
| Optimization of ALPIDE operation: shaping time, noise rate, cable selection, laser scan | by 10/2017 | Xuan, Andi, Cesar, Pat, Ming, Walt
| Short FireFly extension cable test, connectors | by 11/2017 | Xuan, Walt, Sanghoon
| Short CERN extension PCB production and test, help from CERN? | by 12/2017 | Sanghoon, Walt, Xuan,
CAEN Power Supply
| setup and operate PS | by 08/2017 | Sho, Pat, Sanghoon
| remote contorl software/GUI | by 9/2017 | Cesar, Sanghoon, Pat
| Chiller + Colling | by 10/2017 | Hubert, Alex W.
| Power Supply 48V, 2 chs | by 8/2017 | Pat, Kun @Fermilab | we have a 50V PS at Fermilab
Telescope Mechanics
| Mechnical frame/box desgin and assembly | by 10/2017 | Chris, Walt
| Cooling system desgin, assembled and tested w/ a dummy stave frame | by 11/2017 | Chris, Alex W.
FELIX intergration
| FELIXv1.5 installation and operation | by 8/2017 | Sho, Mark
| FELIXv1.5 DMA, sPHENIX RCDAQ integration | by 8/2017 | Kun, Sho, Cesar, Alex T., Ming
| FELIXv1.5 and RU GBT link firmeware | by 10/2017 | Alex T., Sho, Mark, Kun
| FELIX v1.5 firmware development | by 12/2017 | Altex, Mark, Sho
| FELIXv1.5 firmware validation w/ FELIX selftester | by 11/2017 | Kun, Alex T., Sho, Andi, Mark
| FELIXv.2.0 to sPHENIX Timing and Trigger | by 1/2018 | Alex T., Mark, Sho, Kun | FELIX v2.0 availabe ~1/2018?
| FELIX v2.0 interface with sPHENIX TTS integration ; PHENIX GTM? | by 4/2018 | Mark, Alex, Ming
| FELIX v2.0 and RUv1.X integration | by 6/2018 | Sho, Alex, Mark | 7/2017 Review
RUv1.0 integration |  |  |  | RUv1.0 availble ~Aug 2017
| MAPS and RUv1.0 GBT link firmware development (modify from ALICE) | by 10/2017 | Alex, Sho, Mark, Ming
| RU - FELIX v1.5 GBT link firmware and test | by 12/2017 | Alex T., Sho, Mark
| RUv1.0 firmware validation w/ injected MAPS data from stave | by 12/2017 | Sanghoon, AlexT., Kun
| Full load test of FELIX2.0? BNL test? Mockup test with FELIX 1.5, 24 fibers; 8RU+8Staves? | by 4/2018 | Mark, Alex,
PU and Slow Control System
| Power distribution baord unit (PU) | by 10/2017 | Xuan, Sho, Kun | Power distribution board availabe ~ Aug 2017
| MAPS-RU-FELIX system integration w/ Slow Controls and Power Unit | by 12/2017 | Xuan, Matt D., Pat, new staff, Ming
Cosmic ray test
| GEANT simulaiton package for telescope | by 9/2017 | Darren, Hubert, Cesar
| Assemble the 4-layer of MAPS telescope for cosmic ra with full readout chain | 12/2017 - 6/2018 | Ming, new staff, and all
| offline de-code & QA | by 12/2017 | Darren, Sho, Cesar, Ming
| offline analysis software, alignment | 12/2017-6/2018 | Darren, Kun, Xuan, Alex W.
| Telscope trigger | by 12/2017 | Xuan, Hubert
| full readout chain @40MHz |  | for DOE proposal
Offline effort
| Track reconstruction and Vertexing | by 12/2017 | Sanghoon, new staff
| B-jet tagging | by 12/2017 | Darren
| Physics inputs | by 12/2017 | Cesar, Ming, Ivan
MVTX Proposal |  |  |  | submission ~ Jan 2018?
| Cost, Scheudle and Risk | by 12/2017 | Ming, Dave, Mark, Walt
| MVTX collabaoration |  | Ming, Cesar, new staff et al
| Conceptual mechanical desgin |  | Walt, Chris + MIT + LBNL
Fermilab test beam |  | 1/2019-9/2019 | new staff, and all
| shipping to Fermilab | by 1/2019 |  | w/ sPHENIX test beam run
| running experiment |  | new staff and all
| data analysis |  | new staff, Darren, Xuan, Sanghoon
| NIM paper |  | new staff and all