## WBS structure
WBS | Task Name | Material Risk | Labor Risk | Description | Mitigation
1.5.2 | sPHENIX Mechanics Integration | M3 | L3 | ALICE design | early collaboration/training with ALICE techs.
1.5.2.2 | Cooling system | M3 | L3 | ALICE design, FVTX experience. | Early R&D and ALICE collaboration.
1.5.2.3 | Safety Systems | M2 | L2 | ALICE design and FVTX experience. | Early R&D and ALICE collaboration.
1.5.2.4 | Stave Assembly Tooling | M3 | L4 | Similar FVTX experience. | Early R&D and ALICE collaboration.
1.5.3 | Mechanics Final design review | M2 | L3 | Experience with FVTX and ALICE design. | Early R&D and ALICE collaboration.
1.5.4 | MAPS detector final design | M2 | L3 | Experience with FVTX and ALICE design. | Early R&D and ALICE collaboration.
1.5.5 | Detector Production and Assembly | M4 | L3 | ALICE design. | Early R&D and ALICE collaboration.
1.5.5.2.1 | Stave Procurements | M4 | L3 | ALICE design and R&D. | Early R&D and ALICE collaboration.
1.5.5.2.1 | Non-CERN procurements | M3 | L3 | FVTX experience. | Early procurement.
1.5.5.3 | Assembly and testing at BNL | M3 | L3 | FVTX exerience and ALICE design. | R&D preparation.
1.5.6 | Installation | M3 | L3 | FVTX experience. | R&D preparation.