## Slide 1: MAPS Inner Barrel
Michael P. McCumber
Los Alamos National Laboratory

## Slide 2: MAPS Performance Specifications
Inner Silicon tracking driven by heavy flavor jet performance
Track acceptance: -1.1<η<+1.1 and 0<φ<2π
Minimum vertex acceptance: -10 cm < zvtx < +10 cm
Meet or Exceed a 30% b-jet efficiency at 30% b-jet purity
  defined by the CMS of b-jet figure-of-merit
Minimum track efficiency: >95% of all charged particles
Minimum DCAXY resolution: < 70 microns
Resolve multiple collisions vertexes at large collider luminosities
Maintain track momentum resolution:
  Upsilon mass: dp/p <1.2% for 4 < pT < 10 GeV/c
  Jet Fragmentation: dp/p < (0.2% x p) for pT < 40 GeV/c
Maintain small rate of tracking ambiguities: fake tracks

## Slide 3: sPHENIX MAPS Description
TPC
MAPS
ALICE ITS Inner Barrel Staves
  near-clone of ALICE IB
  3-layers in a similar 12/16/20 configuration
  each stave has 9 sensors
  each stave ~0.3% X0
ALPIDE Sensors
  28 x 28 um pitch
  99.9% efficiency
  2-4 usec integration time
  on-pixel digitization
sPHENIX Readout
  Custom FEM-based on ALICE Readout Unit
Why select MAPS?
Minimize Risk, Maximize Physics
Design: ITS IB exceeds our requirements, additional physics
Savings: 15+ years of ALICE R&D
Timeliness: Extend the CERN production (2017 & 2018)
Leverage: US institutions interested in EIC MAPS R&D

## Slide 4: sPHENIX MAPS Geometry I
Inner Barrel Stave
1.5 cm x 27 cm
ALPIDE Generation-4 Sensor
1024*512 = 0.5M channels / sensor
1.5 cm x 3.0 cm x 50 um
9 sensors / stave

## Slide 5: sPHENIX MAPS Geometry II

## Slide 6: MAPS Electronics
ALICE readout path
sPHENIX readout path
MAPS FEM
busy out
DCM2
EvB
existing design
existing sPHENIX design
new custom design,
starting with ALICE boards
existing ALICE design
trigger in

## Slide 7: Design Drivers
Why are three layers needed for sPHENIX?
  Additional anchoring points are helpful for: secondary vertexing, pattern recognition, pileup rejection, self-alignment. Reduces need for addition tracking between MAPS and TPc. Studies of fewer layer options are still on-going.
Why not change the stave design to do X?
  The ALICE design is well-suited for our physics and exceed our coverage needs. Potential cost savings by shortening the stave are countered
  by redesign costs and delays. Cooling tube design requires duplicating ALICE water cooling system

## Slide 8: L3 Project Scope
Covered by MAPS project
  MAPS R&D effort
    4-stave Prototype Tracker with ALICE Readout
    sPHENIX readout electronics design & prototyping
    Mechanics design & prototyping
    Servicing design (safety, cooling, power, etc)
  Construction deliverables
    68 staves assemblies for 3-layer IB (CERN/sPHENIX)
    Mechanical assembly fabrication (LBNL)
    Front end electronics fabrication (x68) (LANL)
    Half-Barrel assembly, metrology (BNL)
  Hand-off for Installation at 1008
    LDRD deliverables

## Slide 9: Schedule Drivers
sPHENIX Readout Research and Development
  Custom readout will begin with ALICE design
  Multiple prototyping rounds expected
  Full system test needed before production
ALICE ITS Inner Barrel Production
  Mid-2017: Arrival of 4-staves for R&D development
  Mid-2018: Natural end of ALICE production
  Late-2018: CD-3 begins

## Slide 10: Resource/Cost Drivers
Building a stave assembly lab from scratch is costly and time consuming (+$1-2M cost, +1 project years)
  Secure access to CERN facility via MOU to extend the assembly line in Switzerland
Some project deliverables outside LANL expertise / capabilities
  Bring in large outside institutions
    LBNL for Mechanics, MIT for Stave assembly
    Focus LANL on readout speciality
  Bring in small outside institutions to provide add. manpower

## Slide 11: Organization
Edward O’Brien
Project
Coordinator
Ming Liu
MAPS L3
Manager (1.3.x)
Tom Hemmick
TPC L3
Manager (1.3.z)
Itaru Nakagawa
Strip L3
Manager (1.3.y)
Tracking L2
(1.3)
John Haggerty
Project Manager - Science
James Mills
Project Manager - Engineering
Don Lynch
Chief Engineer
Irina Sourakova
Project Manager - Controls
Robert Ernst
Project Manager - Resources

## Slide 12: Budget and Labor Profiles

## Slide 13: Timeline of Major Tasks
Key Dates
  Start of LDRD funding: October 1 2016
  Arrival of 4-staves: mid 2017
  Full System Readout Test: late 2017
  Readout Electronics Design Finalization: early 2018
  End of ALICE ITS Inner Stave assembly: mid 2018 (latest ITS update)
  Test Beam Operation: early 2019
  Ready for CD-2 by July 2018
  Ready for CD-3 by August 2018 (sPHENIX CD-3b date)
  Inner Barrel Stave Construction (9 mo): late 2018 to mid 2019

## Slide 14: Project Status
  Funded!
Funding Breakdown:
  ~1/3 M&S
  ~1/3 Experiment Staffing
  ~1/3 Theory Staffing
Funding Profile:
  $5M spread over 3 years
  starting in Oct 2016
Proposals judged on many factors, coverage from multiple divisions, strong Theory is necessary to success
M&S total: $1.5M
Total Experimental Support: $3M
Engineering: $0.5M
Purpose: Obtain key R&D support

## Slide 15: Issues and Concerns
(1) Mating the ALICE and sPHENIX production schedules
  Problem: now only ~1/4 year gap between ITS and CD-3
  Strategy: train experts in-situ, maintain production line at low effort, & ramp back up, look for opportunities to close the gap
(2) Long Development Time for Readout Electronics
  Problem: Full custom board design may be required
  Strategy: Early review of options, early start on design if full custom boards are needed.
  Plan-B: Readout one stave with prototype electronics as proof-of-principle for technical review

## Slide 16: Backups

## Slide 17: ALPIDE Pixel Technology

## Slide 18: ALPIDE Operation

## Slide 19: ALPIDE Readout