## Slide 1: WBS 1.12 MVTX
A separate MIE as an upgrade project
  Full proposal to be submitted by BNL
  Expand HF physics program, ~science case (CD-0)
  BNL Director’s review later this spring/summer, science ”CD0” + C&S “CD1”
MVTX project file: Cost & Schedule updated, 3/21/2017
  LANL & LBNL, detailed labor profile
  MIT, to be updated
  Other institutions, in progress
  Project webpage:
  https://p25ext.lanl.gov/maps/mvtx/mvtx.html
On-going discussion between BNL ALD and LANL/LBNL/MIT NP managers
  1st managers meeting last Friday, follow up meetings next week
  DOE wants to keep the fund below $5M, possibly some redirected $$

## Slide 2: MVTX R&D Status
Readout R&D
  Workfest @UT-Austin, 4/19-20
  LANL MOSAIC test bench in progress
  RUv1 available in May
  CRU being prototyped with Altera evaluation boards; BNL/ATLAS FELIX being evaluated as an alternative
Stave production for LDRD telescope
  Assembly and test at CERN, May – Sept. 2017
Project file – work in progress
  Detailed commitment from each institutions etc
Tracker integration task force
  MVTX + INTT + TPC mechanical integration

## Slide 3: Scope of sPHENIX MIE
The MIE Cost Range 30-35M AY$ in Mission Need (CD-0) approval document

## Slide 4: sPHENIX Schedule
Test Beam at FNAL(1st round prototyping) Feb 2016
CD-0 Sep 2016
Test Beam at FNAL(2nd round prototyping) Jan 2017
CD-1 Director’s Review May-Jun 2017
OPA-CD-1/CD-3a Review Nov 2017
CD-1/CD-3a authorization Dec 2017
All Preproduction R&D and Design complete Jun 2018
OPA- CD-2/CD-3b review Jun 2018
CD-2/CD-3b authorization Aug 2018
sPHENIX installation begins in 1008 Facility Apr 2020
sPHENIX Installed, cabled, ready to commission Apr 2021
First RHIC beam for sPHENIX Jan 2022
The Resource-loaded Schedule contains 8.5 months of float to Jan 2022