## Slide 1: MVTX Cost & Schedule (WBS 3.2)
Dave Lee/Ming Liu
April 9-11, 2019
BNL

## Slide 2: MVTX C & S - Assumptions
LANL 04/10/19
2
Technically Driven Schedule, no manpower smoothing
Self contained project, funding available when needed
Tied to sPHENIXschedule
Risk Based Contingency at 20 - 50%
Electronics cost based on as built experience, FELIX and RU support boards
Procurements assume funding is available
Resource hourly rates are fully burdened with 3% inflation increase each FY
Electronics ready for production on day one due to LDRD effort
Schedule has not been smoothed, 9 month contingency
Staves and Readout Unit (RU) not in Schedule, separate cost
Some changed when input to P6

## Slide 3: Cost and Schedule - Summary
Now in P6, 2/2019, pre-LBNL C&S

## Slide 4: MVTX Schedules and Milestones
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Installed 2 half-barrels
@sPHENIX IR;
Ready for beam;
sPHENIX day-1 run
FELIX
production
Stave testing, half-barrel assembly @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Detector & interface design
Design & procure
support structure
Procure insertion
sys to sPHENIX rails
Today
Complete detector
system test @BNL Lab
Procure & assemble
cooling system
Construction
MVTX Review

## Slide 5: Milestones
Milestone | Date
MVTX Preproposal Finish | 4th Qtr FY 2017
MVTX Proposal Review | 3rd Qtr FY 2018
Stave Procurement | 3rd Qtr FY 2019
Start Construction | 3rd Qtr FY 2019
MVTX Final Design Review | 1st Qtr FY 2020
Half Barrels Assembled | 2nd Qtr FY 2021
Installation Finished | 4th Qtr FY 2022
Ready for Beam | 1st Qtr FY 2023

## Slide 6: Resource Distribution
Chart: Resource by Hours
| FY2019 | FY2020 | FY2021 | FY2022 | FY2023
PHYS | 1787 | 5076 | 825 | 656 | 120
ENG | 1997 | 4178 | 460 | 440 | 160
Tech | 999 | 1698 | 277 | 472 | 160
GRDSTD | 96 | 1036 | 864 | 0
Chart: Hours
| PHYS | ENG | Tech | GRDSTD
hours | 10726 | 7039 | 3116 | 2460
To be updated with Jan. version

## Slide 7: Funding Profile
2/2019, pre-LBNL C&S

## Slide 8: Major Cost Items
WBS | Task Name | Cost (K)
3.2.3.2.2 | End Wheels | $349
3.2.3.2.3.2 | CYSS Cylindrical Structure | $216
3.2.3.2.3.3 | Service Barrel (SB) | $243
3.2.2.4 | Power System | $217
To be updated to Feb version

## Slide 9: Electronics Example low contingency
 | WBS | Cost (K) | Contingency | Basis
FELIX | 3.2.2.3 | $97 | 25% | As Built*
Power Board | 3.2.2.4.1 | $129 | 25% | As Built*
Power Supply | 3.2.2.4.2 | $88 | 25% | CAEN
Total Cost = $401 K
As Built means item is a production unit
To be updated to Feb version

## Slide 10: Carbon Structures Example high contingency
 | WBS | Cost (K) | Contingency | Basis
End Wheels | 3.2.3.2.2 | $349 | 45% | Previous experience
Cylindrical Structure | 3.2.3.2.3.2 | $216 | 45% | Previous experience
Service Barrel | 3.2.3.2.3.3 | $243 | 45% | Previous experience
Total Cost = $ 1,291 K
To be updated to Feb version

## Slide 11: Status and Highlights
Updated Cost & Schedule following MVTX workshop at LBNL, 3/2019
  Carbon structures
    Design
    Production
    Schedule
  Power system
  Contingency
    Electronics
    Mechanics
  Rebalance work load
    LANL, MIT, UT-A
TPC updated
  $4.3M (P6) reduced to $3.7M
  OPC, TEC assigned
MVTX Workshop @LBNL, 2/28-3/2,2019
Discussed major carbon structures’
design & production cost, line by line

## Slide 12: Issues and Concerns
Budget availability
  Final mechanical system design work, at MIT, LANL and LBNL
  Early R&D required to reduce the high production contingency
Carbon structure production cost & schedule
  LBNL, other production plan/ATLAS
  Other companies
  High contingency, ~50%
Global mechanical integration
  Inner volume design is still in a state of flux
  High contingency, ~ 50%

## Slide 13
Cost and Schedule

## Slide 18: Guidance

## Slide 19: L3 Technical Overview
Emphasize any technical issues that still need to be resolved. If all has been decided put it on the slide.

## Slide 20: L3 Scope
What are you building?
Where you fit in the L2

## Slide 21: L3 Collaborators

## Slide 22: Schedule Drivers

## Slide 23: Cost Drivers

## Slide 24: Status and Highlights
Recent technical accomplishments

## Slide 25: Issues and Concerns

## Slide 26: Back Up