## Slide 1: MVTX Overview (WBS 3.2)
Ming Liu, LANL
April 9-11, 2019
BNL Director’s Review

## Slide 2: Outline
MVTX science & technology
MVTX scope
Cost & schedule
Status & highlights
Issues and concerns
Document: sPH-HF-2018-001
https://indico.bnl.gov/event/4072/
MVTX:
Monolithic-active-pixel-sensor based VerTeX detector

## Slide 3: The sPHENIX Detectors
Φ ~ 5m
Outer HCal
SC Magnet
EMCal
TPC
INTT
MVTX
Inner HCal
Tracking system upgrade:
INTT (WBS 3.1)
MVTX (WBS 3.2)
Notes: 15kHz matched to collision rate.

## Slide 4: MVTX Enables the 3rd Science Pillar
Jets
Upsilons
Open Heavy Flavor
Bottom quarks are heavy (4.2 GeV)
Produced in initial collision, probe QGP evolution
Well controlled in pQCD
Access fundamental transport properties of QGP
Precision tracker + High rate capability → Precision bottom observables over wide scales in p+p, p+A and A+A
Initial observables:
  B-meson @ pT <10 GeV/c
  b-jet @ 15< pT<50 GeV/c
DCA< 25um @1GeV

## Slide 5: MVTX Technical Overview
3-layer sensor barrel
- 48 staves, 432 chips
Service cone: signal, power, cooling
and mechanical support
MVTX
parameters
CYSS: Cylindrical Shell Structure
Extended power FPC
Ross & Yuan’s talks
27cm
End-Wheel

## Slide 6: Monolithic Active Pixel Sensors (MAPS) The Next-Generation, State-of-the-Art Pixel Tracker
Advantages of ALICE PIxel DEtector (ALPIDE) sensor:
Very fine pitch (27μm x 29μm), for superb spatial resolution
High efficiency (>99%) and low noise (<10-6), for excellent tracking
Time resolution, as low as ~5 μs, for less pileup
Ultra-thin/low mass, 50μm (~0.3% X0), for less multiple scatterings
0.5M channels with on-pixel digitization, for zero-suppression and fast readout
Low power dissipation, 40mW/cm2, for minimal service materials
An ideal detector for QGP physics!
50 μm
~28 μm
ALPIDE design
Flexible Printed Circuit(FPC)
9 Chips
Cold plate
A 9-chip MAPS stave, 1.5cm x 27cm
ALPIDE sensor:
1.5cm x 3.0cm, 0.5M pixels

## Slide 7: MVTX Readout, Power and Controls
Power Board
Flex PCB Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN bus
CAEN Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
sPHENIX
Data Aggregation Module(DAM)
Jo’s talk

## Slide 8: MVTX Detector in sPHENIX
TPC volume:
Length = 216 cm
Radius = 800 cm
INTT detector
MVTX detector with service cylinder
Support brackets for TPC and INTT
Ross’ talk

## Slide 9: MVTX Scope
Mechanical structure design
  Design & FEA, LANL/MIT
  End Wheels
  Cylindrical structure shells
  Detector service half barrels
  Service patch panels
  Global interface
Mechanical structure fabrication
  Composite structures, LBNL
  Non-composite structures, MIT
  Installation tooling etc., MIT/LANL/LBNL/BNL
Ancillary systems – “adopt” ALICE/ITS
  Cooling plant, MIT/BNL
  Slow control & monitoring etc., MIT/GSU
MVTX electronics
  Backend FELIX and cables
  Integration into sPHENIX DAQ
  Power system
Detector assembly & test
  Stave QA & half detector assembly @LBNL
  System test & integration @LBNL/BNL
Installation & commissioning, by all
  Pre-installation commissioning @BNL
  Installation @IR
Early generic R&D accomplished through LANL LDRD
- Readout integration
- Detector conceptual design

## Slide 10: MVTX Collaborators & Institution Roles

## Slide 11: Schedule Drivers
Budget availability
  Final engineering design of the mechanical system
  Production of support structures
Mechanical structures
  Detector and interface system design
  Carbon structure fabrication
Detector assembly and test
  Assembly jigs design and fabrication
  Detector assembly & QA
  Metrology
Final installation in IR
  Last detector to be installed

## Slide 12: Cost Drivers
Mechanical design and fabrication
CYSS
End wheels
Service barrel
Global interface

## Slide 13: Basis of Estimate & Resource-Loaded Schedules
Electronics: production
  FELIX: ATLAS/sPHENIX production, LANL/LDRD
  RU services, cables: ALICE/ITS production, LANL/LDRD
  Power boards: ALICE/ITS production , LANL/LDRD
  CAEN bulk PS: Quotes from CAEN, ALICE/ITS production, LANL/LDRD
Mechanics & Integration: design and production
  CYSS, End wheels, Service barrel: ALICE/ITS
  Integrations: Recent experience at RHIC, HFT/STAR, FVTX/PHENIX
FELIX
Carbon Structures
MVTX BoE Doc
Labor, M&S
Labor, M&S

## Slide 14: Resource Distribution
MVTX in P6

## Slide 15: MVTX Schedules and Milestones
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU production @CERN
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel &
global system design
End Wheels
CYSS
Half barrel #1
Half barrel #2
6/15 Half barrels
arrive @BNL
Pre-installation commissioning @BNL
RU, FELIX, PS, cables etc.
8/25 Installed
Ready for commissioning
Ready for beam;
sPHENIX day-1 run
FELIX production
Stave testing, half-barrel assembly @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Detector & interface design
sPHENIX interface & global support design
SB & global mech
sys production
Today
Full detector
system test @BNL Lab
cooling & safety
system @BNL
Construction
MVTX final
review
Generic R&D
Sensors for RHIC
IR installation
Feb. 2019, in P6

## Slide 16: Status and Highlights
Full readout chain demonstrated through LANL LDRD
  Successful Fermilab Test Beam run in 2018
Modified stave certified through LANL LDRD
  Successfully tested at CERN
  Radiation hardness verified at CERN
Mechanical system integration MVTX+INTT
  sPHENIX tracking optimized with 2-layer INTT configuration
  Mechanical design being updated and 3-D mockup demonstrated
Readout cables
  BNL approved the use of SamTec non-Halogen-free cables
    Electrically better & mechanically compact
    ALICE confirmed performance with 8m long Halogen-free cables
    For MVTX, ~10m very likely work (30AWG/sPHENIX vs 32AWG/ALICE)
  Samples (6.5 ~ 11.5m long) ordered for R&D test at LANL
    To be tested in coming months
ALICE/ITS:
Halogen-free
readout cables
BNL approved:
Non-Halogen-free
cables for MVTX/sPHENIX

## Slide 17: MVTX Full Readout Chain Demonstrated (3/2018)
4-hit track
4-MAPS telescope
120 GeV proton
beam
- Tracking spatial resolution: <5 um
- Hit efficiency: > 99.5%
4-MAPS
telescope
Fermilab Test Beam: Feb-Mar, 2018
Sho
Darren &
Sanghoon
Alex

## Slide 18: Confirmed HIC with Extended 40(60)cm Power FPC
Built and tested two HICs at CERN in 9/2018
  No change in sensor performance (noise, threshold) observed, as expected;
60cm PWR FPC
40cm PWR FPC
ALICE: 15cm PWR FPC
Followed identical ALICE IB QA test procedure, with a 8m SamTec cable!

## Slide 19: Sensor Irradiation Test – OK at 2.7MRad
Continuous effort by ALICE (@NPI, Czech)
BNL Director’s review recommendation:
- Test sensors up to 1MRad
ALICE/ITS report: 2.7 MRad
https://indico.cern.ch/event/758048/
Operation
Region

## Slide 20: MVTX + INTT 3-D Mockup (11/2018)
MVTX and INTT
Space conflict resolved!
Office of System Integration
– led by Mickey & Bob,
a team of engineers and physicists

## Slide 21: Latest Project Update: MVTX Workshop
Discussed major carbon structures’
design & production cost, line by line;
Also LBNL production schedule
Updated Cost & Schedule
under review;
Significant cost saving possible
Feb. 28 – Mar. 2, 2019, MVTX/HF Workshop @LBNL

## Slide 22: Carbon Structures – Work in Progress
Conical sectors are expensive!
A new design under development to avoid the conical structures, MIT/LANL
Ross’ talk

## Slide 23: Issues and Concerns
Budget availability
  Funding for final mechanical system design work
    Early R&D to reduce high production contingency
  Preparation for Stave acceptance test/QA/storage at LBNL (3 months lead time)
  Schedule is closely tied to the funding level
Carbon structures
  Cost and schedule, high contingency in cost
  Window of opportunity at LBNL before ATLAS production
  Other possible production sites (Italy, France, Korea …)
Mechanical system integration
  sPHENIX beam pipe modification, under discussion with CAD
  Readout cables, cooling etc.
  MVTX+INTT+TPC… global support structure design

## Slide 24: Summary
MVTX enables the 3rd science pillar
MVTX detector design & construction
  As a separate upgrade project from the baseline sPHENIX MIE
  Engineering design work in progress, MIT/LANL/LBNL et al
    Need budget now for the final engineering design work
  Construction and assembly work planned for late 2019
Project integrated into the sPHENIX P6
  Latest Cost & Schedule under review, significant cost saving possible
  To be implemented in P6 after this review
Successful generic R&D through LANL LDRD support
  Readout integration
  Stave modification
  Mechanical system conceptual design
MVTX is ready to receive project funding

## Slide 25: backup

## Slide 26: Address July 2018 Review Recommendations
Stave and RU procurement readiness
Completed sensor/HIC/stave evaluations at CERN
  Built, tested and confirmed two HICs with 40cm and 60cm long power FPC
  Sensors irradiated up to 2.7MRad, no issues (updated 9/18/2018).
Addressed all recommendations on stave/sensor R&D
Cost are set for staves & RUs, procurement through US-ALICE/UTK
  Technical specs document completed for production, BNL/DOE agreed
  sPHENIX RU and stave production starts ~May 2019
MVTX/INTT mechanical integration
  Mechanical design being updated and 3-D mockup demonstrated
  Inner tracking task force completed evaluation, preferred INTT-layers =2
Readout cables
  BNL approved the use of SamTec blue cables
    Electrically better & mechanically compact
    ALICE confirmed signal performance with 8m long readout cables. For MVTX, 10m very likely works (30AWG/sPHENIX vs 32AWG/ALICE), to be confirmed by on-going R&D at LANL
  Samples ordered for system integration mockup and test
https://docs.google.com/document/d/1vsm_G7ZLgqv-kBZqK0jF69T_Nx2Uwk0Zxv86jRVxybw/edit?usp=sharing

## Slide 27: Stave and RU Production QA Plan Documents Available
Staves
Purchase 84 staves from ALICE/CERN
  48 + 28(spares for 2 inner layers) + 8 spares
  Production following the completion of ALICE ITS/IB
  Starting ~Oct. 2018, will last 6-12 months
  Fully tested at CERN before shipping to US
    All Gold/Silver staves (same as ALICE IB)
    A LANL postdoc (Dr. Yasser Morales) oversees production QA at CERN
Acceptance QA at LBNL
  Full test and QA
    Electrical
    Mechanical
  Detector assembly at LBNL
Readout Units
Purchase 60 RUs from ALICE/CERN
  48 + 12 spares(20%)
  To be part of ALICE production
    Cost saving
    Minimize technical risks
  Initial test at CERN
Acceptance QA at UT-Austin
  Full test
  LANL as the 2nd test site
https://indico.bnl.gov/event/4729/

## Slide 28: MVTX in P6 (fully Burd. & Esca.)

## Slide 29: MVTX MS Project 1/4(for estimation)

## Slide 30: MVTX MS Project 2/4

## Slide 31: MVTX MS Project 3/4

## Slide 32: MVTX MS Project 4/4