## Slide 1: MVTX Overview (WBS 3.2)
Ming Liu
April 9-11, 2019
BNL

## Slide 2: The sPHENIX Detectors
Φ ~ 5m
Outer HCal
SC Magnet
EMCal
TPC
INTT
15 kHz trigger
>10 GB/s data
MVTX
Inner HCal
Tracking system upgrade:
- MVTX (WBS3.2)
- INTT (WBS3.1)
Notes: 15kHz matched to collision rate.

## Slide 3: Outline
MVTX science & technology
MVTX scope
Cost & schedule
Status & highlights
Issues and concerns
Document: sPH-HF-2018-001
https://indico.bnl.gov/event/4072/

## Slide 4: MVTX Enables the 3rd Science Pillar
Jets
Upsilons
Open Heavy Flavor
Bottom quarks are heavy (4.2 GeV)
Produced in initial collision, probe QGP evolution
Well controlled in pQCD
Access fundamental transport properties of QGP
Jin/Xin’s talk

## Slide 5: Monolithic Active Pixel Sensors (MAPS) The Next-Generation, State-of-the-Art Pixel Tracker
Advantages of ALICE PIxel DEtector (ALPIDE) sensor:
Very fine pitch (27μm x 29μm), for superb spatial resolution
High efficiency (>99%) and low noise (<10-6), for excellent tracking
Time resolution, as low as ~5 μs, for less pileup
Ultra-thin/low mass, 50μm (~0.3% X0), for less multiple scatterings
0.5M channels with on-pixel digitization, for zero-suppression and fast readout
Low power dissipation, 40mW/cm2, for minimal service materials
An ideal detector for QGP physics!
50 μm
~28 μm
ALPIDE design
Flexible Printed Circuit(FPC)
9 Chips
Cold plate
A 9-chip MAPS stave, 1.5cm x 27cm
ALPIDE sensor:
1.5cm x 3.0cm, 0.5M pixels

## Slide 6: MVTX Detector – Modified from ALICE/ITS Design
3-layer sensor barrel
- 48 staves, 432 chips
Service cone: signal, power, cooling
and mechanical support
MVTX
parameters
End-Wheel
CYSS: Cylindrical Shell Structure
Extended power FPC
Ross’ talk

## Slide 7: MVTX Readout, Power and Controls
Power Board
Flex PCB Filtering Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN bus
CAEN Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
sPHENIX Data Aggregation Module(DAM)
Slow control
Mike’s talk

## Slide 8: MVTX detector in sPHENIX
TPC volume,
length = 2,160.0 mm
INTT detector, 2 layers
MVTX detector with service cylinder
Support brackets for TPC and INTT

## Slide 9: Scope of the MVTX Project
MAPS Staves & Electronics
  Readout Integration R&D (LANL LDRD)
    Frontend: ALICE/ITS, RU
    Backend: ATLAS FELIX
    Reprogram RU & FELIX into RCDAQ/sPHENIX
  Production @CERN: $1.36M
    84 ALICE/ITS-IB staves from CERN
      Acceptance test @LBNL, 48+spares(2-inner layers+)
    60 ALICE/ITS-RU from CERN
      Acceptance test @UT-Austin, 48+spares(12)
  Production & Assembly @US: ~$5M
    Production QA & assembly
      Half detector assembly & test @LBNL
      FELIX test & integration @LANL/BNL, 6+spares(2)
    Ancillary systems
      “adopt” ALICE ITS system
      Power, slow control & monitoring etc.
Mechanics & Cooling
  Modify ALICE/ITS inner tracker mechanical structures
    End Wheels
    Cylindrical structure shells
    Detector half barrels
    Detector and Service half barrels
  Mechanical system integration,
    Conceptual design (LANL LDRD)
    Design & simulations, MIT/LANL
    Composite structure production, LBNL
    Non-composite structure, MIT
    Installation tooling etc., BNL/LANL/MIT/LBNL
  Adopt ALICE cooling plant design
    Modified to fit sPHENIX, MIT/BNL
Final system test @BNL, Installation & commissioning (BNL + MVTX group)

## Slide 10: sPHENIX MVTX Group: Institution Roles
Major institutions lead key tasks
Check WBS #

## Slide 11: MVTX Schedules and Milestones
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Installed 2 half-barrels
@sPHENIX IR;
Ready for beam;
sPHENIX day-1 run
FELIX
production
Stave testing, half-barrel assembly @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Detector & interface design
Design & procure
support structure
Procure insertion
sys to sPHENIX rails
Today
Complete detector
system test @BNL Lab
Procure & assemble
cooling system
Construction

## Slide 12: Cost Drivers
Major Tasks | Cost | Cost + Contingency
Project Management | $543k | $641k
Electronics | $401k | $492k
Mechanics and Detector Assembly | $1,784k | $2,431k
Integration and Infrastructure | $970k | $1,345k

## Slide 13: Basis of Estimate & Resource-Loaded Schedule
BOE:
Electronics: ALICE/ATLAS/sPHENIX production experience
Mechanics & Integration: previous experience, ITS/ALICE, HFT/STAR, FVTX/PHENIX
Stave and RU: fixed cost from ALICE production (separate cost)

## Slide 14: Status and Highlights
Stave and RU production at CERN
  Completed sensor/HIC/stave evaluations at CERN
    Built, tested and confirmed two HICs with 40cm and 60cm long power FPC
    Sensors irradiated up to 2.7MRad by ALICE, no issues found(updated 9/18/2018).
  Cost are set for staves & RUs, procurement through US-ALICE/UTK
    Technical specs document completed for production, BNL/DOE agreed
    sPHENIX RU and stave production following ALICE production
  Addressed all recommendations on stave/sensor R&D from last July 2018 Director’s review
Full readout chain demonstrated
  Successful Fermilab Test Beam run in 2018
Mechanical system integration MVTX+INTT
  sPHENIX tracking optimized with 2-layer INTT configuration
  Mechanical design being updated and 3-D mockup demonstrated MVTX+INTT
Readout cables
  BNL approved the use of SamTec blue cables
    Electrically better & mechanically compact
    ALICE confirmed signal performance with 8m long readout cables. For MVTX, 10m very likely works (30AWG/sPHENIX vs 32AWG/ALICE), to be confirmed by on-going R&D at LANL
  Samples ordered for system integration mockup and test

## Slide 15: Confirmed HIC with Extended 40(60)cm Power FPC
Built and tested two HICs at CERN in the week of 9/17/2018
  No change in sensor performance (noise, threshold) observed, as expected;
60cm PWR FPC
40cm PWR FPC
ALICE: 15cm PWR FPC
Followed identical ALICE IB QA test procedure,
with a 8m SamTec cable!

## Slide 16: Sensor Irradiation Test – OK at 2.7MRad
Continuous effort by ALICE (@NPI, Czech)
BNL Director’s review recommendation:
test sensor up to 1MRad
https://indico.cern.ch/event/758048/

## Slide 17: MVTX + 4-layer INTT 3-D Mockup
MVTX and INTT
Space conflict resolved!
Office of System Integration
– led by Mickey & Bob,
a team of engineers and physicists

## Slide 18: MVTX Full Readout Chain Demonstrated (3/2018)
4-hit track
4-MAPS telescope
120 GeV proton
beam
- Tracking spatial resolution: <5 um
- Hit efficiency: > 99.5%
4-MAPS
telescope
Fermilab Test Beam: Feb-Mar, 2018

## Slide 19: Mechanical System Discussions @LBNL
Discussed major carbon structures’
design & production cost line by line,
also production schedule @LBNL , 3/2019

## Slide 20: Carbon Structures – Work in Progress
Conical sectors are expensive!
A new design under development to avoid the conical structures
Ross’ talk

## Slide 21: Issues and Concerns
Funding for final mechanical system design work
  Need to start engineering design asap
  Early R&D to reduce contingency
Carbon structures
  Cost and schedule, high contingency now
  Opportunity before ATLAS production at LBNL
Mechanical system integration
  Beam pipe modification
  MVTX+INTT+TPC + ...

## Slide 22: Summary: MVTX - WBS 3.2
MS Project being updated, now in the sPHENIX P6
  Latest Cost & Schedule under review, <$5M
MVTX detector design & construction
  As a separated project from the MIE
    Mechanical system design and fabrication
    Update baseline cost and schedule soon
    Monthly report to sPHENIX and BNL upper management
  Engineering design work in progress, MIT/LANL et al
  Construction and assembly work in late 2019
Critical R&D through LANL LDRD
  Readout integration
  Stave modification
  Mechanical system conceptual design
Stave and RU production through US-ALICE
  Early procurements of staves and readout units (RU) through US-Alice
  DOE and BNL agreed, DOE directly pays UTK/US-ALICE
  Received signed letter from CERN on the cost of 60 RUs and 84 Stave, ~$1.36M
  Purchase paperwork in progress at UTK, aiming to complete by ~ May 2019

## Slide 23: backup

## Slide 24: Address July 2018 Review Recommendations
Stave and RU procurement readiness
Completed sensor/HIC/stave evaluations at CERN
  Built, tested and confirmed two HICs with 40cm and 60cm long power FPC
  Sensors irradiated up to 2.7MRad, no issues (updated 9/18/2018).
Addressed all recommendations on stave/sensor R&D
Cost are set for staves & RUs, procurement through US-ALICE/UTK!
  Technical specs document completed for production, BNL/DOE agreed
  sPHENIX RU and stave production starts ~April 2019, practically already in progress
MVTX/INTT mechanical integration
  Mechanical design being updated and 3-D mockup demonstrated
  Inner tracking task force completed evaluation, preferred INTT-layers =2
Readout cables
  BNL approved the use of SamTec blue cables
    Electrically better & mechanically compact
    ALICE confirmed signal performance with 8m long readout cables. For MVTX, 10m very likely works (30AWG/sPHENIX vs 32AWG/ALICE), to be confirmed by on-going R&D at LANL
  Samples ordered for system integration mockup and test
https://docs.google.com/document/d/1vsm_G7ZLgqv-kBZqK0jF69T_Nx2Uwk0Zxv86jRVxybw/edit?usp=sharing
Christof, Rachid, Itaru’s talks

## Slide 25: MVTX Production Schedule Update
Stave production @CERN
  May 2019- May 2020, 84 staves
  ALICE IB average: ~4 staves/wk
Stave acceptance test @LBNL
  MOSAIC system, 9/2019 – 5/2020
Final mechanical design work
  May 2019 – $$ available soon(?)
  CYSS, End wheels
  Service barrel and interface
MVTX detector assembly at LBNL
  LBNL ALICE ML stave production ends ~12/2019, a total of 60 ML staves
  Start MVTX detector assembly ~ late summer of 2019 (or after the completion of ALICE ML?)
MVTX full half-barrel detector test @LBNL
  Starts ~mid of 2021
  Using full readout system if ready: 24RU + 12PU + 3FELIX/2 servers

## Slide 26: 2019 test beam: 4-stave telescope
Scheduled for May 22-29, at Fermilab
Additions compared to the 2018 test beam:
  Staves (from single chips)
  Full-length MVTX signal cables (from 5 m off-the-shelf cables)
  FELIX v2.0 (from v1.5)
  Cooling system
  Power board
  sPHENIX GTM
Full test of all components of the MVTX detector - LDRD “stretch goal”
Sho’s talk

## Slide 27: Mechanical design
Telescope box design completed, sent for fabrication
  One stave can be offset by (0.5,0.5)cm for material scanning

## Slide 28: ALICE/ITS Signal cable design
The Samtec twinax cables carry clock (40 MHz), control (40 Mbps bidirectional), data (9x1.2 Gbps)
ALICE is using halogen-free cables (32 AWG, LDPE dielectric) due to CERN LSZH requirement; 2.65 + 5.3 m cables have been tested and are now in production
Stave
Stave
RU
RU

## Slide 29: sPHENIX MVTX Cable testing
BNL has approved non-halogen-free cables
  sPHENIX/MVTX: 30 AWG, FEP dielectric;
  Improved signal integrity
sPHENIX cable run estimates are converging: 1.4 + 6.5 m
We have ordered Samtec cables for 1.2/2.65 + 5.3/8.8 m (total length 6.5 - 11.45 m)
We will qualify these cables using stave and RU (bit error rates, statistical eye), and scope/network analyzer
We will test full-length MVTX cables in the next months

## Slide 30
Type-A
Type-B
Type-A

## Slide 31: MVTX Readout and Power Cable Rout
sPHENIX MVTX: 7.9+m
  Cable-A: 1.4 m
  Cable-B: 6.5+ m
  Power cable:4.7+ m
On-going R&D for ~10m
PWR
RU
PU
Cable-A: 2.65m
ALICE ITS/IB final readout cables: ~8m
Cable-B: 5.3m
BNL has approved “non-halogen free” cables for sPHENIX
Sho talk

## Slide 32: Stave Production and Shipping etc.
Hand carry staves from CERN to LBNL, 4 trips
Preliminary design from CERN for stave transportation plates
  To be produced at CERN, paid by LBNL/sPHENIX
Extended design from CERN
for MVTX
ALICE ITS IB

## Slide 33: Guidance

## Slide 34: The Subsystem

## Slide 35: The Subsystem Technical Overview

## Slide 36: Scope

## Slide 37: Subsystem Collaborators

## Slide 38: Schedule Drivers

## Slide 39: Cost Drivers

## Slide 40: Basis of Estimate & Resource-Loaded Schedule

## Slide 41: Status and Highlights

## Slide 42: Issues and Concerns

## Slide 43: Summary

## Slide 44: Back Up