## Slide 1: Review Charge

## Slide 2: Topics for Today
Overview
  Ming et al
Physics and detector simulations
  Xin
Coffee break
LDRD status and plan
  Cesar
Mechanics and detector assembly
  Giacomo
MVTX electronics
  Mark
Lunch break
MVTX support and infrastructure
  Walt
Integration of MVTX and sPHENIX
  Ed
Cost & schedule & risk
  Dave et al
Executive session (closed)
https://indico.bnl.gov/conferenceDisplay.py?confId=3270

## Slide 3: MVTX Overview
Ming Liu
Los Alamos National Laboratory
For the sPHENIX MVTX Upgrade Group
BNL Director’s Review
07/10/2017

## Slide 4: MVTX: MAPS-based Vertex Detector for sPHENIX
A separate upgrade project for the baseline sPHENIX experiment, with
Compelling Science and;
Feasible cost & schedule
Parallel Activities
MAPS-based Vertex Detector (MVTX)
Intermediate Silicon Strip Tracker (INTT)

## Slide 5: Outline
Science of MVTX upgrade
Scope of MVTX project
  Readout
  Integration
  Cost & schedule
Organization & plan

## Slide 6: Exciting Science: Physics of the 3rd Pillar
sPHENIX is the next flagship heavy ion physics experiment in the US (NSAC LRP2015)
  Jets
  Upsilons
  B-jets and B hadrons
MVTX will complete QGP heavy flavor physics
  Unambiguous determination of key parameters of QGP properties and interactions
  Precision study of the “inner workings of QGP”
Cannot be done easily at the LHC for lack of low pT reach and huge backgrounds
sPHENIX Three Physics Pillars
Jets
Upsilons
B
D

## Slide 7: MVTX – Bring sPHENIX to a New Horizon
Unambiguously determine quark energy loss mechanisms, particularly over the mostly interesting transition region, pT ~ M
  Radiative dE/dX
  Collisional dE/dX
  Other effects
Xin’s talk
Expectations @RHIC
Learned @CERN

## Slide 8: Planned sPHENIX Runs: 2022-2026
Projected maximum collision event rates:
  Au+Au: 200kHz ( ~50 kHz, |Z|<10cm)
  p+p: 10MHz ( ~3 MHz, |Z|<10cm)
  p+A: 2.8MHz ( ~0.7 MHz,|Z|<10cm)
  sPHENIX DAQ: 15kHz
Precision vertexing:
  Tracking resolution better than 60um @pT=1GeV
  High multiplicity HI collisions
  Low multiplicity but high rate p+p collisions
B hadrons: O(1M?)
b-jets/pT>15GeV: O(100K)

## Slide 9: Our Approach
ALICE ITS Upgrade:
Inner Barrel Tracker
sPHENIX Inner Tracking
“Adopt” ITS/IB
- Min. Risks
- Max. Phys.
Major challenges:
- Readout
- Mechanics
R: 23/32/39 mm
Z: 271 mm

## Slide 10: Monolithic-Active-Pixel-Sensors (MAPS) A State of the Art Tracker
Advantages of ALICE MAPS/ALPIDE:
  Very fine pitch (28x28 μm)
  High efficiency (>99%) and low noise (<10-6)
  Fast readout, ~4 μS
  Ultra-thin/low mass, 50μm (~0.3% X0)
  On-pixel digitization, low power dissipation
An ideal detector for QGP b-jet physics!
50 μm
28 μm
ALPIDE design
FPC
9 Chips
Cooling plate
A 9-chip MAPS stave, 1.5 x 27cm2

## Slide 11: ALPIDE/MAPS Timing & Trigger
Well fit sPHENIX/RHIC environment, 10MHz Clock (LHC 40MHz)
DV=Q/C
v
t
PIX_IN
tr> 100 us
tf~= 10 ns
OUT_D
STROBE
~5-6 ms
~5-6 us
v
t
OUT_A
threshold
sPHENIX trigger latency: ~4uS

## Slide 12: sPHENIX MVTX vs ALICE ITS/IB Specifications from ALICE ITS Upgrade & sPHENIX design
Event size, dN/dη: sPHENIX = 1/3 ALICE (pp), 1/5 ALICE(AA)
 | ALICE | sPHENIX
Pb+Pb / Au+Au | 200 kHz | 200 kHz
p+p | 1 MHz | 10 MHz
Trigger | 50 kHz | 15 kHz

## Slide 13: MVTX Readout and Control System
Power Board
Filtering Board
(Capacitors)
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Regulated Power
FELIX
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5~10 m
GBT Optical Links
9-sensor Stave
sPHENIX GL-1 & GTM
DCS
CAN bus
Power supplies
Power
Trigger & Clock
Marks’s talk

## Slide 14: MVTX Pre-proposal Submitted!
Pre-proposal submitted to DOE, 2/2017
  Follow-up discussions with DOE and BNL managers
  Weekly proj. leaders meeting BNL/LANL/LBNL/MIT
Plan to update proposal to DOE, late 2017
  Expanded science “CD0” + Cost & Schedule “CD1”
  Assumed funding starts in FY18
A growing collaboration
  15+ institutions from US and abroad
“Adopt” ALICE ITS Upgrade Inner Barrel 3-layer MAPS detector
  Mini. risk, Max. Physics
Precision vertexing for b-jet/B-hadron tagging in HI with high efficiency and high purity
B-jet modification in QGP at low-medium pT to determine QGP properties, study mass-dependence on collisional vs radiative energy loss, flow etc.
A separate DOE upgrade fund to build the full detector, ~$5M for construction
Early R&D by LANL LDRD, $5M, FY17-19, readout, mechanical design and physics

## Slide 15: Scope of the MVTX Project
MAPS Staves & Electronics
  MAPS staves “MoU” to build 68 ITS inner Barrel Staves
    No modification
  Readout Electronics
    Frontend: ALICE/ITS, RU
    Backend: ATLAS FELIX
    Modify/reprogram RU & FELIX for sPHENIX
    R&D by LANL LDRD
  Production:
    Extend ALICE/ITS MAPS stave production
      WBS 1.5.3.1, LANL
      sPHENIX personnel help at CERN
    Reproduce additional ALICE/RU & ATLAS/FELIX
      WBS 1.5.2.1, UT-Austin
      WBS 1.5.2.2 , LANL
    Final assembly and test in US
      WBS 1.5.3, LBNL
  Ancillary systems, “adopt” ALICE system
    Power distribution, cables, crates, racks etc.,
      WBS 1.5.2.3, LBNL
    Slow control, safety and monitoring
Mechanics & Cooling
  Some changes to ALICE/ITS inner tracker mechanical structures, WBS 1.5.3
    End Wheels
    Cylindrical structure shells
    Detector half barrels
    Detector and Service half barrels
  Mechanical Integration, WBS 1.5.4
    Conceptual design by LANL LDRD
    Prototype by sPHENIX R&D, MIT/LANL
    Design integration frames
    Carbon frames etc., LBNL
    Installation tooling etc.
  Adopt ALICE cooling plant design
    Minor modification to fit sPHENIX
    Smaller heat load than ALICE ITS
  Metrology and Survey

## Slide 16: LDRD – MVTX Key Tasks/Milestones
RUv1.0/FELIX1.5 Integration
40MHz, 7/17-12/17
RUv1.x/FELIX2.0, 10MHz,
10/17 – 6/18
MVTX Design Review 7/2018
System test, cosmic & source
6/18 - 1/19
LDRD
MVTX: 1/2018 – 12/2022
Stave Production, procure FPGA, GBT etc.
8/18-4/19
7/17
10/17
10/18
10/19
Electronics Production
1/19-8/19
Test Beam, tracking performance
analysis, physics sim, NIM paper etc.
1/19 – 9/19
Today
BNL Director Review
7/10-11, 2017
Cesar’s talk

## Slide 17: LANL LDRD Progress Highlights
Complete MVTX readout design and development
Preliminary conceptual mechanical integration
R&D status:
MOSAIC test bench in operation
  Single MAPS chip high-speed readout
  9-chip HIC/”stave” readout
  Threshold scan
  Noise scan
  External trigger
  Test data readout performance
    1.2Gb/sec
    0.6Gb/sec
    0.4Gb/sec
Test firefly cable performance
  5m (ALICE default)
  7m, 10m
  Short extension cables, +20~30cm
  Important for integration
Cesar’s talk
FireFly cables
MAPS chip
MOSAIC test bench
9-chip HIC/stave

## Slide 18: Detector Assembly
Precision positioning and installation of staves on end-wheels
IB CYSS
Layer 0
Layer 1
Layer 2
Assembly of layers and carbon fiber structure into half-detector
Stave testing at each step
Metrology survey
Giacomo’s talk

## Slide 19: System Integration
Walt’s talk
MVTX+INTT

## Slide 20: Cost Basis – Major Items
Electronics (WBS 1.5.2): $1,285K
  ALICE ITS RU & PS
  ATLAS FELIX
  Power system and controls
  PHENIX/STAR/ALICE experience
MAPS and Detector (WBS 1.5.3): $2,900K
  ALICE ITS/IB production
  PHENIX/ALICE/STAR experience
Mechanical integration (WBS 1.5.4): $909K
  ALICE ITS inner tracker design
  FVTX/PHENIX, HFT/STAR experience
Total project cost: $5.7M w. 35% Cont.
x48
Dave Lee’s talk

## Slide 21
Electronics
LANL
WBS 1.x
Readout Units
UT Austin -WBS 1.xx
Back-end
LANL - WBS 1.xx
Power systems
LBNL - WBS 1.xx
Mechanics & Detector Assembly
LBNL - WBS 1.y
Staves
LANL- WBS 1.yy
Carbon Structures
LBNL- WBS 1.yy
Barrel Assembly
LBNL- WBS 1.yy
Integration & Infrastructures
MIT - WBS 1.z
Cooling
MIT - WBS 1.zz
Safety System
MIT - WBS 1.zz
Global Support
MIT - WBS 1.zz
MVTX
Principal Investigator: M. Liu (LANL)
Lead Coordinator: M. Chamizo-Llatas (BNL)
Co-investigators: G.Odyenic (LBNL),R.Redwine(MIT)
ES&H liason: TBC
Installation & Commissioning
LBNL/BNL - WBS 1.zz
sPHENIX integration
sPHENIX DAQ
Major institutions lead key tasks

## Slide 22
A growing collaboration!
new sPHENIX/MVTX members:
Czech groups: Charles Univ. and Inst. of Phys. of the Czech Academy of Sciences
  Stave production at CERN
CCNU – MAPS lab
  HICs assembly and test
  Mechanic integration
Potential ones:
USTC
  Physics simulations w/ LBNL
Peking Univ.
  Physics and detector simulations w/LANL
TCU, Taiwan
From MVTX pre-proposal

## Slide 23: Project Tasks and Timeline
Det. Install.
@BNL
Readout R&D
Mech. design
@LANL/ALICE
Mech. Integr.
& Prototype
@LANL/MIT/LBNL
Production
Key R&D
LDRD@LANL
FY2017
FY2018
FY2019
FY2020
FY2021
FY2016
CD-1
CD-2/3
8/1
CD-0
9/2016
Ready for
Beam
6/2021
“MoU” w/ ALICE/ITS: 11/2016
- Produce MAPS chips and Stave Space frames for sPHENIX as part of ALICE production!
- Full staves and RU & FELIX production cost & schedule  MVTX Upgrade
Detector Assembly
& Test @LBNL
MAPS Prod. & QA
@ALICE
Stave prod.&test @CERN;
C-Stru. Prod.
@LBNL
“RU” & “FELIX”
Prod. @US
A schedule driven project!
ALICE ITS/IB
prod. ends
sPHENIX
baseline

## Slide 24: Status, Plans and Issues
Agreement with ALICE/CERN
  Obtained ALICE readout test stand, MAPS sensors, staves and electronics for early R&D
  Obtained design files, electronics and mechanics
  Training sPHENIX personnel
  ALICE produces MAPS and stave space frames for sPHENIX as part of the contingency
  Provide prototype and final staves
Potential schedule/funding gap of stave production
  ITS/IB production: 7/2017 - 6/2018
  If funding significantly delayed, concerns over the availability of CERN facilities
  Risk Mitigation:
    Early training through LDRD effort, maintain activity at low level
    External foreign funding, CCNU Pixel Lab etc
    Possible mortgage for sPHENIX production from ALICE/CERN with MoU
sPHENIX readout and mechanical integration R&D
  Schedule risks due to unavailability of key R&D elements like staves and readout
  MVTX/INTT integration
  Risk mitigation:
    Early joint R&D with ALICE as associate members
    Early R&D with prototype staves, RU and FELIX
    Early mechanical system integration R&D

## Slide 25: Summary
Exciting science
  New B-physics @RHIC Xin
Early ALICE & ATLAS R&D investment
  Reduce technical risk and contingency
LANL LDRD critical
  mitigate risks and reduce contingency Cesar
No high risk R&D
  Readout Mark
  Mechanics Giacomo
  Integration Walt
Ready for sPHENIX Day-1
  Cost & schedule Dave

## Slide 26: Backup

## Slide 27
4th sPHENIX Collaboaration Meeting at BNL, June 2017

## Slide 28: Key Observables w/ MVTX @sPHENX
B-jet quenching & correlations
  Energy loss mechanisms
  QGP density
B-hadron “flow”
  Bulk viscosity
  Coupling & collectivity
  Diffusion
- Detailed study of QGP properties: T, density, viscosity, couplings etc.

## Slide 29: MAPS-based Vertex Detector (MVTX) for sPHENIX
“Adopt” ALICE ITS Upgrade Inner Barrel 3-layer MAPS detector
  Mini. risk, Max. Physics
Precision vertexing for b-jet/B-hadron tagging in HI with high efficiency and high purity
B-jet modification in QGP at low-medium pT to determine QGP properties, study mass-dependence on collisional vs radiative energy loss, flow etc.
A separate DOE MIE to build the full detector, WBS 1.12, ~$5M for construction;
Early R&D by LANL LDRD, $5M, FY17-19, readout and mechanical integration;
R = 2.4; 3.2; 3.9cm;
L = 27.1cm; @Z=|10|cm, eta =(1.2,0.94,0.81)
|eta| < 2.0

## Slide 30: Stave Production & Test @ CERN
Preparation for final stave production
  Successful ITS Stave production readiness review on Apr/27, 2017
  Optimization of final configuration is underway
Final stave production: July 2017 – June 2018
  One stave per day
  1st set of full staves complete in Jan. 2018
Chip test and HIC assembly machine
Probe-card
Chip
pre-position
Chuck (PPC)
Chips tray
HIC assembly table
Chip gripper
Cesar’s talk
FPC
Chips
Cooling plate

## Slide 31: Updated Cost and Schedule WBS: 6/5/2017

## Slide 32
Sensor Series Production
Stave Develop
2016
2017
2018
2019
2020
Commissioning @ Surface
Installation
Commissioning in ALICE
Stave Mechanics
HIC Production
CMOS processing, thinning & dicing, test
HIC and Stave
Stave Production
Mechanical Support Structures
Design & Prototyping
Design & Prototyping
Production & Test
PRR
PRR
Global Assembly
EDR
PRR
Development
Production
2016
2017
2018
2019
2020
EDR
PRR
Readout Electronics
Commissioning
11 months
Dry Assembly Test
ALICE ITS Upgrade
Overall ITS Planning (Simplified Global View)
From L. Musa, 4/27/2017
Stave PRR Presentation

## Slide 33
  Pixel Sensor Chip - EDR (Oct’ 15)
  Stave - EDR (May’ 16)
  Detector Barrel Mechanics - EDR (Jul ’16)
  Cooling – EDR (Jul ’16)
  Pixel Sensor Chip - PRR (Nov ’16)
  Detector Barrel Mechanics - PRR (Dec ’16)
  Service Barrel Mechanics - EDR (Dec ‘16): done
  Cooling – PRR (Dec ’16): done
  Readout Electronics – EDR (Jan ‘17): done
  Stave - PRR (Apr ‘17)
  Service Barrel Mechanics – PRR (May ‘17)
  Readout Electronics – PRR (Dec ’17)
Project Review Milestones
ALICE ITS Upgrade
Stave Production Readiness Review:
4/27/2017
Stave production starts ~May/June;
1st set of IB by Jan 2018;
2nd set of IB by July 2018
LANL people + others/MVTX work on stave production from May 2017 at CERN, prototype available soon at LANL
Fully working staves for R&D available ~Jan 2018;
Near final readout RU/CRU: ~12/2017
From L. Musa, 4/27/2017

## Slide 34: Stave Production at CERN: WBS 1.5.3.1
48+20 (spares) ALICE/ITS IB staves for sPHENIX
  To be produced at CERN using ALICE ITS/IB facilities
  CERN technicians and sPHENIX students/postdocs
Production cost & schedule
  08/2018 - 4/2019 after ALICE/IB prod.
  Material Cost: 0.45M
  Full cost recovery: 0.5M
  add 35% contingency
One assembled stave:
  1 FPC
  9 MAPS chips
  Cooling plate
  Carbon space frame
  Wire bonded
FPC
Chips
Cooling plate

## Slide 35: Detector Assembly
Carbon supporting structures
Stave assembly & test
Giacomo’s talk
Side view of MVTX

## Slide 36: Integration

## Slide 37: INTT-MVTX Conflict
INTT 4-layers
Currently a clear conflict between the INTT and MVTX
  INTT only includes ladder, no connectors, cooling barbs, etc
R&D items: 1) Extend cables to move the conical structure further out in z-direction; 2) Design/optimize INTT layers to fit current MVTX geometry;
  FPC data cable is the HDI and can’t be easily extended, short “firefly” cables possible?
  Reduce angle of cone – redesign C-structures and connectors
|η|<0.95
|η|<1.09
|η|<1.28
|η|<1.12
INTT Acceptance
@ |z|=10

## Slide 38: INTT-MVTX Conflict
INTT 4-layers
Extend cables to move the conical structure further out in z-direction
  FPC data cable is the HDI and can’t be easily extended
  Possibly add short “firefly” cables to hook up to patch panel, R&D needed
Reduce angle of cone – redesign

## Slide 39: MVTX/INTT Integration Extend MVTX Service Cables?
506.2 mm
16 mm
41.9 mm
16.15 mm
The 9 silicon chips are read out in parallel: each chip sends its data stream to the end of Stave by a dedicated differential pair, 100 mm wide. Two additional differential pairs distribute the clock and configuration signals.
CHIP 1
CHIP 9
……
CHIP 2

## Slide 40: FPC Extension for Connection to Electrical Services
FPC
DVDD
AGND
DGND
DVDD
DGND
DVDD
AVDD
AVDD
AVDD
AGND
AGND
DGND
The connection to the service cables is achieved by a double FPC extension which is soldered to the HIC
x-section at interconnection between FPC and extensions
signal lines (FPC)
analogue power
digital power
FPC
AVDD
AGND
AVDD
AGND
AGND
AVDD
Flex power extension
FPC
DVDD
DGND
DVDD
DVDD
DGND
DGND
Flex power extension
Antonello Di Mauro, Stave PRR 4/27/2017

## Slide 43: Alice ITS Cabling & Support similar for sPHENIX

## Slide 44: Cost & Schedule

## Slide 45: Cost Basis For Electronics
48(+40%)
sPHENIX
J. Phys. G: Nucl. Part. Phys. 41 (2014) 087002

## Slide 46: ALICE Stave and Global Support Structure Cost and Schedule Basis
J. Phys. G: Nucl. Part. Phys. 41 (2014) 087002
ALICE Stave

## Slide 48: HICs Assembly Lab @CCNU space ~ 70m2 (1K clean room); 20m2 (10K clean room, 2.9m head room)
Chip and FPC gluing
Gluing FPC/MAPS
Chip mounting
Wire Bonding
Electrical circuit testing
Storage
Not Doing at present:
Stave assembly
No carbon structures
storage
Gluing & assembly
tables
Test bench
Chip mounting
Wire bonding
Machine shop: (Sun, Daming, Tech.)
CNC etc.
Simple mechanical structures

## Slide 49: CCNU Plan – Cont.
Experts and Designers of ALICE MAPS/ALPIDE on-chip electronics
  Analogy circuit – Dr. Chaosong Gao
  Digital circuit – Dr. Ping Yang
  They will help us!
PLAC – Pixel Lab At CCNU
  Also interested in mechanical system integration
  Plan to hire a full time engineer to work on sPHENIX integration effort
    Visit LANL 6-12 months, work on preliminary conceptual design for the MVTX/INTT/TPC
Physics simulation and analysis
  Many students
Gao
Yang
PLAC Ass. Director
Dr. Xiangming Sun

## Slide 50: MVTX R&D Status and Plan
Readout R&D
  5 single-chip MAPS tested at LANL
  Workfest @UT-Austin, 4/19-20
  RUv1 available in July, will be used for LDRD telescope
  BNL/ATLAS FELIX being evaluated as the default backend
    Computer arrived, fibers/cables ordered
    Obtain one FELIX in a few weeks
    “CRU” being prototyped with Altera evaluation boards, able to communicate with the RUv0 board @ UT-Austin;
  LANL MOSAIC test bench in operation!
Tracker integration task force
  MVTX + INTT + TPC mechanical system integration
  Identified the major tasks
Stave production @CERN
  ALICE Stave Production Readiness Review 4/27, prod. Starts in June/July
  LANL people do assembly and testing at CERN, May – Sept. 2017
  MVTX plan

## Slide 51: Data Flow and Control

## Slide 52: MVTX Readout and Control System
Power Board
Filtering Board
(Capacitors)
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Regulated Power
FELIX (or CRU)
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
5 m
GBT Optical Links
9-sensor Stave
FELIX v1.5:
Arrived June
RUv1 prototype:
available: ~July/Aug
Available:
~August
Prototype stave:
Arrived: June
Mark’s talk
sPHENIX GL-1 & GTM
DCS
CAN bus
Power supplies
Power
Trigger & Clock

## Slide 53: sPHENX Data Flow (TPC)
DAM Data Aggregation Module
EBDC Event Buffering and Data Compressor
Buffer Box
To RCF/
HPSS
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Data Concentration
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DAM
EBDC
DAM
EBDC
DAM
EBDC
DAM
EBDC
DAM
EBDC
DAM
EBDC
10+ Gigabit
Crossbar
Switch
Not in 1.7 Scope
We currently envision the DAM to be a PCIe card in a generic computer that acts as EBDC
The demarcation line between WBS 1.2 and 1.7 runs through the EBDC – budget-wise in 1.2
Functionality-wise partially in 1.7
TPC
The TPC features a continuous readout which is conceptually different from the calorimeter triggered readout
Plan to have a very similar system for MVTX, but in the triggered mode
FEE = RU;
DAM/EBDC = FELIX;

## Slide 54: sPHENIX Design Specs
A sustained DAQ rate of 15KHz
Archive 40Gbit/s to long-term storage in the RACF
Interface to various detector systems:
  Calorimeter
  TPC
  Intermediate tracker (INTT)
  MVTX detector
  Min Bias trigger detector
Global Level 1 trigger
Local level 1 trigger interface and decision-making

## Slide 55: Design Specs - Components
Triggered detectors (calos, INTT, MinBias) Readout
  Subevent buffers (SEB)
  ATPs (assembly and trigger processors)
Continuous Readout Detectors (TPC) Readout
  EBDC interface and functionality
MAPS detector
  EBDC-like component? Design not specified yet
High-end Network Switch ( > 150Gbit/s capacity)
Buffer boxes ( some 50+ hrs local data buffer space)
Networks to the RACF (admin/setup, fibers in place)
= +
SEB
= +
jSEB2
A “Subevent Buffer” (SEB) refers to a Linux PC with a “jSEB2” interface card
Card receives data from the DCM2’s via another board
First time data are seen in a standard PC

## Slide 56: Design Specs – channel counts
Note that this does not translate 1:1 into data volume
Calorimeters 120K o(20) SEBs
TPC 100K o(10) EBDCs
INTT ~230K o(10) ?? SEBs
MVTX ~220 million pixels* o(10) ?? PCs (440 sensors)

## Slide 57: Data compression
Buffer Boxes (7)
LZO
algorithm
New buffer with the
compressed one as payload
Add new
buffer hdr
buffer
buffer
buffer
buffer
buffer
buffer
LZO
Unpack
Original uncompressed buffer restored
This is what a file then looks like
On readback:
This is what a file normally looks like
All this is handled completely in the I/O layer, the higher-level routines just receive a buffer as before.
After all data reduction techniques (zero-suppression, bit-packing, etc) are applied, you typically find that your raw data are still gzip-compressible to a significant amount
Introduced a compressed raw data format that supports a late-stage compression

## Slide 58: Data compression load
Buffer Boxes (7)
This compression buys you a lot spare bandwidth and nice features (e.g, your analysis runs faster!)
However:
A late-stage compression (think: in your tape drive in the extreme case) doesn’t really help you
The compression has to kick in before the data hit your storage system for the first time
No single machine can keep up with compressing a >2GByte/s rate

## Slide 59: Local Level 1 Triggers
Receive trigger primitives from other subsystems
Form higher-level trigger decisions especially in p+p, p+A
Example: high-Pt trigger from the EmCal
Trigger primitive formation in other WBS’ scope (e.g. Calorimeter electronics)
Common format, receiver, decision-forming circuitry (very likely FPGA card)
Important to distinguish the between trigger detectors and the trigger system (the one that takes the decision and distributes this to the triggered detectors)

## Slide 60: Multi-Event buffering
This is what makes the DAQ as fast as it is
Or, in other words: that keeps the dead time in the low 90%’s
Comes down to dealing with your data from various events in parallel
Our hardware is designed to deal with 5-event buffering
More is a diminishing return for $$$
We actually mostly ran 4-event buffering in PHENIX

## Slide 61: 5-year RHIC Run Plan

## Slide 62: 5-Year Run Plan

## Slide 63: Expected Luminosity and Collision Rate

## Slide 66: Motivation
Check if extend the readout cable length from 5m to 7-10m can fit the particle flux at sPHENIX.
ALICE readout speed 1.2Gb/s at 5m, we would like to run at 600Mb/s at around 7-10m.
Run PYTHIA6 MB in 200 GeV and 5 TeV p+p collisions and check the number of charged tracks versus pseudorapidity.

## Slide 67: dN/dη in p+p collisions
With |η|<2.0 region, dN(ALICE) ~2.9*dN(sPHENIX).

## Slide 68: dN/dη in 0-10% Au+Au/Pb+Pb collisions
With |η|<2.0 region, dN(ALICE) ~5.1*dN(sPHENIX).
Ncoll(Au+Au)=962, Ncoll(Pb+Pb)=1670.

## Slide 69: dN/dη in MB Au+Au/Pb+Pb collisions
With |η|<2.0 region, dN(ALICE) ~4.6*dN(sPHENIX).
Ncoll(Au+Au)=258, Ncoll(Pb+Pb)=401.

## Slide 70: Conclusions
The sPHENIX particle flux within |η|<2.0 region in p+p and heavy ion collisions is less than 33% than the collisions at ALICE. It will be fine if we reduce the data readout speed by around 33%.

## Slide 71
Clock
Recall ALICE system– readout electronics is organized in Readout Units
Control
Data (960 Mb/s max)
Trigger
Central Trigger Processor
GBT optical
GBT optical
CRU & O2
Data (9.6 Gb/s max)
Passive electrical (copper) links, up to 1.2 Gb/s (data and control @ 40 Mb/s)
× 192
staves
Each Readout Unit is connected to one stave, both for in Inner and Outer Barrels
Control
Readout Units (RU)
Power Board (PB)
Monitored power
Power supplies
Power
Power
The whole ITS front-end electronic is organized in modular Readout Units, with copper cables connecting each stave end with a single Readout Unit, which optically interfaces with both the Common Readout Unit and the Central Trigger Processor.
DCS
× n
CAN bus

## Slide 72: ALPIDE/MAPS Chip
Advantages of ALPIDE MAPS:
  Very fine pitch (28x28 μm)
  High efficiency (>99%) and low noise (<10-6)
  Fast readout, 2~4 μS
  Ultra-thin/low mass, 50μm (~0.3% X0)
  On-pixel digitization, low power dissipation

## Slide 73: Alpide Architecture
THR
COMP
AMP
Bias, Readout, Control
Readout (zero suppression)
Readout (zero suppression)
Readout (zero suppression)
Readout (zero suppression)
512 rows
1024 pixel columns
In pixel:
  Amplification
  Discrimination
  3 hit storage registers (MEB)

## Slide 75
Modes of Operation
The ITS is planned to be operated in two modes:
  Triggered mode: Pixels are latched with a short strobe window and read out based on an external trigger.
  Continuous mode: Pixels are latched using a long, periodic strobe window and read out.

## Slide 76
Recall – sensor pixel cell timing
Time
Threshold
Amp. out
Sensing node
Amplifier
Comparator
And
Threshold
Strobe window
Pixel memory
Pixel cell
Only pixel with signal higher than threshold DURING the strobe window will get latched in memory
Cmp. out
Strobe window
Signal
Signal can be due to an actual particle hitting the pixel (background included) or to the pixel noise
Slow shaping time acts as an analogue memory buffering the signal until the arrival of the trigger (time over threshold of about 5 µs on average). Whichever signal over threshold during the strobe windows is latched into the pixel buffer.
Analog “slow” shaping time (µs order) saves power.
Called “pulse length”
Latch set
Pixel memory
Pixel buffer

## Slide 77
Recall ALICE/ITS – Trigger distribution to FEE for ITS
ITS is a type II detector.
  Triggers are distributed to the ITS FEE (Readout Unit) directly from the LTU using the GBT protocol.
Type I detectors:
  Option would be to distribute triggers via the CRU over PON and GBT.
  This would add a latency of minimum 300 ns.
ITS

## Slide 78
Latency estimation for LM trigger / L0 trigger:
ALICE Timing – trigger detailed latency
We therefore go with the LM trigger!
 | LM trigger [ns] | L0 trigger [ns]
Trigger inputs at CTP | 425 | 1200
CTP processing + Low latency + LTU | 100 + 65 + 25 = 190 | 100 + 65 + 25 = 190
GBT downstream latencies (using Kintex-7 FPGA) | 190 | 190
Optical fibers (35 m long) from CTP to the readout electronic | 175 | 175
Electrical cables from the readout module to detector | 250 | 250
Total | 1230 | 2005

## Slide 79
Event rate – average number of interactions per second, Poisson distributed. Design goal is 100 kHz Pb-Pb collisions and 400 kHz p-p collisions.
Background – QED interactions, depends linearly to the beam intensity and on integration time. It significantly affects the inner layers only.
Noise – electronic pixel noise (thermal, RTS, etc.), generates fake pixel hits.
Trigger – all pixels with a signal over threshold during the strobe window (due to an event, background, noise, etc.) store an hit into their buffer.
Timing – sensor operations (triggered)
Time
Trg. 1
Trg. 2
Trg. 3
Ev. n+1
Ev. n+2
Ev. n+5
Ev. n-1
Ev. n
Ev. n+3
Ev. n+4
Ev. n+6
Time width within signals are recorded on trigger depends on the analog shaping time (≈ 5 µs)

## Slide 80
pixel buffer input
#1
#2
#3
Readout…
E0
Time [µs]
0
-1
1
2
3
4
5
6
7
8
9
Evn. #0 active time (pulse length)
Timing – detailed strobe and latching timing
Comparator
output
1
Threshold
Time walk
≈ 0.3 µs
Evn. #0 pulse
0
Trigger latency (≈ 1.2 µs)
Trg. #0
Drawings are (reasonably) to scale. Timing figures are indicative, not precise.
Strobe signal is driven by trigger.
The analogue pulse duration behaves as an analogue memory, holding the hit information until the arrival of the trigger pulse. The pulse duration must therefore last enough for the trigger to arrive.
Strobe window
Trigger connection
The trigger latency (to the matrix, including delay due to transmission and processing from the Readout Electronic ) will be about 1.2 µs.
Hit latched in pixel memory
Hit read from pixel matrix

## Slide 81
Trg. #0
pixel buffer input
#1
#2
#3
E0
E1
Time [µs]
0
-1
1
2
3
4
5
6
7
8
9
Evn. #1 active time (pulse length)
Evn. #0 active time (pulse length)
Timing – strobe re-latching previous strobe data
Comparator
output
1
Threshold
Time walk
≈ 0.3 µs
Evn. #0 pulse
0
Time walk
≈ 0.3 µs
Trigger latency (1.2 µs)
Trg. #1
Evn. #1 pulse
Drawings are (reasonably) to scale. Timing figures are approximated, not precise!
Strobe signal is driven by trigger.
In this example, the second trigger (Trg. #1) actually stores Evn. #1 and Evn. #0.
For simplicity, strobe delay and width are not illustrated here.
Trigger latency (1.2 µs)
Events separation (2µs in this example)
Strobe window
Strobe window
Readout…
In buffer #2 are stored both Event #0 and Event #1, even if event #0 has been already stored in buffer #1

## Slide 82
pixel buffer input
#1
#2
#3
E0
E1
Time [µs]
0
-1
1
2
3
4
5
6
7
8
9
Evn. #1 active time (pulse length)
Evn. #0 active time (pulse length)
Timing – trigger overlapping and storing two times the data
Comparator
output
1
Threshold
Time walk
≈ 0.3 µs
Evn. #0 pulse
0
Time walk
≈ 0.3 µs
Trigger latency (1.2 µs)
Trg. #0
Trg. #1
Evn. #1 pulse
Events separation (1.1µs in this example)
In this example, the second trigger (Trg. #1) is useless, as both Evn. #0 and Evn. #1 are stored at the occurrence of Trg. #0 (look at the strobe window). Trg. #1 will store again both events in a new buffer. Therefore we can “filter” such trigger (see next slide).
Strobe window
Strobe window
Readout…
In buffer #0 both Event #0 and Event #1, get stored
In buffer #1 again both Event #0 and Event #1 get stored

## Slide 83
Readout – trigger filtering
From timing slides: whenever a trigger arrives within a trigger latency (minus the analog signal time walk) from the previous trigger, data events associated with this trigger have been already stored by the previous one.
This happens just because the system has been designed with such equivalent “analog” memory, i.e. the long (about 5 µs) shaping time.
Therefore, no trigger are sent to the sensor within a trigger delay windows (minus all the other delays in the chain, both analog and digital).
Triggers from the CTP are filtered to a smaller (or equal) number of triggers sent to the detectors. Full trigger log is kept by the RU and associated to the outgoing data.
Clock
Data
Control / trigger
A trigger is passed ONLY if enough time has passed since the previous one (this time being ≈ trigger latency – active delay – other delays)
CTP main trigger
Every CTP trigger is anyway stored, and associate with trigger signal sent to the sensor
Referenced data
Control
Readout
Unit

## Slide 84
From CTP to RU
From RU to sensor
From sensor to RU
Timing – Readout Unit trigger filtering
Triggers from the CTP
≈ trg latency
Triggers to the chips
Logged into the RU with time and trigger ID.
Time [µs]
0
-1
1
2
3
4
5
6
7
Time [µs]
0
-1
1
2
3
4
5
6
7
Busy condition
The RU can retrieve which trigger has failed even if the trailer is corrupted/missing
0001
0100
0011
0010
Time [µs]
0
-1
1
2
3
4
5
6
7
Data from the sensor
Matched to logged triggers into the RU.
Multiple CTP triggers can be grouped into a single trigger sent to the sensor to the same trigger
The RU labels the data frame with all the CTP triggers associated to its trgID
Triggers close in time re-record the same information, and the sensor can handle a minimum trigger spacing of about 1 µs (less than 0.1% probability at 100 kHz). The RU will therefore “filter” close-in-time (≈ < 1 µs) triggers. This also allow for the busy flag to be propagated to the readout unit before another trigger is issued (see next slide).

## Slide 85: Hits and Event Data Rate
sPHENIX = 1/3 ALICE
Identical geometry for MVTX and ITS/IB(layer 0-2)
sPHENIX integration time ~5uS, less noise compared with ALICE with 30uS.
PYTHIA Sim

## Slide 86: ALICE Data Rate and Dead Time

## Slide 87: Readout Unit
Interface the sensors and powering system on the staves;
Control and trigger system
Implements ancillary functions like PS monitoring and control and health status of sensor operation parameters
One RU reads out 9 high-speed copper links (firefly cables)
For each sensor chip, running at 1.2Gb/s.
Located about 5m from MVTX in the IR
Radiation tolerant, GBT chipset over the “CERN Versatile Link”, each capable of 3.2Gb/s payload bandwidth, 3 chipset required to accommodate the full 9-MAPS readout.
A total of 48 RUs requried.
Firmware functionalities include:
  MAPS chip status and power control
  Data readout from 9 sensors per RU
  Control and Monitoring to/from the sensors
  Busy management
  Trigger management
  Data building and transmission through the GBT links to FELIX (or CRU)
  Remote update of the firmware
  Data handling in the FELIX (or CRU)

## Slide 88
48 RU boards
Readout Units Required for ITS & sPHENIX
48 inner staves
ITS IB:
Produce 120 staves in one year
120% contingency
sPHENIX: 48 +40% = 68

## Slide 89: Expected Hits/Data Rate Per Event
sPHENIX = ~25% ALICE per event
Trigger rate: 15/50 = 30%
Collision rate: 100kHz @sPHENIX
MAPS hits = noise + physics hits (noise < phy. hits)
Expected average data rate:
  sPHENIX = 30% x 30% ALICE = 10% ALICE

## Slide 90: Readout Unit – connections toward the staves
Readout Unit
Readout Unit
(4+4+4+4) data, (1+1+1+1) clock, (1+1+1+1) control
9 data lines, 1 clock, 1 control
(7+7+7+7) data, (1+1+1+1) clock, (1+1+1+1) control
Inner Layers
Middle Layers
Outer Layers
Readout Unit
16 data pairs,
400 Mb/s each
28 data pairs,
400 Mb/s each
9 data pairs,
1.2 Gb/s each
Each readout unit is connected to a stave through copper cables (5m long), which carry both bidirectional control lines and unidirectional clock and data lines.

## Slide 91: ITS Readout - Radiation Load
Position respect to beam |  |  | Radiation levels (total) |  |  | 
r | z | Name | TID | 1 MeV neq fluence | High energy hadron flux* | Charged particle flux
[cm] | [cm] |  | [krad] | [cm-2] | [kHz cm-2] | [kHz cm-2]
2.2 | [-13.5 ÷ 13.5] | ITS L0 | 2734 | 1.7 × 1013 | 765 (770) | 890 (910)
43 | [-73.7 ÷ 73.7] | ITS L6 | 20 | 8.1 × 1011 | 3.4 (4.9) | 4.5 (6.7)
79 | [-260 ÷ 260] | TPC In | 5.6 | 7.0 × 1011 | 1.35 (1.8) | 1.7 (3.45)
100 | 330 | RE | ≈ 5 | ≈ 1.6 × 1011 | 0.86 | 1.7
258 | [-260 ÷ 260] | TPC Out | 0.86 | 1.4 × 1011 | 0.27 (0.37) | 0.2 (0.3)
290 | [-290 ÷ 290] | TRD | 0.6 | 1.2 × 1011 | 0.23 (0.31) | 0.15 (0.23)
TID & fluence = (table 1 × 1.3data taking efficiency + Table 2 / 10better vacuum) × 10safety factor
Safety factor of 10 on top of TID and fluence calculated as in the above line.
Hadrons and charged particles as for 50 kHz Pb-Pb collisions (table 1, worst case scenario).
The average value within the z span is reported first, in brackets the peak value within the z interval.
* Momentum > 20 MeV.
We will assume 1 kHz cm-2 for simplicity as baseline.

## Slide 92: ALICE DAQ – “Radiation Hard Optical Link Project” Architecture
The GBTx supports three frame types:
  “GBT” Frame (3.28 Gb/s user bandwidth)
  “Wide Bus” Frame (3.52 Gb/s)
  “8B/10B” Frame (4.48 Gb/s)
GBT Frames include “Forward Error Correction”
Development of a high speed bi-directional radiation hard optical link:
GBT project:
  Rad-hard ASIC design
  Verification
  Functionality testing
  Packaging
Versatile link project:
  Opto-electronics
  Radiation hardness
  Functionality testing
  Packaging
Versatile optical link project
GBT project
GBT project
On-Detector
Radiation Hard Electronics
Off-Detector
Commercial Off-The-Shelf (COTS)

## Slide 93: Readout Unit – overall connections overview
Direct connections to sensors control, clock and data lines.
Fiber optic connection toward the CRU using the GBT chipset (3 GBTx + 1 GBT-SCA chip).
CAN bus as backup path to the DCS system (main path through CRU and GBT).
Control
Data @ 3.2 Gb/s
Data @ 3.2 Gb/s
Available
Trigger
Data @ 3.2 Gb/s
GBTx
GBTx
GBTx
3.2 Gb/s
3.2 Gb/s
3.2 Gb/s
3.2 Gb/s
3.2 Gb/s
SRAM
FPGA
FLASH
FPGA
Programmable Logic
SCA
Temperature, voltage & current monitoring
Redundant slow control from DCS through CAN bus
Power board monitoring and control

## Slide 94: Readout Unit – distribution and data/control connections per layer
Layout |  |  | Readout Units |  | GBT Versatile link |  |  |  | Fibers |  | 
Layer | Staves | Copper assembly | RUs × stave | RUs × layer | GBTx × layer | SCA × layer | VTRx × layer | VTTx × layer | TRG × layer | Data × layer | Ctrl × layer
0 | 12 | 12 | 1 | 12 | 36 | 12 | 24 | 12 | 12 | 36 | 12
1 | 16 | 16 | 1 | 16 | 48 | 16 | 32 | 16 | 16 | 48 | 16
2 | 20 | 20 | 1 | 20 | 60 | 20 | 40 | 20 | 20 | 60 | 20
3 | 24 | 96 | 1 | 24 | 72 | 24 | 48 | 24 | 24 | 72 | 24
4 | 30 | 120 | 1 | 30 | 90 | 30 | 60 | 30 | 30 | 90 | 30
5 | 42 | 168 | 1 | 42 | 126 | 42 | 84 | 42 | 42 | 126 | 42
6 | 48 | 192 | 1 | 48 | 144 | 48 | 96 | 48 | 48 | 144 | 48
Total |  | 624 |  | 192 | 576 | 192 | 384 | 192 | 192 | 576 | 192
CRU
ITS
Control
Data @ 3.2 Gb/s
Trigger
192 × Readout Unit
Data @ 3.2 Gb/s
Data @ 3.2 Gb/s
Not mandatory for “baseline” (Pb-Pb @ 50 kHz) operations.
Data also contain responses to control commands and status info

## Slide 95: RUv1 – Block Diagram

## Slide 96: RUv1 – Mechanical Layout
“standard” VME 6U board, only J1 connector towards backplane
Grounding and power from J1 connector, it will be VME compatible for testing
Balcony dimension representative only, to be optimized for final cables routing

## Slide 97: Prototype Readout System – RUv0 & GBTxFMC

## Slide 98: Prototype Setup
RUv0a with GBTxFMC & SFP
CERN USB-I2C dongle
ITS Power Board
Power Loads
Ref Clock

## Slide 99: Setup with two RUv0
RUv0
“CRU”
Alpide
Altera Arria10 Devkit
FireFly Cable
Sensor
Power
RefClk

## Slide 100: RU – Power Board Interface

## Slide 101: Schedule

## Slide 102: ALICE/ITS Readout R&D 5 RUv1 available for LANL R&D ~July 2017

## Slide 103: FELIX Board
Some documents available:
https://www.phenix.bnl.gov/WWW/publish/mxliu/sPHENIX/Readout/FELIX/

## Slide 104: ATLAS/FELIX BNL-711 PCIe Card
BNL-711 Board chosen for ATLAS FELIX project, and used in ATLAS phase I upgrade, which is projected to complete before sPHENIX.
Readout for ATLAS Phase-I sub-system of Liquid Argon Calorimeter, Level-1 calorimeter trigger, New small wheel of the muon spectrometer
Credit: Kai Chen (BNL), https://indico.bnl.gov/conferenceDisplay.py?confId=2653

## Slide 106: ATLAS/FELIX BNL-711 PCIe Card
Main features for FELIX PCIe Card
  Design: BNL/Omega group, Layout: BNL/Instrumentation, multiple users.
  A large Kintex Ultrascale FPGA, 1.5 M LC
  48 bi-directional GBT link, PCIex16 Gen3, 101 Gbps demonstrated
  2x DDR4 memory slots (v1.0, v1.5), removed v2.0
  TTC-timing input (v1.0, v1.5), allow timing mezzanine card (v2.0) – provide help design sPHENIX GTM mezzanine card
Current version: v1.5 prototype, can be ordered
Next version: v2.0 pre-production, design starts now, expect available Oct 2017
BNL/Omega group, Local expert expressed willing for help us to adapt FELIX in sPHENIX
  Boards for initial evaluation test, support firmware software development, timing mezzanine card design
  The team is also help in possible use of FELIX card in protoDune.
  The FELIX team is open for inputs in guiding the design to be more generic to various users.
Credit: Kai Chen (BNL), https://indico.bnl.gov/conferenceDisplay.py?confId=2653
FELIX v1.5 Card in server, BNL ATLAS Group

## Slide 107: FPGA Choices
Xlinux - Kintex Ultrascale
Available
XCKU115
FELIX v1.5 test boards
1.451
1.3
0.66
4320
75.9
(48 input + 48 output fiber links in FELIX)
48
6
CRU/ PCIe40
FELIX

## Slide 108: MVTX options: 6x (PCIe card + server)
Buffer box
Event Buffering and Data Compressor (EBDC): Rack server that can host at 1x PCIex16 cards + 2x 10 Gbps Ethernet port
Data Aggregation Module (DAM):
PCIex8 or x16 card with multiple (48x) GBT fiber IO
Example: Dell PowerEdge R830
2x12 cores, 2x10 GBps, ~ 10k$
Option 1: LHCb/ALICE CRU
Option 2: ATLAS FELIX
Option 3: build our own based on ALICE/ATLAS exp.
MVTX/TPC

## Slide 109: Electronics R&D – Cont. FELIX and MVTX Power Distribution Boards
FELIX: visited BNL Labs and had FELIX system demo
  V1.5 boards, all functionalities available- data, slow control and Timing/Trigger/Busy, w/ GBT
  Multi-channel GBT links and PCIe interface code developed, with examples of user modules
  V2.0, available ~end of 2017, sPHENIX application
  A 1.5v FELIX board produced and tested, ready for shipment to LANL; Optical cables etc. to be ordered soon for LANL test bench
Power distribution boards and PS
  LBNL PS distribution board available for R&D from CERN/LBNL ~ August. Order placed, 4wks + testing
  R&D power supply and control system ordered (CAEN), available ~August
FELIX: tested @BNL
To be shipped to LANL

## Slide 110: Comm. RU

## Slide 111: ALICE O2 – Detailed Layout

## Slide 112: O2 Data Flow

## Slide 113: CRU Interfaces
CRU has three interfaces:
  1 – GBT Link (Radiation Tolerant High Speed Optical Link)
  2 – GBT/10Gigabit PON
  3 – DDL3 link ( PCIe Gen 3 x16)

## Slide 114: CRU – Connections to/from ITS
O2 FLP
CRU
Readout Unit
Sensor
8 RUs per CRU
< 2 CRUs per FLP
Up to 28 Data
lines per RU
The O2 First Level Processors (FLPs) manage the detectors and collect/aggregate the data streams before storage. Each FLP hosts up to two Common Readout Units (CRU), which are optically interfaced with the ITS front-end electronics (Readout Units).
Up to 3 GBT link per RU (3.2 Gb/s each)
FLP architecture
CRU architecture

## Slide 115: CRU Architecture

## Slide 117: ALICE DAQ – CRU Data Paths

## Slide 118: Servers
2U server, capable of hosting 2 CRUs
2 initial candidates
  Dell PowerEdge R730
    Initial tests with Altera Development Kit, good results (55 Gbps)
  Asus ESC4000-G3
    To be tested
Thorough evaluation only once CRU is available
Final O2 hardware to be purchased ALAP, cannot define it now
Need support with FLP purchase: contact “alice-o2-flp-prototype@cern.ch”

## Slide 119: CRU – Prototype efforts
C-RORC/G-RORC
12 bi-directional links @ 6 Gb/s
PCIe Gen2 x8
2 x RAM SLOTS
FMC connector
XILINX VIRTEX6 FPGA
CRU
48 bi-directional links @ 10 Gb/s
PCIe Gen3 x16
ALTERA ARRIAX FPGA

## Slide 120: Altera Arria-10 Development Kit
Arria 10 GX 1150, 4500$
1 x SFP+
1 x QSFP
2 x FMC
PCIe Gen3 x8
https://www.altera.com/products/boards_and_kits/dev-kits/altera/kit-a10-gx-fpga.html

## Slide 121: Dell Servers & Readout Cards
A few comments:
Tested on a DELL server
LENGTH !!!
WIDTH !!!
It is not “easy” to install it, to be compared with the actual CRU

## Slide 122: FireFly Cables

## Slide 123: MOSAIC Test Bench @LANL

## Slide 124: Test under internal trigger (40MHz)
Readout speed 1.2 Gb/s and 50 injections.
Scan the noise per pixel and the average value is 7.47±1.80 (e).
From Xuan

## Slide 125: Test under internal trigger (40MHz)
Readout speed 600 Mb/s and 50 injections.
Scan the noise per pixel and the average value is 7.53±1.76 (e).

## Slide 126: External Trigger and Source
Single chip readout
Use a pulse generator as the external trigger
Use the Strontium-90 to produce beta rays.
  Vary the distance between the source and the silicon chip
Sr-90
1kHZ trigger
Xuan et al

## Slide 127: A Single-chip MAPS Telescope
Check the readout occupancy and efficiency under different internal trigger clock (10-40MHz), readout speed (400-1200Mb/s) and threshold (set up by the analog signal or the configuration file?).
Set cosmic ray triggers with scintillator bars or pads to read out single MVTX chip with the external coincidence cosmic ray trigger.
Design of single chip based telescope in progress
μ-
μ-
Efficiency tester
Simple tracker