| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2 | MVTX Project |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 21 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish: 1/27/23 fixed cost: calculated fixed cost: $1,239,333 Resource cost: $2,365,560 Cost: $3,604,893 Overhead: Cost with Overhead+contingency: $4,781,063

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1 | MVTX Project Management |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 22 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 904 days Start: 4/1/19 Finish: 9/15/22 calculated fixed cost: $50,000 resource cost: $493,050 cost: 543,050 overhead: Cost with Overhead+contingency: $641,660

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.1 | Milestone Start MVTX |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 23 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 4/1/19 Finish: 9/15/22 Cost with Overhead+contingency: 0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.2 | lead Coordinator |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 24 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 3/17/22 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.3 | Project Manager |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 25 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 9/15/22 Resource Cost: $394,478 Cost +Overhead+contingency: $473,374

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.4 | Mechanical Integration Engineer |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 26 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 3/17/22 Resource cost: $98,572 Cost with Overhead+contingency: $118,286

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | Engineer (sPHENIX) |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.5 | Electronics Integration |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 27 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 3/17/22 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.6 | Travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 28 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 3/17/22 Calculated Fixed cost: $ 50,000 Cost: $50,000 Cost with Overhead+contingency: $50,000

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2 | Electronics |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 29 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 332 days Start: 4/1/19 Finish: 7/7/20 Calculated Fixed Cost: $319,647 Resources Cost: 112,044 Cost: $ 431,691 Cost with Overhead+contingency: $573,130

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1 | Stave extemsion cable |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 30 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 182 days Start: 4/1/19 Finish:12/10/19 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1.1 | Stave Extension Cable design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 31 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 months Start: 4/1/19 Finish: 7/19/19 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2..1.2 | Stave Extension Cable prototype |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 32 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 months Start: 7/22/19 Finish: 9/13/19 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1.3 | Stabe Extension cable review |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 33 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 days Start: 9/16/19 Finish: 9/17/19 Cost with Overhead+contingency: 0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1.4 | Stabe Extension cable procure |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 34 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 months Start: 9/18/19 Finish: 11/12/19 Cost with Overhead+contingency: 0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1.5 | Stabe Extension cable test |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 35 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 11/13/19 Finish: 12/10/19 Cost with Overhead+contingency: 0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2 | RU |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 36 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 385 days Start: 4/1/19 Finish: 9/18/20 calculated fix cost: $ 87,108 Resources Cost: $121,434 Cost with Overhead+contingency: $161,904

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.8 | RU: travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 37 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 4/1/19 Finish: 9/18/20 Calcu;ated Fixed Cost: $18,780 Cost: $18,780 Cost with Overhead+contingency: $25,353

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.1 | RU: cold plate |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 38 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 weeks Start: 4/1/19 Finish: 9/26/19 Calculated Fixed Cost: $15,353 Cost: $ 15,353 Cost with Overhead+contingency: $20,727

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.2 | RU: transition board |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 39 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 hours Start: 4/29/19 Finish: 4/30/19 Fixed Cost: $7,935 Resource Cost: $850 Cost: $8,785 Cost with Overhead+contingency: $10,542

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.3 | RU: Power mezzanine |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 40 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/30/19 Finish: 5/14/19 Calculated Fixed Cost: $ 4,757 Cost: $4,757 Cost with Overhead+contingency: $5,708

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.4 | RU: Test/QA |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 41 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 320 hours Start: 7/20/20 Finish: 9/11/20 Fixed Cost: $7,500 Calculated Fixed Cost: $7,500 Resources Cost: $32,554 Cost: $40,054 Cost with Overhead+contingency: $54,072

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.5 | RU: procure 60 SamTec Cables |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 42 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 60 days Start: 4/1/19 Finish: 6/21/19 Fixed Cost: $30,000 Calculated Fixed Cost: $30,000 Resources Cost: $30,922 Cost with Overhead: $41,745

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.6 | RU: Ship to UT Austin from CERN |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 43 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 9/14/20 Finish: 9/19/20 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $0 Cost with Overhead: $2,700

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.7 | RU: Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 44 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 9/14/20 Finish: 9/18/20 Fixed Cost: $783 Calculated Fixed Cost: $783 Resources Cost: $0 Cost with Overhead: $1,057

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3 | Felix |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 42 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 161 days Start: 4/1/20 Finish: 11/12/20 Fixed Cost: $0 Calculated Fixed Cost: $76,400 Resources Cost: $17,350 Cost: $93,750 Cost with Overhead: $112,801

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.1 | felix: First production |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 46 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 weeks Start: 4/1/20 Finish: 4/28/20 Fixed Cost: $8,000 Calculated Fixed Cost: $80,000 Resources Cost: $3,152 Cost: $11,152 Cost with Overhead: $13,382

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.2 | FELIX: procure optical fiber |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 47 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/1/20 Finish: 4/14/20 Fixed Cost: $50 Calculated Fixed Cost: $50 Resources Cost: $315 Cost: 365 Cost with Overhead: $438

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.3 | FELIX: Test/QA |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 48 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/15/20 Finish: 4/28/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost with Overhead: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.4 | FELIX: Procure 7 remaining units |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 49 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 8 weeks Start: 8/24/20 Finish: 10/28/20 Fixed Cost: $56,000 Calculated Fixed Cost: $56,000 Resources Cost: $1,280 Cost: 57,280 Cost with Overhead: $68,736

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.5 | FELIX: Procure 57 optical fibers |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 50 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/29/20 Finish: 5/12/20 Fixed Cost: $2,850 Calculated Fixed Cost: $2,850 Resources Cost: $315 Cost: $3,165 Cost with Overhead: $3,798

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.6 | Felix: test/QA |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 51 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5.3 days Start: 10/29/20 Finish: 11/05/20 Fixed Cost: $7,500 Calculated Fixed Cost: $7,500 Resources Cost: $12,2 Cost: $19,788 Cost with Overhead: $23,746

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.7 | Felix: Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 52 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 11/5/20 Finish: 11/20/20 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $0 Cost: 2,000 Cost with Overhead: $2,700

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4 | Power System |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 53 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 200 days Start: 4/1/19 Finish: 1/6/20 Fixed Cost: $0 Calculated Fixed Cost: $156,139 Resources Cost: $60,368 Costs: $216,507 Cost with Overhead: $259,808

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1 | MAPS Power Boards |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 54 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 75 days Start: 4/1/19 Finish: 7/12/19 Fixed Cost: $0 Calculated Fixed Cost: $79,020 Resources Cost: $49,672 Costs: $128,692 Cost with Overhead: $154,431

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.1 | Fabricate Breakout Board |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 20 days |  |  |

9. Approved Changes

9. Element Task Description

Duration: 60 days Start: 4/1/19 Finish: 4/26/19 Fixed Cost: $6,600 Calculated Fixed Cost: $6,600 Resources Cost: $0 Costs: 6,600 Cost with Overhead: $7,920

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.2 | Fabicate PB to Stave |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 56 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 60 hours Start: 4/29/19 Finish: 5/8/19 Fixed Cost: $8,000 Calculated Fixed Cost: $8,000 Resources Cost: $7,080 Cost: 15,080 Cost with Overhead: $18,096

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.3 | Fabricate Cooling |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 57 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/29/19 Finish: 5/10/19 Fixed Cost: $3,420 Calculated Fixed Cost: $3,420 Resources Cost: $2,112 Cost: 5,532 Cost with Overhead: $6,638

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.4 | Production power boards |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 58 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 40 days Start: 4/29/19 Finish: 6/21/19 Fixed Cost: $60,000 Calculated Fixed Cost: $60,000 Resources Cost: $8,620 Cost: $68,620 Cost with Overhead: $82,345

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2..4.1.5 | Assembly power boards |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 59 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 hours Start: 6/24/19 Finish: 6/19/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $3,540 Cost with Overhead: $4,248

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.6 | Test Power Boards |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 60 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 90 hours Start: 6/27/19 Finish: 7/12/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $10,620 Costs: $10,620 Cost with Overhead: $12,744

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.7 | Power cable Harness |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 61 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 4/29/19 Finish: 5/17/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $14,160 Cost: $14,160 Cost with Overhead: $16,992

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.8 | Ship power system to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 62 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 hours Start: 4/1/19 Finish: 4/4/19 Fixed Cost: $1,000 Calculated Fixed Cost: $1,000 Resources Cost: $3,540 Cost: $ 4,540 Cost with Overhead: $5,448

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2 | Power Suppies |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 63 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 200 days Start: 4/1/19 Finish: 1/6/20 Fixed Cost: $0 Calculated Fixed Cost: $77,119 Resources Cost: $10,696 Cost: $87,815 Cost with Overhead: $105,377

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.1 | CAEN A3484 48V PS |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 64 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 200 days Start: 4/1/19 Finish: 1/6/20 Fixed Cost: $8,607 Calculated Fixed Cost: $8,607 Resources Cost: $0 Cost: 8,607 Cost with Overhead: $10,328

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.2 | CAEN SY4527 Main Frame |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 65 |  |  |

9. Approved Changes

| 9. Element Task Description |  |  |
| --- | --- | --- |
| Duration: 30 days Start: 4/1/19 Finish: 5/10/19 Fixed Cost: $11,620 Calculated Fixed Cost: $11,620 Resources Cost: $0 Cost: 11,620 Cost with Overhead: $13,944 |  |  |
| 1. Project Title: | 2. Date: | 3: Person Responsible |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.3 | CAEN A4532 Power board |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 66 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 5/13/19 Finish: 5/17/19 Fixed Cost: $1,216 Calculated Fixed Cost: $1,216 Resources Cost: $0 Cost: 1,216 Cost with Overhead+contingency: $1,459

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.4 | CAEN A2518 Power module |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 67 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.3 days Start: 5/20/19 Finish: 5/21/19 Fixed Cost: $43,676 Calculated Fixed Cost: $43,676 Resources Cost: $0 Cost: $43,676 Cost with Overhead+contingency: $52,411

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.5 | Cabling |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 68 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 5/21/19 Finish: 5/28/19 Fixed Cost: $10,000 Calculated Fixed Cost: $10,000 Resources Cost: $4,720 Cost: $14,720 Cost with Overhead+contingency: $17,664

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.6 | test PB with PS |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 69 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 5/28/19 Finish: 6/4/19 Fixed Cost: $1,216 Calculated Fixed Cost: $0 Resources Cost: $4,720 Cost: $4,720 Cost with Overhead+contingency: $5,664

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.7 | Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 70 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.3 days Start: 6/4/19 Finish: 6/5/19 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $1,256 Cost: $3,256 Cost with Overhead+contingency: $3,907

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3 | Mechanics and Detector Assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 71 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 100 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $535,486 Resources Cost: $1,202,571 Cost: $1,738,057 Cost with Overhead+contingency: $2,361,763

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1 | Staves |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 72 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 345 days Start: 4/1/19 Finish:7/24/20 Fixed Cost: $0 Calculated Fixed Cost: $146,852 Resources Cost: $124,034 Cost: $270,886 Cost with Overhead+contingency: $365,131

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1 | Stave production |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 73 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 267 days Start: 4/1/19 Finish:4/7/20 Fixed Cost: $0 Calculated Fixed Cost: $57,360 Resources Cost: $72 Cost: $57,432 Cost with Overhead+contingency: $77,534

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1.1 | Staves test and QA at cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 74 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 160 days Start: 7/31/19 Finish: 3/10/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1.2 | CERN test system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 75 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 4/1/19 Finish:4/1/19 Fixed Cost: $7,360 Calculated Fixed Cost: $7,360 Resources Cost: $72 Cost: $72,432 Cost with Overhead+contingency: $10,034

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1.3 | travel and per diem at cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 76 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 5/20/19 Finish:5/20/19 Fixed Cost: $50,000 Calculated Fixed Cost: $50,000 Resources Cost: $0 Cost: $50,000 Cost with Overhead+contingency: $67,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1.4 | Test and QA at cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 77 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 180 days Start: 7/31/19 Finish:4/7/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.2 | Stave assembly tooling |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 78 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 120 days Start: 2/10/20 Finish:7/24/20 Fixed Cost: $0 Calculated Fixed Cost: $25,000 Resources Cost: $44,352 Cost: $69,352 Cost with Overhead+contingency: $93,625

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.2.1 | stave tooling design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 79 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 weeks Start: 2/10/20 Finish:3/6/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $13,440 Cost: $13,440 Cost with Overhead+contingency: $18,144

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.2.2 | stave tooling final jig design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 80 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 40 days Start: 3/9/20 Finish:5/1/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,880 Cost: $26,880 Cost with Overhead+contingency: $36,288

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.2.3 | procure assembly fixtures |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 81 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 60 days Start: 5/4/20 Finish:7/24/20 Fixed Cost: $25,000 Calculated Fixed Cost: $25,000 Resources Cost: $4,032 Cost: $29,032 Cost with Overhead+contingency: $39,193

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3 | Metrology |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 82 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 105 days Start: 2/10/20 Finish:7/3/20 Fixed Cost: $0 Calculated Fixed Cost: $7,000 Resources Cost: $58,007 Cost: $65,007 Cost with Overhead+contingency: $87,759

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3.1 | Metrology design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 83 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 months Start: 2/10/20 Finish:4/3/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,880 Cost: $26,880 Cost with Overhead+contingency: $36,288

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3.2 | design jigs |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 84 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 40 days Start: 4/6/20 Finish:5/29/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,880 Cost: $26,880 Cost with Overhead+contingency: $36,288

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3.3 | procure jigs |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 85 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 weeks Start: 6/1/20 Finish:6/26/20 Fixed Cost: $5,000 Calculated Fixed Cost: $5,000 Resources Cost: $315 Cost: $5,315 Cost with Overhead+contingency: $7,175

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3.4 | ship to lbnl |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 86 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 6/29/20 Finish:7/3/20 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $3,932 Cost: $5,932 Cost with Overhead+contingency: $8,008

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4 | Shipping and storage components |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 87 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 227 days Start: 4/1/19 Finish:2/11/20 Fixed Cost: $0 Calculated Fixed Cost: $33,492 Resources Cost: $21,603 Cost: $55,095 Cost with Overhead+contingency: $73,814

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.1 | Design&fabricate storage |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 88 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 39 days Start: 4/1/19 Finish:5/23/19 Fixed Cost: $6,992 Calculated Fixed Cost: $6,992 Resources Cost: $5,355 Cost: $12,347 Cost with Overhead+contingency: $16,668

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.2 | design&fabricate shipment |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 89 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 50 days Start: 12/4/19 Finish:2/11/20 Fixed Cost: $11,500 Calculated Fixed Cost: $11,500 Resources Cost: $5,480 Cost: $16,980 Cost with Overhead+contingency: $22,923

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.3 | design shipping container |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 90 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 5/20/19 Finish:5/24/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $9,480 Cost: $9,480 Cost with Overhead+contingency: $12,798

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.4 | procure stave shipping |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 91 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 4/1/19 Finish:4/1/19 Fixed Cost: $10,000 Calculated Fixed Cost: $10,000 Resources Cost: $1,288 Cost: $11,288 Cost with Overhead+contingency: $14,674

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.5 | Ship to cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 92 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 months Start: 4/2/19 Finish:5/27/19 Fixed Cost: $5,000 Calculated Fixed Cost: $5,000 Resources Cost: $0 Cost: $5,000 Cost with Overhead+contingency: $6,750

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5 | shipping staves to bnl |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 93 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 202 days Start: 7/31/19 Finish:5/7/20 Fixed Cost: $0 Calculated Fixed Cost: $24,000 Resources Cost: $0 Cost: $24,000 Cost with Overhead+contingency: $32,400

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5.1 | shipping staves from cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 94 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 7 days Start: 7/31/19 Finish:8/8/19 Fixed Cost: $6,000 Calculated Fixed Cost: $6,000 Resources Cost: $0 Cost: $6,000 Cost with Overhead+contingency: $8,100

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5.2 | shipping staves from cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 95 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 7 days Start: 10/30/19 Finish:11/7/19 Fixed Cost: $6,000 Calculated Fixed Cost: $6,000 Resources Cost: $0 Cost: $6,000 Cost with Overhead+contingency: $8,100

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5.3 | shipping staves from cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 96 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 7 days Start: 4/1/20 Finish:2/6/20 Fixed Cost: $6,000 Calculated Fixed Cost: $6,000 Resources Cost: $0 Cost: $6,000 Cost with Overhead+contingency: $8,100

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5.4 | shipping staves from cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 97 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 7 days Start: 4/29/20 Finish:5/7/20 Fixed Cost: $6,000 Calculated Fixed Cost: $6,000 Resources Cost: $0 Cost: $6,000 Cost with Overhead+contingency: $8,100

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2 | carbon structures |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 98 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $359,820 Resources Cost: $867,641 Cost: $1,227,461 Cost with Overhead+contingency: $1,670,999

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.1 | Mechanics detector design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 99 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 100 days Start: 4/1/19 Finish:8/16/19 Fixed Cost: $0 Calculated Fixed Cost: $2,000 Resources Cost: $0 Cost: $389,026 Cost with Overhead+contingency: $525,185

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lanl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.1.1 | develop maps inner |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 100 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 months Start: 4/1/19 Finish:7/19/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $195,507 Cost: $195,507 Cost with Overhead+contingency: $263,935

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.1.2 | mechanical model MIT |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 101 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 months Start: 4/1/19 Finish:8/16/19 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $191,519 Cost: $193,519 Cost with Overhead+contingency: $261,251

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3 | Mechanics Fabrication |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 102 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $337,000 Resources Cost: $451,175 Cost: $788,995 Cost with Overhead+contingency: $1,091,429

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.1 | Travel LBNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 103 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $70,000 Calculated Fixed Cost: $70,000 Resources Cost: $0 Cost: $70,000 Cost with Overhead+contingency: $94,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4 | End wheels |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 104 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 145 days Start: 8/19/19 Finish:3/6/20 Fixed Cost: $0 Calculated Fixed Cost: $75,940 Resources Cost: $219,272 Cost: $295,212 Cost with Overhead+contingency: $428,057

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.8 | tooling Design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 105 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.75 months Start: 8/19/19 Finish:10/4/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $33,340 Cost: $33,340 Cost with Overhead+contingency: $48,343

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.9 | tooling material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 106 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 10/7/19 Finish:11/15/19 Fixed Cost: $60,000 Calculated Fixed Cost: $60,000 Resources Cost: $1,644 Cost: $61,644 Cost with Overhead+contingency: $89,384

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.10 | Tooling assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 107 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 107 days Start: 11/18/19 Finish:12/27/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $32,880 Cost: $32,880 Cost with Overhead+contingency: $47,676

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.11 | Material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 108 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 days Start: 12/30/19 Finish:12/31/19 Fixed Cost: $15,940 Calculated Fixed Cost: $15,940 Resources Cost: $3,952 Cost: $19,892 Cost with Overhead+contingency: $28,843

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.12 | Production and test |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 109 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 48 days Start: 1/1/20 Finish:3/6/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $147,456 Cost: $147,456 Cost with Overhead+contingency: $213,811

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2 | CYSS Cylindrical STructure |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 110 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 98 days Start: 8/19/19 Finish:1/1/20 Fixed Cost: $0 Calculated Fixed Cost: $75,940 Resources Cost: $104,073 Cost: $180,013 Cost with Overhead+contingency: $261,018

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.8 | Tooling design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 111 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.2 months Start: 8/19/19 Finish:9/19/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $22,752 Cost: $22,752 Cost with Overhead+contingency: $32,990

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.2 | tooling material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 112 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 9/20/19 Finish:10/10/19 Fixed Cost: $30,000 Calculated Fixed Cost: $30,000 Resources Cost: $0 Cost: $30,000 Cost with Overhead+contingency: $43,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.3 | Tooling iteration |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 113 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 10/11/19 Finish:10/31/19 Fixed Cost: $30,000 Calculated Fixed Cost: $30,000 Resources Cost: $0 Cost: $30,000 Cost with Overhead+contingency: $43,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.4 | Procure CYSS Material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 114 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 11/1/19 Finish:11/7/19 Fixed Cost: $15,940 Calculated Fixed Cost: $15,940 Resources Cost: $0 Cost: $15,940 Cost with Overhead+contingency: $23,113

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.5 | Tooling assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 115 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 11/8/19 Finish:11/28/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $16,440 Cost: $16,440 Cost with Overhead+contingency: $23,838

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.6 | Production & test CYSS |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 116 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 24 days Start: 11/29/19 Finish:1/1/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $64,881 Cost: $64,881 Cost with Overhead+contingency: $94,077

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.7 | Milestone complete |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 117 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 1/1/20 Finish:1/1/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3 | Service Barrel (SB) |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 118 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 80 days Start: 10/11/19 Finish:1/30/20 Fixed Cost: $0 Calculated Fixed Cost: $115,940 Resources Cost: $127,831 Cost: $243,771 Cost with Overhead+contingency: $307,854

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.1 | review SB design-fabrication |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 119 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 40 days Start: 10/11/19 Finish:12/5/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $12,646 Cost: $12,646 Cost with Overhead+contingency: $16,440

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.2 | hold SB Review |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 120 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 10/11/19 Finish:10/31/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $12,581 Cost: $12,581 Cost with Overhead+contingency: $16,355

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.3 | Tooling |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 121 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 11/1/19 Finish:11/28/19 Fixed Cost: $40,000 Calculated Fixed Cost: $40,000 Resources Cost: $50,480 Cost: $90,480 Cost with Overhead+contingency: $108,576

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.4 | Procure SB Material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 122 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 11/29/19 Finish:12/5/19 Fixed Cost: $75,940 Calculated Fixed Cost: $75,940 Resources Cost: $0 Cost: $75,940 Cost with Overhead+contingency: $98,722

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.5 | Production & Test SE |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 123 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 21 days Start: 1/2/20 Finish:1/30/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $52,123 Cost: $52,123 Cost with Overhead+contingency: $67,760

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.6 | Milestone Complete |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 124 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 1/30/20 Finish:1/30/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.4 | MVTX Final Design Review |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 125 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 23 days Start: 11/1/19 Finish:12/3/19 Fixed Cost: $0 Calculated Fixed Cost: $20,000 Resources Cost: $29,440 Cost: $49,440 Cost with Overhead+contingency: $54,384

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.4.1 | MVTX Design Review LBNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 126 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 days Start: 11/1/19 Finish:11/4/19 Fixed Cost: $10,000 Calculated Fixed Cost: $10,000 Resources Cost: $1,976 Cost: $11,976 Cost with Overhead+contingency: $13,174

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.4.2 | Incorporate review comments |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 128 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 9 days Start: 11/7/19 Finish:11/19/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,892 Cost: $8,892 Cost with Overhead+contingency: $9,781

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lanl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.4.5 | Incorporate review comments |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 129 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 9 days Start: 11/20/19 Finish:12/2/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $11,304 Cost: $11,304 Cost with Overhead+contingency: $12,434

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.3 | Complete final design LBNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 130 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 12/3/19 Finish:12/3/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $988 Cost: $988 Cost with Overhead+contingency: $1,087

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lanl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.6 | Complete final design LANL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 131 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 12/3/19 Finish:12/3/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $1,256 Cost: $1,256 Cost with Overhead+contingency: $1,382

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3 | Barrel Assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 132 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 406 days Start: 8/9/19 Finish:2/26/20 Fixed Cost: $0 Calculated Fixed Cost: $28,814 Resources Cost: $210,896 Cost: $239,710 Cost with Overhead+contingency: $325,633

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1 | Barrel assembly and testing |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 133 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 406 days Start: 8/9/19 Finish:2/26/21 Fixed Cost: $0 Calculated Fixed Cost: $28,814 Resources Cost: $210,896 Cost: $239,710 Cost with Overhead+contingency: $325,633

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.1 | Receive 1st batch stave |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 134 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 8/9/19 Finish:8/9/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.2 | Test and rework 1st batch |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 135 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 12 days Start: 8/12/19 Finish:8/27/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,240 Cost: $5,240 Cost with Overhead+contingency: $6,812

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.3 | Receive 2nd batch stave |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 136 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 11/8/19 Finish:11/8/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.4 | Test and Rework 2nd batch |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 137 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 12 days Start: 11/11/19 Finish:11/26/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,449 Cost: $5,449 Cost with Overhead+contingency: $7,084

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.5 | Receive 3rd batch staves |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 138 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 2/7/20 Finish:2/7/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.6 | Test and review 3rd batch |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 139 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 512days Start: 2/10/20 Finish:2/25/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,449 Cost: $5,449 Cost with Overhead+contingency: $7,084

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.7 | Receive 4th batch staves |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 140 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 5/8/20 Finish:5/8/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.8 | Test and rework 4th batch |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 141 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 12 days Start: 5/11/20 Finish:5/26/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,449 Cost: $5,449 Cost with Overhead+contingency: $7,084

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9 | layer assembly and test |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 142 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 140 days Start: 3/9/20 Finish:9/18/20 Fixed Cost: $0 Calculated Fixed Cost: $5,336 Resources Cost: $68,670 Cost: $74,006 Cost with Overhead+contingency: $101,329

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.1 | test installation of staves |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 143 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 3/9/20 Finish:4/3/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $7,056 Cost: $7,056 Cost with Overhead+contingency: $9,526

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.2 | Hold half-detector assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 144 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 4/6/20 Finish:4/10/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $2,672 Cost: $2,672 Cost with Overhead+contingency: $3,206

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.3 | Install staves onto layers |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 145 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 70 days Start: 4/13/20 Finish:7/17/20 Fixed Cost: $2,760 Calculated Fixed Cost: $2,760 Resources Cost: $33,656 Cost: $36,416 Cost with Overhead+contingency: $50,982

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.4 | Test and rework layer |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 146 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 7/20/20 Finish:8/28/20 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $14,278 Cost: $16,854 Cost with Overhead+contingency: $22,752

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.5 | Perform Half-Detector |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 147 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 8/31/20 Finish:9/18/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $11,009 Cost: $11,009 Cost with Overhead+contingency: $14,862

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.6 | Milestone Complete |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 148 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 9/18/20 Finish:9/18/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10 | Half barrel #1 assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 149 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 95 days Start: 9/21/20 Finish:1/29/21 Fixed Cost: $0 Calculated Fixed Cost: $11,739 Resources Cost: $60,206 Cost: $71,945 Cost with Overhead+contingency: $97,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.1 | Assemble Layers and barrel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 150 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 9/21/20 Finish:10/16/20 Fixed Cost: $2,760 Calculated Fixed Cost: $2,760 Resources Cost: $13,965 Cost: $16,725 Cost with Overhead+contingency: $23,415

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.2 | Test and rework half barrel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 151 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 10/19/20 Finish:11/27/20 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $19,200 Cost: $21,776 Cost with Overhead+contingency: $29,398

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.3 | Perform Half-detector |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 152 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 11/30/20 Finish:12/11/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,120 Cost: $8,120 Cost with Overhead+contingency: $10,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.4 | Validation of final assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 153 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 12149/20 Finish:1/8/21 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $13,976 Cost: $16,552 Cost with Overhead+contingency: $22,345

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.5 | Pack/Ship Final Assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 154 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 1/11/21 Finish:1/29/21 Fixed Cost: $3,827 Calculated Fixed Cost: $3,827 Resources Cost: $4,945 Cost: $8,772 Cost with Overhead+contingency: $11,843

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11 | Half barrel #2 assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 155 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 95 days Start: 10/19/20 Finish:2/26/21 Fixed Cost: $0 Calculated Fixed Cost: $11,739 Resources Cost: $60,433 Cost: $72,172 Cost with Overhead+contingency: $98,280

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.1 | Assemble Layers and barrel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 156 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 10/19/20 Finish:11/13/20 Fixed Cost: $2,760 Calculated Fixed Cost: $2,760 Resources Cost: $14,192 Cost: $16,952 Cost with Overhead+contingency: $23,733

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.2 | Test and rework half barrel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 157 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 11/16/20 Finish:12/25/20 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $19,200 Cost: $21,776 Cost with Overhead+contingency: $29,398

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.3 | Perform Half-detector |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 158 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 12/28/20 Finish:1/8/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,120 Cost: $8,120 Cost with Overhead+contingency: $10,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.4 | Validation of final assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 159 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 1/11/21 Finish:2/5/21 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $13,976 Cost: $16,552 Cost with Overhead+contingency: $22,345

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.5 | Pack/Ship Final Assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 160 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 2/8/21 Finish:2/26/21 Fixed Cost: $3,827 Calculated Fixed Cost: $3,827 Resources Cost: $4,945 Cost: $8,772 Cost with Overhead+contingency: $11,843

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.6 | Milestone Complete |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 161 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 2/26/21 Finish:2/26/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4 | Integration and Infrastructure |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 162 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $334,200 Resources Cost: $557,895 Cost: $892,095 Cost with Overhead+contingency: $1,243,127

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.1 | Clean Tent/room |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 163 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 100 days Start: 10/1/19 Finish:2/17/20 Fixed Cost: $50,000 Calculated Fixed Cost: $50,000 Resources Cost: $0 Cost: $50,000 Cost with Overhead+contingency: $67,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2 | Cooling system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 164 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $87,000 Resources Cost: $42,239 Cost: $129,239 Cost with Overhead+contingency: $174,472

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.1 | travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 165 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $25,000 Calculated Fixed Cost: $25,000 Resources Cost: $0 Cost: $25,000 Cost with Overhead+contingency: $33,750

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.2 | design(modify ALICE) |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 166 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 month Start: 4/20/20 Finish:5/15/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $21,304 Cost: $21,304 Cost with Overhead+contingency: $28,760

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.3 | Mockup testing |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 167 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 3 weeks Start: 5/18/20 Finish:6/5/20 Fixed Cost: $20,000 Calculated Fixed Cost: $20,000 Resources Cost: $12,551 Cost: $32,551 Cost with Overhead+contingency: $43,944

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.4 | Final Design of Cooling system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 168 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 6/8/20 Finish:6/12/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,720 Cost: $6,720 Cost with Overhead+contingency: $9,072

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.5 | Procure cooling plant |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 169 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 100 days Start: 10/1/21 Finish:2/17/22 Fixed Cost: $40,000 Calculated Fixed Cost: $40,000 Resources Cost: $1,664 Cost: $41,664 Cost with Overhead+contingency: $56,246

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.6 | Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 170 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 2/18/22 Finish:2/24/22 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $0 Cost: $2,000 Cost with Overhead+contingency: $2,700

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3 | Safety system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 171 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 724 days Start: 4/1/19 Finish:1/6/22 Fixed Cost: $0 Calculated Fixed Cost: $35,200 Resources Cost: $98,795 Cost: $133,995 Cost with Overhead+contingency: $179,550

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.1 | travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 172 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 700 days Start: 4/1/19 Finish:12/3/21 Fixed Cost: $25,000 Calculated Fixed Cost: $25,000 Resources Cost: $0 Cost: $25,000 Cost with Overhead+contingency: $33,750

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.2 | Define MVTX Safety andInterlock system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 173 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 6/15/20 Finish:6/26/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,720 Cost: $6,720 Cost with Overhead+contingency: $9,072

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.3 | review sensors & interlock |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 174 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 6/29/20 Finish:7/10/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,720 Cost: $6,720 Cost with Overhead+contingency: $7,728

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.4 | design electronics safety sysem |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 175 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5.14 weeks Start: 7/13/20 Finish:8/17/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $13,824 Cost: $13,824 Cost with Overhead+contingency: $18,662

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.5 | Cooling interlocks design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 176 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 8/17/20 Finish:9/28/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $20,160 Cost: $20,160 Cost with Overhead+contingency: $27,216

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.6 | Procure Safety system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 177 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 8 weeks Start: 10/1/21 Finish:11/25/21 Fixed Cost: $10,000 Calculated Fixed Cost: $10,000 Resources Cost: $9,069 Cost: $19,069 Cost with Overhead+contingency: $25,743

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.7 | System test at MIT |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 178 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 3 weeks Start: 11/26/21 Finish:12/16/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $19,742 Cost: $19,742 Cost with Overhead+contingency: $26,652

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.8 | Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 179 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 12/17/21 Finish:12/23/22 Fixed Cost: $2000 Calculated Fixed Cost: $2000 Resources Cost: $0 Cost: $200 Cost with Overhead+contingency: $270

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.9 | Test at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 180 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 12/24/21 Finish:1/6/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $22,560 Cost: $22,560 Cost with Overhead+contingency: $30,456

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4 | Service Barrel Support frame & interface to sPHENIX |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 181 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $162,000 Resources Cost: $235,421 Cost: $397,421 Cost with Overhead+contingency: $587,801

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.1 | travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 182 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $20,000 Calculated Fixed Cost: $20,000 Resources Cost: $0 Cost: $20,000 Cost with Overhead+contingency: $22,000

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.2 | Design interface to sPHENIX |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 183 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 125 days Start: 8/19/19 Finish:2/7/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $166,760 Cost: $166,760 Cost with Overhead+contingency: $250,140

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.3 | FEA, Thermal, stress analysis |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 184 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 4/1/19 Finish:4/1/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.4 | Design insersion system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 185 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 weeks Start: 2/10/20 Finish:4/17/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $67,200 Cost: $67,200 Cost with Overhead+contingency: $100,800

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.5 | Procure support structure |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 186 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 8 weeks Start: 2/10/20 Finish:4/3/20 Fixed Cost: $100,000 Calculated Fixed Cost: $100,000 Resources Cost: $629 Cost: $100,629 Cost with Overhead+contingency: $150,944

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.6 | Procure insersion system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 187 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 8 weeks Start: 4/20/20 Finish:6/12/20 Fixed Cost: $40,000 Calculated Fixed Cost: $40,000 Resources Cost: $629 Cost: $40,629 Cost with Overhead+contingency: $60,944

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.7 | Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 188 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0.1 weeks Start: 10/15/20 Finish:10/15/20 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $203 Cost: $2,203 Cost with Overhead+contingency: $2,974

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5 | Half detector assembly Rea |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 189 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 781 days Start: 6/5/19 Finish:6/2/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $54,452 Cost: $54,452 Cost with Overhead+contingency: $73,510

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.1 | Test half barrel #1 |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 190 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 2/1/21 Finish:2/19/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,144 Cost: $6,144 Cost with Overhead+contingency: $8,294

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.2 | Test Barrel #2 |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 191 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 3/1/21 Finish:3/19/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,144 Cost: $6,144 Cost with Overhead+contingency: $8,294

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.3 | Assembly and test cooling system at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 192 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 2/25/22 Finish:3/10/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $15,440 Cost: $15,440 Cost with Overhead+contingency: $20,844

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.4 | Complete system test at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 193 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 3 months Start: 3/11/22 Finish:6/2/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.5 | test RU at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 194 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0.8 weeks Start: 9/21/20 Finish:9/24/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $11,408 Cost: $11,408 Cost with Overhead+contingency: $15,401

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lanl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.6 | test FELIX at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 195 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0.8 weeks Start: 11/12/20 Finish:11/18/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $11,696 Cost: $11,696 Cost with Overhead+contingency: $15,790

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.7 | PS tests at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 196 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0.5 week Start: 6/5/19 Finish:6/10/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $3,620 Cost: $3,620 Cost with Overhead+contingency: $4,887

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6 | Installation and Commissioning |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 197 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 464 days Start: 3/22/21 Finish:12/29/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $126,988 Cost: $126,988 Cost with Overhead+contingency: $160,294

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.1 | Installation preparation |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 198 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 3/22/21 Finish:4/2/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $15,520 Cost: $15,520 Cost with Overhead+contingency: $20,952

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.2 | Installation review |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 199 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 4/5/21 Finish:4/5/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $1,720 Cost: $1,720 Cost with Overhead+contingency: $1,892

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.3 | Install FELIX |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 200 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 days Start: 4/6/21 Finish:4/7/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,168 Cost: $5,168 Cost with Overhead+contingency: $6,977

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.4 | Install Optical fibers |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 201 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 4/8/21 Finish:4/14/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,120 Cost: $8,120 Cost with Overhead+contingency: $10,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.5 | Install RU |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 202 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.5 weeks Start: 4/15/21 Finish:4/26/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,100 Cost: $5,100 Cost with Overhead+contingency: $6,885

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.6 | Install Samtec Cables |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 203 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 4/26/21 Finish:5/3/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,120 Cost: $8,120 Cost with Overhead+contingency: $10,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.7 | Half detector assembly Rea |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 204 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 3 months Start: 5/3/21 Finish:7/26/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.8 | Install Half-Barrel 1 |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 205 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 month Start: 7/1/22 Finish:7/28/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,320 Cost: $26,320 Cost with Overhead+contingency: $35,532

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.9 | Install Half-Barrel 2 |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 206 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 month Start: 7/29/22 Finish:8/25/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,320 Cost: $26,320 Cost with Overhead+contingency: $35,532

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.10 | Commissioning |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 207 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 90 days Start: 8/26/22 Finish: 12/29/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $30,600 Cost: $30,600 Cost with Overhead+contingency: $30,600

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.5 | Ready for the beam |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 208 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 12/29/22 Finish:12/29/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0