MVTX Master Dictionary of WBS

July 26, 2019, v2

This is the MVTX WBS ditionary before we move to P6.

WBS line numbers,  costs and schedules are based on the last pre-P6 MS Project file (06/03/2019 version). There are some changes in the project scope since MVTX is moved into P6.

The latest project Cost & Schedule information is in the P6 now.

This document will be updated after MVTX Cost & Schedule Review.

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MVTX | 7/25/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2 | MVTX Project |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 21 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish: 1/27/23 fixed cost: calculated fixed cost: $1,239,333 Resource cost: $2,365,560 Cost: $3,604,893 Overhead: Cost with Overhead+contingency: $4,781,063

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1 | MVTX Project Management |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 22 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 904 days Start: 4/1/19 Finish: 9/15/22 calculated fixed cost: $50,000 resource cost: $493,050 cost: 543,050 overhead: Cost with Overhead+contingency: $641,660

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.1 | Milestone Start MVTX |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 23 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 4/1/19 Finish: 9/15/22 Cost with Overhead+contingency: 0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.2 | lead Coordinator |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 24 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 3/17/22 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.3 | Project Manager |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 25 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 9/15/22 Resource Cost: $394,478 Cost +Overhead+contingency: $473,374

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.4 | Mechanical Integration Engineer |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 26 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 3/17/22 Resource cost: $98,572 Cost with Overhead+contingency: $118,286

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | Engineer (sPHENIX) |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.5 | Electronics Integration |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 27 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 3/17/22 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.1.6 | Travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 28 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 774 days Start: 4/1/19 Finish: 3/17/22 Calculated Fixed cost: $ 50,000 Cost: $50,000 Cost with Overhead+contingency: $50,000

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2 | Electronics |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 29 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 332 days Start: 4/1/19 Finish: 7/7/20 Calculated Fixed Cost: $319,647 Resources Cost: 112,044 Cost: $ 431,691 Cost with Overhead+contingency: $573,130

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1 | Stave extemsion cable |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 30 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 182 days Start: 4/1/19 Finish:12/10/19 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1.1 | Stave Extension Cable design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 31 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 months Start: 4/1/19 Finish: 7/19/19 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2..1.2 | Stave Extension Cable prototype |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 32 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 months Start: 7/22/19 Finish: 9/13/19 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1.3 | Stabe Extension cable review |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 33 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 days Start: 9/16/19 Finish: 9/17/19 Cost with Overhead+contingency: 0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1.4 | Stabe Extension cable procure |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 34 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 months Start: 9/18/19 Finish: 11/12/19 Cost with Overhead+contingency: 0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.1.5 | Stabe Extension cable test |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 35 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 11/13/19 Finish: 12/10/19 Cost with Overhead+contingency: 0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2 | RU |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 36 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 385 days Start: 4/1/19 Finish: 9/18/20 calculated fix cost: $ 87,108 Resources Cost: $121,434 Cost with Overhead+contingency: $161,904

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.8 | RU: travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 37 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 4/1/19 Finish: 9/18/20 Calcu;ated Fixed Cost: $18,780 Cost: $18,780 Cost with Overhead+contingency: $25,353

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.1 | RU: cold plate |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 38 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 weeks Start: 4/1/19 Finish: 9/26/19 Calculated Fixed Cost: $15,353 Cost: $ 15,353 Cost with Overhead+contingency: $20,727

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.2 | RU: transition board |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 39 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 hours Start: 4/29/19 Finish: 4/30/19 Fixed Cost: $7,935 Resource Cost: $850 Cost: $8,785 Cost with Overhead+contingency: $10,542

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.3 | RU: Power mezzanine |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 40 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/30/19 Finish: 5/14/19 Calculated Fixed Cost: $ 4,757 Cost: $4,757 Cost with Overhead+contingency: $5,708

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.4 | RU: Test/QA |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 41 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 320 hours Start: 7/20/20 Finish: 9/11/20 Fixed Cost: $7,500 Calculated Fixed Cost: $7,500 Resources Cost: $32,554 Cost: $40,054 Cost with Overhead+contingency: $54,072

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.5 | RU: procure 60 SamTec Cables |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 42 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 60 days Start: 4/1/19 Finish: 6/21/19 Fixed Cost: $30,000 Calculated Fixed Cost: $30,000 Resources Cost: $30,922 Cost with Overhead: $41,745

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.6 | RU: Ship to UT Austin from CERN |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 43 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 9/14/20 Finish: 9/19/20 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $0 Cost with Overhead: $2,700

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.2.7 | RU: Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 44 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 9/14/20 Finish: 9/18/20 Fixed Cost: $783 Calculated Fixed Cost: $783 Resources Cost: $0 Cost with Overhead: $1,057

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3 | Felix |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 42 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 161 days Start: 4/1/20 Finish: 11/12/20 Fixed Cost: $0 Calculated Fixed Cost: $76,400 Resources Cost: $17,350 Cost: $93,750 Cost with Overhead: $112,801

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.1 | felix: First production |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 46 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 weeks Start: 4/1/20 Finish: 4/28/20 Fixed Cost: $8,000 Calculated Fixed Cost: $80,000 Resources Cost: $3,152 Cost: $11,152 Cost with Overhead: $13,382

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.2 | FELIX: procure optical fiber |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 47 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/1/20 Finish: 4/14/20 Fixed Cost: $50 Calculated Fixed Cost: $50 Resources Cost: $315 Cost: 365 Cost with Overhead: $438

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.3 | FELIX: Test/QA |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 48 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/15/20 Finish: 4/28/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost with Overhead: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.4 | FELIX: Procure 7 remaining units |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 49 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 8 weeks Start: 8/24/20 Finish: 10/28/20 Fixed Cost: $56,000 Calculated Fixed Cost: $56,000 Resources Cost: $1,280 Cost: 57,280 Cost with Overhead: $68,736

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.5 | FELIX: Procure 57 optical fibers |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 50 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/29/20 Finish: 5/12/20 Fixed Cost: $2,850 Calculated Fixed Cost: $2,850 Resources Cost: $315 Cost: $3,165 Cost with Overhead: $3,798

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.6 | Felix: test/QA |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 51 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5.3 days Start: 10/29/20 Finish: 11/05/20 Fixed Cost: $7,500 Calculated Fixed Cost: $7,500 Resources Cost: $12,2 Cost: $19,788 Cost with Overhead: $23,746

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.3.7 | Felix: Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 52 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 11/5/20 Finish: 11/20/20 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $0 Cost: 2,000 Cost with Overhead: $2,700

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4 | Power System |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 53 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 200 days Start: 4/1/19 Finish: 1/6/20 Fixed Cost: $0 Calculated Fixed Cost: $156,139 Resources Cost: $60,368 Costs: $216,507 Cost with Overhead: $259,808

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1 | MAPS Power Boards |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 54 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 75 days Start: 4/1/19 Finish: 7/12/19 Fixed Cost: $0 Calculated Fixed Cost: $79,020 Resources Cost: $49,672 Costs: $128,692 Cost with Overhead: $154,431

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.1 | Fabricate Breakout Board |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 20 days |  |  |

9. Approved Changes

9. Element Task Description

Duration: 60 days Start: 4/1/19 Finish: 4/26/19 Fixed Cost: $6,600 Calculated Fixed Cost: $6,600 Resources Cost: $0 Costs: 6,600 Cost with Overhead: $7,920

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.2 | Fabicate PB to Stave |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 56 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 60 hours Start: 4/29/19 Finish: 5/8/19 Fixed Cost: $8,000 Calculated Fixed Cost: $8,000 Resources Cost: $7,080 Cost: 15,080 Cost with Overhead: $18,096

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.3 | Fabricate Cooling |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 57 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 4/29/19 Finish: 5/10/19 Fixed Cost: $3,420 Calculated Fixed Cost: $3,420 Resources Cost: $2,112 Cost: 5,532 Cost with Overhead: $6,638

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.4 | Production power boards |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 58 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 40 days Start: 4/29/19 Finish: 6/21/19 Fixed Cost: $60,000 Calculated Fixed Cost: $60,000 Resources Cost: $8,620 Cost: $68,620 Cost with Overhead: $82,345

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2..4.1.5 | Assembly power boards |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 59 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 hours Start: 6/24/19 Finish: 6/19/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $3,540 Cost with Overhead: $4,248

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.6 | Test Power Boards |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 60 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 90 hours Start: 6/27/19 Finish: 7/12/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $10,620 Costs: $10,620 Cost with Overhead: $12,744

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.7 | Power cable Harness |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 61 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 4/29/19 Finish: 5/17/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $14,160 Cost: $14,160 Cost with Overhead: $16,992

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.1.8 | Ship power system to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 62 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 hours Start: 4/1/19 Finish: 4/4/19 Fixed Cost: $1,000 Calculated Fixed Cost: $1,000 Resources Cost: $3,540 Cost: $ 4,540 Cost with Overhead: $5,448

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2 | Power Suppies |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 63 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 200 days Start: 4/1/19 Finish: 1/6/20 Fixed Cost: $0 Calculated Fixed Cost: $77,119 Resources Cost: $10,696 Cost: $87,815 Cost with Overhead: $105,377

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.1 | CAEN A3484 48V PS |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 64 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 200 days Start: 4/1/19 Finish: 1/6/20 Fixed Cost: $8,607 Calculated Fixed Cost: $8,607 Resources Cost: $0 Cost: 8,607 Cost with Overhead: $10,328

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.2 | CAEN SY4527 Main Frame |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 65 |  |  |

9. Approved Changes

| 9. Element Task Description |  |  |
| --- | --- | --- |
| Duration: 30 days Start: 4/1/19 Finish: 5/10/19 Fixed Cost: $11,620 Calculated Fixed Cost: $11,620 Resources Cost: $0 Cost: 11,620 Cost with Overhead: $13,944 |  |  |
| 1. Project Title: | 2. Date: | 3: Person Responsible |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.3 | CAEN A4532 Power board |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 66 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 5/13/19 Finish: 5/17/19 Fixed Cost: $1,216 Calculated Fixed Cost: $1,216 Resources Cost: $0 Cost: 1,216 Cost with Overhead+contingency: $1,459

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.4 | CAEN A2518 Power module |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 67 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.3 days Start: 5/20/19 Finish: 5/21/19 Fixed Cost: $43,676 Calculated Fixed Cost: $43,676 Resources Cost: $0 Cost: $43,676 Cost with Overhead+contingency: $52,411

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.5 | Cabling |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 68 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 5/21/19 Finish: 5/28/19 Fixed Cost: $10,000 Calculated Fixed Cost: $10,000 Resources Cost: $4,720 Cost: $14,720 Cost with Overhead+contingency: $17,664

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.6 | test PB with PS |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 69 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 5/28/19 Finish: 6/4/19 Fixed Cost: $1,216 Calculated Fixed Cost: $0 Resources Cost: $4,720 Cost: $4,720 Cost with Overhead+contingency: $5,664

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.2.4.2.7 | Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 70 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.3 days Start: 6/4/19 Finish: 6/5/19 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $1,256 Cost: $3,256 Cost with Overhead+contingency: $3,907

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3 | Mechanics and Detector Assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 71 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 100 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $535,486 Resources Cost: $1,202,571 Cost: $1,738,057 Cost with Overhead+contingency: $2,361,763

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1 | Staves |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 72 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 345 days Start: 4/1/19 Finish:7/24/20 Fixed Cost: $0 Calculated Fixed Cost: $146,852 Resources Cost: $124,034 Cost: $270,886 Cost with Overhead+contingency: $365,131

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1 | Stave production |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 73 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 267 days Start: 4/1/19 Finish:4/7/20 Fixed Cost: $0 Calculated Fixed Cost: $57,360 Resources Cost: $72 Cost: $57,432 Cost with Overhead+contingency: $77,534

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1.1 | Staves test and QA at cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 74 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 160 days Start: 7/31/19 Finish: 3/10/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1.2 | CERN test system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 75 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 4/1/19 Finish:4/1/19 Fixed Cost: $7,360 Calculated Fixed Cost: $7,360 Resources Cost: $72 Cost: $72,432 Cost with Overhead+contingency: $10,034

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1.3 | travel and per diem at cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 76 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 5/20/19 Finish:5/20/19 Fixed Cost: $50,000 Calculated Fixed Cost: $50,000 Resources Cost: $0 Cost: $50,000 Cost with Overhead+contingency: $67,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.1.4 | Test and QA at cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 77 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 180 days Start: 7/31/19 Finish:4/7/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.2 | Stave assembly tooling |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 78 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 120 days Start: 2/10/20 Finish:7/24/20 Fixed Cost: $0 Calculated Fixed Cost: $25,000 Resources Cost: $44,352 Cost: $69,352 Cost with Overhead+contingency: $93,625

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.2.1 | stave tooling design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 79 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 weeks Start: 2/10/20 Finish:3/6/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $13,440 Cost: $13,440 Cost with Overhead+contingency: $18,144

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.2.2 | stave tooling final jig design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 80 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 40 days Start: 3/9/20 Finish:5/1/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,880 Cost: $26,880 Cost with Overhead+contingency: $36,288

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.2.3 | procure assembly fixtures |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 81 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 60 days Start: 5/4/20 Finish:7/24/20 Fixed Cost: $25,000 Calculated Fixed Cost: $25,000 Resources Cost: $4,032 Cost: $29,032 Cost with Overhead+contingency: $39,193

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3 | Metrology |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 82 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 105 days Start: 2/10/20 Finish:7/3/20 Fixed Cost: $0 Calculated Fixed Cost: $7,000 Resources Cost: $58,007 Cost: $65,007 Cost with Overhead+contingency: $87,759

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3.1 | Metrology design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 83 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 months Start: 2/10/20 Finish:4/3/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,880 Cost: $26,880 Cost with Overhead+contingency: $36,288

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3.2 | design jigs |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 84 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 40 days Start: 4/6/20 Finish:5/29/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,880 Cost: $26,880 Cost with Overhead+contingency: $36,288

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3.3 | procure jigs |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 85 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 weeks Start: 6/1/20 Finish:6/26/20 Fixed Cost: $5,000 Calculated Fixed Cost: $5,000 Resources Cost: $315 Cost: $5,315 Cost with Overhead+contingency: $7,175

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.3.4 | ship to lbnl |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 86 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 6/29/20 Finish:7/3/20 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $3,932 Cost: $5,932 Cost with Overhead+contingency: $8,008

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4 | Shipping and storage components |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 87 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 227 days Start: 4/1/19 Finish:2/11/20 Fixed Cost: $0 Calculated Fixed Cost: $33,492 Resources Cost: $21,603 Cost: $55,095 Cost with Overhead+contingency: $73,814

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.1 | Design&fabricate storage |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 88 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 39 days Start: 4/1/19 Finish:5/23/19 Fixed Cost: $6,992 Calculated Fixed Cost: $6,992 Resources Cost: $5,355 Cost: $12,347 Cost with Overhead+contingency: $16,668

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.2 | design&fabricate shipment |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 89 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 50 days Start: 12/4/19 Finish:2/11/20 Fixed Cost: $11,500 Calculated Fixed Cost: $11,500 Resources Cost: $5,480 Cost: $16,980 Cost with Overhead+contingency: $22,923

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.3 | design shipping container |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 90 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 5/20/19 Finish:5/24/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $9,480 Cost: $9,480 Cost with Overhead+contingency: $12,798

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.4 | procure stave shipping |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 91 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 4/1/19 Finish:4/1/19 Fixed Cost: $10,000 Calculated Fixed Cost: $10,000 Resources Cost: $1,288 Cost: $11,288 Cost with Overhead+contingency: $14,674

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.4.5 | Ship to cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 92 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 months Start: 4/2/19 Finish:5/27/19 Fixed Cost: $5,000 Calculated Fixed Cost: $5,000 Resources Cost: $0 Cost: $5,000 Cost with Overhead+contingency: $6,750

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5 | shipping staves to bnl |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 93 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 202 days Start: 7/31/19 Finish:5/7/20 Fixed Cost: $0 Calculated Fixed Cost: $24,000 Resources Cost: $0 Cost: $24,000 Cost with Overhead+contingency: $32,400

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5.1 | shipping staves from cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 94 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 7 days Start: 7/31/19 Finish:8/8/19 Fixed Cost: $6,000 Calculated Fixed Cost: $6,000 Resources Cost: $0 Cost: $6,000 Cost with Overhead+contingency: $8,100

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5.2 | shipping staves from cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 95 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 7 days Start: 10/30/19 Finish:11/7/19 Fixed Cost: $6,000 Calculated Fixed Cost: $6,000 Resources Cost: $0 Cost: $6,000 Cost with Overhead+contingency: $8,100

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5.3 | shipping staves from cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 96 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 7 days Start: 4/1/20 Finish:2/6/20 Fixed Cost: $6,000 Calculated Fixed Cost: $6,000 Resources Cost: $0 Cost: $6,000 Cost with Overhead+contingency: $8,100

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.1.5.4 | shipping staves from cern |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 97 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 7 days Start: 4/29/20 Finish:5/7/20 Fixed Cost: $6,000 Calculated Fixed Cost: $6,000 Resources Cost: $0 Cost: $6,000 Cost with Overhead+contingency: $8,100

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2 | carbon structures |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 98 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $359,820 Resources Cost: $867,641 Cost: $1,227,461 Cost with Overhead+contingency: $1,670,999

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.1 | Mechanics detector design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 99 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 100 days Start: 4/1/19 Finish:8/16/19 Fixed Cost: $0 Calculated Fixed Cost: $2,000 Resources Cost: $0 Cost: $389,026 Cost with Overhead+contingency: $525,185

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lanl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.1.1 | develop maps inner |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 100 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 4 months Start: 4/1/19 Finish:7/19/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $195,507 Cost: $195,507 Cost with Overhead+contingency: $263,935

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.1.2 | mechanical model MIT |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 101 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 months Start: 4/1/19 Finish:8/16/19 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $191,519 Cost: $193,519 Cost with Overhead+contingency: $261,251

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3 | Mechanics Fabrication |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 102 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $337,000 Resources Cost: $451,175 Cost: $788,995 Cost with Overhead+contingency: $1,091,429

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.1 | Travel LBNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 103 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $70,000 Calculated Fixed Cost: $70,000 Resources Cost: $0 Cost: $70,000 Cost with Overhead+contingency: $94,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4 | End wheels |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 104 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 145 days Start: 8/19/19 Finish:3/6/20 Fixed Cost: $0 Calculated Fixed Cost: $75,940 Resources Cost: $219,272 Cost: $295,212 Cost with Overhead+contingency: $428,057

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.8 | tooling Design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 105 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.75 months Start: 8/19/19 Finish:10/4/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $33,340 Cost: $33,340 Cost with Overhead+contingency: $48,343

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.9 | tooling material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 106 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 10/7/19 Finish:11/15/19 Fixed Cost: $60,000 Calculated Fixed Cost: $60,000 Resources Cost: $1,644 Cost: $61,644 Cost with Overhead+contingency: $89,384

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.10 | Tooling assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 107 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 107 days Start: 11/18/19 Finish:12/27/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $32,880 Cost: $32,880 Cost with Overhead+contingency: $47,676

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.11 | Material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 108 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 days Start: 12/30/19 Finish:12/31/19 Fixed Cost: $15,940 Calculated Fixed Cost: $15,940 Resources Cost: $3,952 Cost: $19,892 Cost with Overhead+contingency: $28,843

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.12 | Production and test |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 109 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 48 days Start: 1/1/20 Finish:3/6/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $147,456 Cost: $147,456 Cost with Overhead+contingency: $213,811

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2 | CYSS Cylindrical STructure |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 110 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 98 days Start: 8/19/19 Finish:1/1/20 Fixed Cost: $0 Calculated Fixed Cost: $75,940 Resources Cost: $104,073 Cost: $180,013 Cost with Overhead+contingency: $261,018

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.8 | Tooling design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 111 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.2 months Start: 8/19/19 Finish:9/19/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $22,752 Cost: $22,752 Cost with Overhead+contingency: $32,990

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.2 | tooling material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 112 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 9/20/19 Finish:10/10/19 Fixed Cost: $30,000 Calculated Fixed Cost: $30,000 Resources Cost: $0 Cost: $30,000 Cost with Overhead+contingency: $43,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.3 | Tooling iteration |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 113 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 10/11/19 Finish:10/31/19 Fixed Cost: $30,000 Calculated Fixed Cost: $30,000 Resources Cost: $0 Cost: $30,000 Cost with Overhead+contingency: $43,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.4 | Procure CYSS Material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 114 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 11/1/19 Finish:11/7/19 Fixed Cost: $15,940 Calculated Fixed Cost: $15,940 Resources Cost: $0 Cost: $15,940 Cost with Overhead+contingency: $23,113

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.5 | Tooling assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 115 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 11/8/19 Finish:11/28/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $16,440 Cost: $16,440 Cost with Overhead+contingency: $23,838

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.6 | Production & test CYSS |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 116 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 24 days Start: 11/29/19 Finish:1/1/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $64,881 Cost: $64,881 Cost with Overhead+contingency: $94,077

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.2.7 | Milestone complete |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 117 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 1/1/20 Finish:1/1/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3 | Service Barrel (SB) |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 118 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 80 days Start: 10/11/19 Finish:1/30/20 Fixed Cost: $0 Calculated Fixed Cost: $115,940 Resources Cost: $127,831 Cost: $243,771 Cost with Overhead+contingency: $307,854

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.1 | review SB design-fabrication |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 119 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 40 days Start: 10/11/19 Finish:12/5/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $12,646 Cost: $12,646 Cost with Overhead+contingency: $16,440

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.2 | hold SB Review |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 120 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 10/11/19 Finish:10/31/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $12,581 Cost: $12,581 Cost with Overhead+contingency: $16,355

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.3 | Tooling |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 121 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 11/1/19 Finish:11/28/19 Fixed Cost: $40,000 Calculated Fixed Cost: $40,000 Resources Cost: $50,480 Cost: $90,480 Cost with Overhead+contingency: $108,576

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.4 | Procure SB Material |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 122 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 11/29/19 Finish:12/5/19 Fixed Cost: $75,940 Calculated Fixed Cost: $75,940 Resources Cost: $0 Cost: $75,940 Cost with Overhead+contingency: $98,722

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.5 | Production & Test SE |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 123 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 21 days Start: 1/2/20 Finish:1/30/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $52,123 Cost: $52,123 Cost with Overhead+contingency: $67,760

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.3.6 | Milestone Complete |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 124 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 1/30/20 Finish:1/30/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.4 | MVTX Final Design Review |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 125 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 23 days Start: 11/1/19 Finish:12/3/19 Fixed Cost: $0 Calculated Fixed Cost: $20,000 Resources Cost: $29,440 Cost: $49,440 Cost with Overhead+contingency: $54,384

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.4.1 | MVTX Design Review LBNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 126 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 days Start: 11/1/19 Finish:11/4/19 Fixed Cost: $10,000 Calculated Fixed Cost: $10,000 Resources Cost: $1,976 Cost: $11,976 Cost with Overhead+contingency: $13,174

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.4.2 | Incorporate review comments |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 128 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 9 days Start: 11/7/19 Finish:11/19/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,892 Cost: $8,892 Cost with Overhead+contingency: $9,781

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lanl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.4.5 | Incorporate review comments |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 129 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 9 days Start: 11/20/19 Finish:12/2/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $11,304 Cost: $11,304 Cost with Overhead+contingency: $12,434

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.3 | Complete final design LBNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 130 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 12/3/19 Finish:12/3/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $988 Cost: $988 Cost with Overhead+contingency: $1,087

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lanl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.2.3.4.6 | Complete final design LANL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 131 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 12/3/19 Finish:12/3/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $1,256 Cost: $1,256 Cost with Overhead+contingency: $1,382

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3 | Barrel Assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 132 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 406 days Start: 8/9/19 Finish:2/26/20 Fixed Cost: $0 Calculated Fixed Cost: $28,814 Resources Cost: $210,896 Cost: $239,710 Cost with Overhead+contingency: $325,633

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1 | Barrel assembly and testing |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 133 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 406 days Start: 8/9/19 Finish:2/26/21 Fixed Cost: $0 Calculated Fixed Cost: $28,814 Resources Cost: $210,896 Cost: $239,710 Cost with Overhead+contingency: $325,633

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.1 | Receive 1st batch stave |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 134 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 8/9/19 Finish:8/9/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.2 | Test and rework 1st batch |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 135 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 12 days Start: 8/12/19 Finish:8/27/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,240 Cost: $5,240 Cost with Overhead+contingency: $6,812

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.3 | Receive 2nd batch stave |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 136 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 11/8/19 Finish:11/8/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.4 | Test and Rework 2nd batch |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 137 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 12 days Start: 11/11/19 Finish:11/26/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,449 Cost: $5,449 Cost with Overhead+contingency: $7,084

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.5 | Receive 3rd batch staves |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 138 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 2/7/20 Finish:2/7/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.6 | Test and review 3rd batch |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 139 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 512days Start: 2/10/20 Finish:2/25/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,449 Cost: $5,449 Cost with Overhead+contingency: $7,084

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.7 | Receive 4th batch staves |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 140 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 5/8/20 Finish:5/8/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.8 | Test and rework 4th batch |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 141 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 12 days Start: 5/11/20 Finish:5/26/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,449 Cost: $5,449 Cost with Overhead+contingency: $7,084

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9 | layer assembly and test |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 142 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 140 days Start: 3/9/20 Finish:9/18/20 Fixed Cost: $0 Calculated Fixed Cost: $5,336 Resources Cost: $68,670 Cost: $74,006 Cost with Overhead+contingency: $101,329

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.1 | test installation of staves |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 143 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 3/9/20 Finish:4/3/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $7,056 Cost: $7,056 Cost with Overhead+contingency: $9,526

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.2 | Hold half-detector assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 144 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 4/6/20 Finish:4/10/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $2,672 Cost: $2,672 Cost with Overhead+contingency: $3,206

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.3 | Install staves onto layers |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 145 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 70 days Start: 4/13/20 Finish:7/17/20 Fixed Cost: $2,760 Calculated Fixed Cost: $2,760 Resources Cost: $33,656 Cost: $36,416 Cost with Overhead+contingency: $50,982

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.4 | Test and rework layer |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 146 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 7/20/20 Finish:8/28/20 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $14,278 Cost: $16,854 Cost with Overhead+contingency: $22,752

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.5 | Perform Half-Detector |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 147 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 8/31/20 Finish:9/18/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $11,009 Cost: $11,009 Cost with Overhead+contingency: $14,862

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.9.6 | Milestone Complete |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 148 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 9/18/20 Finish:9/18/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10 | Half barrel #1 assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 149 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 95 days Start: 9/21/20 Finish:1/29/21 Fixed Cost: $0 Calculated Fixed Cost: $11,739 Resources Cost: $60,206 Cost: $71,945 Cost with Overhead+contingency: $97,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.1 | Assemble Layers and barrel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 150 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 9/21/20 Finish:10/16/20 Fixed Cost: $2,760 Calculated Fixed Cost: $2,760 Resources Cost: $13,965 Cost: $16,725 Cost with Overhead+contingency: $23,415

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.2 | Test and rework half barrel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 151 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 10/19/20 Finish:11/27/20 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $19,200 Cost: $21,776 Cost with Overhead+contingency: $29,398

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.3 | Perform Half-detector |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 152 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 11/30/20 Finish:12/11/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,120 Cost: $8,120 Cost with Overhead+contingency: $10,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.4 | Validation of final assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 153 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 12149/20 Finish:1/8/21 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $13,976 Cost: $16,552 Cost with Overhead+contingency: $22,345

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.10.5 | Pack/Ship Final Assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 154 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 1/11/21 Finish:1/29/21 Fixed Cost: $3,827 Calculated Fixed Cost: $3,827 Resources Cost: $4,945 Cost: $8,772 Cost with Overhead+contingency: $11,843

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11 | Half barrel #2 assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 155 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 95 days Start: 10/19/20 Finish:2/26/21 Fixed Cost: $0 Calculated Fixed Cost: $11,739 Resources Cost: $60,433 Cost: $72,172 Cost with Overhead+contingency: $98,280

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.1 | Assemble Layers and barrel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 156 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 10/19/20 Finish:11/13/20 Fixed Cost: $2,760 Calculated Fixed Cost: $2,760 Resources Cost: $14,192 Cost: $16,952 Cost with Overhead+contingency: $23,733

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.2 | Test and rework half barrel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 157 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 11/16/20 Finish:12/25/20 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $19,200 Cost: $21,776 Cost with Overhead+contingency: $29,398

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.3 | Perform Half-detector |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 158 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 12/28/20 Finish:1/8/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,120 Cost: $8,120 Cost with Overhead+contingency: $10,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.4 | Validation of final assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 159 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 20 days Start: 1/11/21 Finish:2/5/21 Fixed Cost: $2,576 Calculated Fixed Cost: $2,576 Resources Cost: $13,976 Cost: $16,552 Cost with Overhead+contingency: $22,345

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.5 | Pack/Ship Final Assembly |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 160 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 2/8/21 Finish:2/26/21 Fixed Cost: $3,827 Calculated Fixed Cost: $3,827 Resources Cost: $4,945 Cost: $8,772 Cost with Overhead+contingency: $11,843

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.3.3.1.11.6 | Milestone Complete |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 161 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 2/26/21 Finish:2/26/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4 | Integration and Infrastructure |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 162 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $334,200 Resources Cost: $557,895 Cost: $892,095 Cost with Overhead+contingency: $1,243,127

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.1 | Clean Tent/room |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 163 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 100 days Start: 10/1/19 Finish:2/17/20 Fixed Cost: $50,000 Calculated Fixed Cost: $50,000 Resources Cost: $0 Cost: $50,000 Cost with Overhead+contingency: $67,500

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2 | Cooling system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 164 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $87,000 Resources Cost: $42,239 Cost: $129,239 Cost with Overhead+contingency: $174,472

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.1 | travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 165 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $25,000 Calculated Fixed Cost: $25,000 Resources Cost: $0 Cost: $25,000 Cost with Overhead+contingency: $33,750

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.2 | design(modify ALICE) |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 166 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 month Start: 4/20/20 Finish:5/15/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $21,304 Cost: $21,304 Cost with Overhead+contingency: $28,760

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.3 | Mockup testing |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 167 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 3 weeks Start: 5/18/20 Finish:6/5/20 Fixed Cost: $20,000 Calculated Fixed Cost: $20,000 Resources Cost: $12,551 Cost: $32,551 Cost with Overhead+contingency: $43,944

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.4 | Final Design of Cooling system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 168 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5 days Start: 6/8/20 Finish:6/12/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,720 Cost: $6,720 Cost with Overhead+contingency: $9,072

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.5 | Procure cooling plant |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 169 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 100 days Start: 10/1/21 Finish:2/17/22 Fixed Cost: $40,000 Calculated Fixed Cost: $40,000 Resources Cost: $1,664 Cost: $41,664 Cost with Overhead+contingency: $56,246

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.2.6 | Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 170 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 2/18/22 Finish:2/24/22 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $0 Cost: $2,000 Cost with Overhead+contingency: $2,700

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3 | Safety system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 171 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 724 days Start: 4/1/19 Finish:1/6/22 Fixed Cost: $0 Calculated Fixed Cost: $35,200 Resources Cost: $98,795 Cost: $133,995 Cost with Overhead+contingency: $179,550

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.1 | travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 172 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 700 days Start: 4/1/19 Finish:12/3/21 Fixed Cost: $25,000 Calculated Fixed Cost: $25,000 Resources Cost: $0 Cost: $25,000 Cost with Overhead+contingency: $33,750

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.2 | Define MVTX Safety andInterlock system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 173 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 6/15/20 Finish:6/26/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,720 Cost: $6,720 Cost with Overhead+contingency: $9,072

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.3 | review sensors & interlock |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 174 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 6/29/20 Finish:7/10/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,720 Cost: $6,720 Cost with Overhead+contingency: $7,728

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.4 | design electronics safety sysem |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 175 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 5.14 weeks Start: 7/13/20 Finish:8/17/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $13,824 Cost: $13,824 Cost with Overhead+contingency: $18,662

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.5 | Cooling interlocks design |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 176 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 30 days Start: 8/17/20 Finish:9/28/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $20,160 Cost: $20,160 Cost with Overhead+contingency: $27,216

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.6 | Procure Safety system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 177 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 8 weeks Start: 10/1/21 Finish:11/25/21 Fixed Cost: $10,000 Calculated Fixed Cost: $10,000 Resources Cost: $9,069 Cost: $19,069 Cost with Overhead+contingency: $25,743

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.7 | System test at MIT |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 178 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 3 weeks Start: 11/26/21 Finish:12/16/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $19,742 Cost: $19,742 Cost with Overhead+contingency: $26,652

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.8 | Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 179 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 12/17/21 Finish:12/23/22 Fixed Cost: $2000 Calculated Fixed Cost: $2000 Resources Cost: $0 Cost: $200 Cost with Overhead+contingency: $270

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.3.9 | Test at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 180 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 weeks Start: 12/24/21 Finish:1/6/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $22,560 Cost: $22,560 Cost with Overhead+contingency: $30,456

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4 | Service Barrel Support frame & interface to sPHENIX |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 181 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $0 Calculated Fixed Cost: $162,000 Resources Cost: $235,421 Cost: $397,421 Cost with Overhead+contingency: $587,801

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.1 | travel |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 182 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1000 days Start: 4/1/19 Finish:1/27/23 Fixed Cost: $20,000 Calculated Fixed Cost: $20,000 Resources Cost: $0 Cost: $20,000 Cost with Overhead+contingency: $22,000

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.2 | Design interface to sPHENIX |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 183 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 125 days Start: 8/19/19 Finish:2/7/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $166,760 Cost: $166,760 Cost with Overhead+contingency: $250,140

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.3 | FEA, Thermal, stress analysis |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 184 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 4/1/19 Finish:4/1/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.4 | Design insersion system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 185 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 weeks Start: 2/10/20 Finish:4/17/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $67,200 Cost: $67,200 Cost with Overhead+contingency: $100,800

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.5 | Procure support structure |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 186 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 8 weeks Start: 2/10/20 Finish:4/3/20 Fixed Cost: $100,000 Calculated Fixed Cost: $100,000 Resources Cost: $629 Cost: $100,629 Cost with Overhead+contingency: $150,944

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.6 | Procure insersion system |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 187 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 8 weeks Start: 4/20/20 Finish:6/12/20 Fixed Cost: $40,000 Calculated Fixed Cost: $40,000 Resources Cost: $629 Cost: $40,629 Cost with Overhead+contingency: $60,944

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.4.7 | Ship to BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 188 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0.1 weeks Start: 10/15/20 Finish:10/15/20 Fixed Cost: $2,000 Calculated Fixed Cost: $2,000 Resources Cost: $203 Cost: $2,203 Cost with Overhead+contingency: $2,974

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5 | Half detector assembly Rea |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 189 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 781 days Start: 6/5/19 Finish:6/2/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $54,452 Cost: $54,452 Cost with Overhead+contingency: $73,510

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.1 | Test half barrel #1 |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 190 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 2/1/21 Finish:2/19/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,144 Cost: $6,144 Cost with Overhead+contingency: $8,294

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.2 | Test Barrel #2 |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 191 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 15 days Start: 3/1/21 Finish:3/19/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $6,144 Cost: $6,144 Cost with Overhead+contingency: $8,294

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.3 | Assembly and test cooling system at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 192 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 2/25/22 Finish:3/10/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $15,440 Cost: $15,440 Cost with Overhead+contingency: $20,844

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.4 | Complete system test at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 193 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 3 months Start: 3/11/22 Finish:6/2/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.5 | test RU at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 194 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0.8 weeks Start: 9/21/20 Finish:9/24/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $11,408 Cost: $11,408 Cost with Overhead+contingency: $15,401

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lanl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.6 | test FELIX at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 195 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0.8 weeks Start: 11/12/20 Finish:11/18/20 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $11,696 Cost: $11,696 Cost with Overhead+contingency: $15,790

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | lbnl |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.5.7 | PS tests at BNL |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 196 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0.5 week Start: 6/5/19 Finish:6/10/19 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $3,620 Cost: $3,620 Cost with Overhead+contingency: $4,887

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6 | Installation and Commissioning |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 197 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 464 days Start: 3/22/21 Finish:12/29/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $126,988 Cost: $126,988 Cost with Overhead+contingency: $160,294

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.1 | Installation preparation |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 198 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 10 days Start: 3/22/21 Finish:4/2/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $15,520 Cost: $15,520 Cost with Overhead+contingency: $20,952

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | MIT |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.2 | Installation review |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 199 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 day Start: 4/5/21 Finish:4/5/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $1,720 Cost: $1,720 Cost with Overhead+contingency: $1,892

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.3 | Install FELIX |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 200 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 2 days Start: 4/6/21 Finish:4/7/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,168 Cost: $5,168 Cost with Overhead+contingency: $6,977

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.4 | Install Optical fibers |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 201 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 4/8/21 Finish:4/14/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,120 Cost: $8,120 Cost with Overhead+contingency: $10,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | UTA |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.5 | Install RU |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 202 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1.5 weeks Start: 4/15/21 Finish:4/26/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $5,100 Cost: $5,100 Cost with Overhead+contingency: $6,885

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.6 | Install Samtec Cables |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 203 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 week Start: 4/26/21 Finish:5/3/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $8,120 Cost: $8,120 Cost with Overhead+contingency: $10,962

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LANL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.7 | Half detector assembly Rea |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 204 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 3 months Start: 5/3/21 Finish:7/26/21 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.8 | Install Half-Barrel 1 |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 205 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 month Start: 7/1/22 Finish:7/28/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,320 Cost: $26,320 Cost with Overhead+contingency: $35,532

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 | LBNL |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.9 | Install Half-Barrel 2 |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 206 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 1 month Start: 7/29/22 Finish:8/25/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $26,320 Cost: $26,320 Cost with Overhead+contingency: $35,532

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.4.6.10 | Commissioning |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 207 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 90 days Start: 8/26/22 Finish: 12/29/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $30,600 Cost: $30,600 Cost with Overhead+contingency: $30,600

| 1. Project Title: | 2. Date: | 3: Person Responsible |
| --- | --- | --- |
| SPHENIX MAPS | 6/3/19 |  |

| 4. WBS Element Code | 5. WBS Element Title |
| --- | --- |
| 3.2.5 | Ready for the beam |

| 6. Index Line Number: | 7. Revision Number and Authorization: | 8: Rev. Date |
| --- | --- | --- |
| 208 |  |  |

9. Approved Changes

9. Element Task Description

Duration: 0 days Start: 12/29/22 Finish:12/29/22 Fixed Cost: $0 Calculated Fixed Cost: $0 Resources Cost: $0 Cost: $0 Cost with Overhead+contingency: $0