MVTX Basis of Estimate Document (BoE)

04/02/2019 v1

07/25/2019 v2 synced to P6

Introduction

The MVTX upgrade project for sPHENIX relies on the fact that much of the conceptual design, prototype design, and prototyping  has/will be done by the ALICE ITS Upgrade Group at CERN and through a Los Alamos National Laboratory LDRD(Laboratory Directed research and Development) development effort.  The cost and schedule of the DOE/BNL support consists of final design efforts, procurement, assembly and installation.  Presented here are the effort for the DOE/BNL portion.  The complete cost and schedule file including the ALICE/ITS and LDRD effort is found in the MVTX project file (also in P6).  The total project cost is $3.7M and after contingency is applied $4.9M.  Finish date is the 1st Qtr of FY2024.

The mechanical design of the MVTX detector will be a “replication” of the ALICE design but since the MVTX detector will sit inside the Intermediate Tracker which is not yet fully designed we have included a 40% contingency to cover a possible modification. Mechanical Integration into sPHENIX requires a clear definition of the surrounding systems. Unfortunately, because the inner volume is still in a state of flux, we have looked at the global support structure for the TPC as an estimate for our needs but with a large contingency. Contingency is risked based and varies between 30% and 40%.

84 Staves and 60 Readout Units (RU) will be procured directly from CERN through US-ALICE with a fixed cost of $1.36M, and are not included in this document (off-project).

MVTX Project Scope - WBS

MVTX upgrade project major cost items

Below we list major cost items and the basis of estimate for the MVTX upgrade project.

WBS Number: 3.02.02.01  Frontend Electronics - RU Services

Technical scope:

This item contains all the services required for the operation of MVTX readout unit.

Work statement:

Produce the identical ALICE/ITS RU cold plates, mezzanine boards and SamTec data cables in the US for 60 RU mother boards to be provided by BNL purchased from ALICE ITS upgrade project.

Assumptions used in developing estimate:

We will use the identical RU service components for the MVTX frontend readout system. All the costs are based on the actual ALICE ITS production cost or quotes from fabrication houses used for the ALICE project. The cost of the MVTX custom SamTec cables are based on the actual cost from LANL R&D purchase of less quantity of 10, scaled up to MVTX quantity of 60.

Cost Summary: (Burd. AY$)

| Total (K) | M&S | Labor | Contingency (average) |
| --- | --- | --- | --- |
| 213 | 84 | 129 | 25% |

Quotes of M&S items

| Major Items | Cost (Quote), $K |
| --- | --- |
| Cold Plates | 15.4 |
| RU Transition Boards | 7.9 |
| RU Power Mezzanine Cards | 4.7 |
| SamTec Cables | 30 |

Cold plates, Transition baords and Power Mezz. are based on quotes from UT-A in 2019;

SamTec cables are based on the actual cost of LANL R&D 8m long cables, $1k/per-pair for quantity of 10 readout cables. Scaled up to 60 cables (30 pairs of readout cables), total of $30K.

Figure 1 Quote from UT-A on RU Cold plates, and transition and power mezz. boards.

WBS Number: 3.02.02.02  Backend Electronics - FELIX 2.0

Technical scope:

This item contains all the backend readout electronics FELIX boards and associated optical fiber and patch panel systems required for MVTX readout.

Work statement:

Produce 8 FELIX boards to integrate MVTX readout electronics into the sPHENIX DAQ system. And procure optical fibers and patch panel boxes for 8 FELIX units.

Assumptions used in developing estimate:

We will use the ATLAS FELIX v2.0 PCIe board developed by the BNL group for the ATLAS upgrade. The FELIX board production quote for sPHENIX was obtained in 2018, under $8K per board for sPHENIX TPC production.  A total of 8 FELIX boards ( 6 + 2 spares) are required for MVTX. Cos of the optical fibers and patch panel boxes are based on the actual cost occurred to LANL MVTX readout R&D project.

Cost Summary: (Burd. AY$)

| Total (K) | M&S | Labor | Contingency (average) |
| --- | --- | --- | --- |
| 110.6 | 90.0 | 20.5 | 25% |

Figure 2. FELIX v2.0 production cost shown in the sPHENIX PD2/3 for TPC DAM production, as well as optical fibers, patch panels. For 20 FELIX v2.0, total direct cost is $130K, or $6.5K per FELIX board.

WBS Number: 3.02.02.03.01  MVTX Power Unit Boards

Technical scope:

This item contains all power control and modules required for MVTX staves and electronics.

Work statement:

Produce 30 ALICE/ITS power distribution units (24 + 6 spares) for staves.

Assumptions used in developing estimate:

We will use the identical ALICE/ITS power distribution units (PU) for MVTX operation. The production cost is estimated (from ALICE production) $2500 per board for a production of 30 boards in US; and also the cooling plates for each PU board.

Cost Summary: (Burd. AY$)

| Total (K) | M&S | Labor | Contingency (average) |
| --- | --- | --- | --- |
| 246.0 | 184.4 | 61.6 | 25% |

WBS Number: 3.02.02.03.02  MVTX CAEN Power System

Technical scope:

This item contains all power control and modules required for MVTX staves and electronics.

Work statement:

Produce CAEN power supply modules.

Assumptions used in developing estimate:

For the CAEN off the shelf power supply controller and modules, we have obtained a very similar/identical modules (less quantities) and controllers from CAEN for LANL R&D in 2018. LBNL received very similar quotes from CAEN this year.

Cost Summary: (Burd. AY$)

| Total (K) | M&S | Labor | Contingency (average) |
| --- | --- | --- | --- |
| 315 | 90.7 | 11 | 25% |

Identical/similar CAEN powered system and modules purchased by LANL for R&D.

The MVTX PS system cost is based on the scaled up numbers.

WBS Number: 3.02.03  Mechanics and Detector Assembly

Technical scope:

This item contains all the mechanical supporting structures required to integrate and operate the MVTX detector in the sPHENIX system.

Work statement:

Design and produce mechanical supporting structures to integrate the MVTX detectors into the sPHENIX system, including MVTX detector design, fabrication and assembly, MVTX detector services, low mass carbon structures.

Assumptions used in developing estimate:

We will use the modified staves and carbon supporting structures based on the ALICE/ITS Inner Barrel design. The amount of design work and carbon structure production cost are based on ALICE/ITS upgrade work and also our previous experience with similar detectors, including the recent STAR HFT and PHENIX FVTX silicon detector upgrades at BNL.

Cost Summary: (Burd. AY$)

| Total $ (K) | M&S | Labor | Contingency (average) |
| --- | --- | --- | --- |
| 1701 | 679 | 1022 | 40% |

Since the carbon structure production is one of the major high cost items, we have obtained preliminary quotes on both CYSS and the 3rd layer of End Wheels for the ALICE ITS IB design. The preliminary quotes are comparable to the estimates from LBNL. For the current project planning purpose, we use the estimated numbers from LBNL.

WBS Number: 3.02.04  Integration and Infrastructure

Technical scope:

This item contains all the MVTX detector system integration into the sPHENIX experiment.

Work statement:

Design and produce MVTX mechanical supporting structures to interface the sPHENIX global supporting frame; design and build MVTX detector safety system; install and commission the MVTX detector in the sPHENIX IR.

Assumptions used in developing estimate:

We will use the modified cooling and mechanical supporting structures based on the ALICE/ITS Inner Barrel design. The amount of design work and mechanical structure production cost are based on ALICE/ITS upgrade work and also our previous experience with similar detectors, including the recent STAR HFT and PHENIX FVTX silicon detector upgrades at BNL.

Cost Summary:

| Total $ (K) | M&S | Labor | Contingency (average) |
| --- | --- | --- | --- |
| 873.3 | 416.5 | 456.8 | 40% |