## Sheet1
WBS | BNL_WBS_Hierarchical | WBS Name | Activity ID | Activity Name | Start | Finish | Resource ID | BNL_RAU_Institution | Budgeted Units | Budgeted Cost | BNL_RAU_EU Factor | BNL_RAU_EU $ of Burd Esc | BNL_RAU_Burdened $ Esc w EU | sPHENIX Resource Category | Resource Type | Spreadsheet Field | FY19 | FY20 | FY21 | FY22
Project: POM02B_3 POM02 sPHENIX WBS 3.02 Preliminary Baseline [MVTX] |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 1213307 | 3909683 |  | 1011622 | 4919188 |  |  | Budgeted Cost | 225071 | 2536156 | 918158 | 230297
Project: POM02B_3 POM02 sPHENIX WBS 3.02 Preliminary Baseline [MVTX] |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 1213307 | 3909683 |  | 1011622 | 4919188 |  |  | Budgeted Units | 77222 | 766715 | 321052 | 48319
WBS: POM02B_3.02 MVTX |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 1213307 | 3909683 |  | 1011622 | 4919188 |  |  | Budgeted Cost | 225071 | 2536156 | 918158 | 230297
WBS: POM02B_3.02 MVTX |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 1213307 | 3909683 |  | 1011622 | 4919188 |  |  | Budgeted Units | 77222 | 766715 | 321052 | 48319
WBS: POM02B_3.02.01 MVTX Project Management |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 37798 | 544602 |  | 0 | 544602 |  |  | Budgeted Cost | 23540 | 210128 | 209596 | 101338
WBS: POM02B_3.02.01 MVTX Project Management |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 37798 | 544602 |  | 0 | 544602 |  |  | Budgeted Units | 6299 | 10614 | 10612 | 10274
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100600 | Project Manager | 2019-09-03 | 2022-03-17 | MGR LANL | LANL | 1238 | 398112 | 0 | 0 | 398112 | MGR | Labor | Budgeted Cost | 12579 | 157861 | 157232 | 70440
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100600 | Project Manager | 2019-09-03 | 2022-03-17 | MGR LANL | LANL | 1238 | 398112 | 0 | 0 | 398112 | MGR | Labor | Budgeted Units | 39 | 491 | 489 | 219
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100700 | Mechanical Integration Engineer | 2019-09-03 | 2022-03-17 | PROF4 LANL | LANL | 310 | 99657 | 0 | 0 | 99657 | PROF | Labor | Budgeted Cost | 3149 | 39516 | 39359 | 17633
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100700 | Mechanical Integration Engineer | 2019-09-03 | 2022-03-17 | PROF4 LANL | LANL | 310 | 99657 | 0 | 0 | 99657 | PROF | Labor | Budgeted Units | 10 | 123 | 122 | 55
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100800 | Electronics Integration Engineer | 2019-09-03 | 2022-03-17 | PROF4 LANL | LANL | 0 | 0 | 0 | 0 | 0 | PROF | Labor | Budgeted Cost
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100800 | Electronics Integration Engineer | 2019-09-03 | 2022-03-17 | PROF4 LANL | LANL | 0 | 0 | 0 | 0 | 0 | PROF | Labor | Budgeted Units
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100900 | Travel FY19 | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 6250 | 7813 | 0 | 0 | 7813 |  | Nonlabor | Budgeted Cost | 7813
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100900 | Travel FY19 | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 6250 | 7813 | 0 | 0 | 7813 |  | Nonlabor | Budgeted Units | 6250
POM02B_3.02.01 | 2.01 | MVTX Project Management | S101100 | Travel FY20 | 2019-10-01 | 2020-09-30 | Purch 1st $2M sOL | OL | 10000 | 12750 | 0 | 0 | 12750 |  | Nonlabor | Budgeted Cost |  | 12750
POM02B_3.02.01 | 2.01 | MVTX Project Management | S101100 | Travel FY20 | 2019-10-01 | 2020-09-30 | Purch 1st $2M sOL | OL | 10000 | 12750 | 0 | 0 | 12750 |  | Nonlabor | Budgeted Units |  | 10000
POM02B_3.02.01 | 2.01 | MVTX Project Management | S101200 | Travel FY21 | 2020-10-01 | 2021-09-30 | Purch 1st $2M sOL | OL | 10000 | 13005 | 0 | 0 | 13005 |  | Nonlabor | Budgeted Cost |  |  | 13005
POM02B_3.02.01 | 2.01 | MVTX Project Management | S101200 | Travel FY21 | 2020-10-01 | 2021-09-30 | Purch 1st $2M sOL | OL | 10000 | 13005 | 0 | 0 | 13005 |  | Nonlabor | Budgeted Units |  |  | 10000
POM02B_3.02.01 | 2.01 | MVTX Project Management | S101300 | Travel FY22 | 2021-10-01 | 2022-03-17 | Purch 1st $2M sOL | OL | 10000 | 13265 | 0 | 0 | 13265 |  | Nonlabor | Budgeted Cost |  |  |  | 13265
POM02B_3.02.01 | 2.01 | MVTX Project Management | S101300 | Travel FY22 | 2021-10-01 | 2022-03-17 | Purch 1st $2M sOL | OL | 10000 | 13265 | 0 | 0 | 13265 |  | Nonlabor | Budgeted Units |  |  |  | 10000
WBS: POM02B_3.02.02 MVTX Electronics |  |  |  |  | 2019-09-03 | 2020-09-15 |  |  | 303491 | 569582 |  | 101642 | 671224 |  |  | Budgeted Cost | 41687 | 527895
WBS: POM02B_3.02.02 MVTX Electronics |  |  |  |  | 2019-09-03 | 2020-09-15 |  |  | 303491 | 569582 |  | 101642 | 671224 |  |  | Budgeted Units | 20377 | 283115
WBS: POM02B_3.02.02.01 Readout Unit (RU) |  |  |  |  | 2019-10-30 | 2020-09-15 |  |  | 70010 | 213002 |  | 27867 | 240870 |  |  | Budgeted Cost |  | 213002
WBS: POM02B_3.02.02.01 Readout Unit (RU) |  |  |  |  | 2019-10-30 | 2020-09-15 |  |  | 70010 | 213002 |  | 27867 | 240870 |  |  | Budgeted Units |  | 70010
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101900 | Test/QA RU - Labor | 2019-12-02 | 2020-01-29 | SCI3 LANL | LANL | 100 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101900 | Test/QA RU - Labor | 2019-12-02 | 2020-01-29 | SCI3 LANL | LANL | 100 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units |  | 100
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101900 | Test/QA RU - Labor | 2019-12-02 | 2020-01-29 | ElectTech UTAustin | UTAustin | 320 | 33784 | 0.1 | 3378 | 37163 | TECH | Labor | Budgeted Cost |  | 33784
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101900 | Test/QA RU - Labor | 2019-12-02 | 2020-01-29 | ElectTech UTAustin | UTAustin | 320 | 33784 | 0.1 | 3378 | 37163 | TECH | Labor | Budgeted Units |  | 320
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102100 | Procure 60 SamTec Cables -Provide Requirements to Procurement | 2020-01-30 | 2020-02-05 | TECH4 LANL | LANL | 5 | 950 | 0.1 | 95 | 1045 | TECH | Labor | Budgeted Cost |  | 950
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102100 | Procure 60 SamTec Cables -Provide Requirements to Procurement | 2020-01-30 | 2020-02-05 | TECH4 LANL | LANL | 5 | 950 | 0.1 | 95 | 1045 | TECH | Labor | Budgeted Units |  | 5
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102800 | Test/QA SamTec Cables Check if still needed | 2020-07-07 | 2020-08-31 | SCI3 LANL | LANL | 320 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102800 | Test/QA SamTec Cables Check if still needed | 2020-07-07 | 2020-08-31 | SCI3 LANL | LANL | 320 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units |  | 320
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102800 | Test/QA SamTec Cables Check if still needed | 2020-07-07 | 2020-08-31 | ElectTech UTAustin | UTAustin | 320 | 33784 | 0.1 | 3378 | 37163 | TECH | Labor | Budgeted Cost |  | 33784
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102800 | Test/QA SamTec Cables Check if still needed | 2020-07-07 | 2020-08-31 | ElectTech UTAustin | UTAustin | 320 | 33784 | 0.1 | 3378 | 37163 | TECH | Labor | Budgeted Units |  | 320
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102700 | Procure 60 SamTec Cables - Delivery Acceptance | 2020-06-29 | 2020-07-06 | Purch 1st $2M sDOE | DOE | 30000 | 34850 | 0.1 | 3485 | 38335 |  | Nonlabor | Budgeted Cost |  | 34850
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102700 | Procure 60 SamTec Cables - Delivery Acceptance | 2020-06-29 | 2020-07-06 | Purch 1st $2M sDOE | DOE | 30000 | 34850 | 0.1 | 3485 | 38335 |  | Nonlabor | Budgeted Units |  | 30000
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102900 | Ship RU & SamTec Cables from CERN to UT Austin | 2020-09-01 | 2020-09-08 | Purch 1st $2M sOL | OL | 2000 | 2550 | 0.1 | 255 | 2805 |  | Nonlabor | Budgeted Cost |  | 2550
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102900 | Ship RU & SamTec Cables from CERN to UT Austin | 2020-09-01 | 2020-09-08 | Purch 1st $2M sOL | OL | 2000 | 2550 | 0.1 | 255 | 2805 |  | Nonlabor | Budgeted Units |  | 2000
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101800 | Procure Power Mezzanine for RU M&S | 2019-10-30 | 2019-11-13 | Purch 1st $2M sOL | OL | 4757 | 6065 | 0.25 | 1516 | 7581 |  | Nonlabor | Budgeted Cost |  | 6065
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101800 | Procure Power Mezzanine for RU M&S | 2019-10-30 | 2019-11-13 | Purch 1st $2M sOL | OL | 4757 | 6065 | 0.25 | 1516 | 7581 |  | Nonlabor | Budgeted Units |  | 4757
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102800 | Test/QA SamTec Cables Check if still needed | 2020-07-07 | 2020-08-31 | ElectEng UTAustin | UTAustin | 320 | 52043 | 0.1 | 5204 | 57247 | PROF | Labor | Budgeted Cost |  | 52043
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102800 | Test/QA SamTec Cables Check if still needed | 2020-07-07 | 2020-08-31 | ElectEng UTAustin | UTAustin | 320 | 52043 | 0.1 | 5204 | 57247 | PROF | Labor | Budgeted Units |  | 320
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101500 | Produce RU Cold Plate - Labor | 2019-10-30 | 2019-11-27 | ElectTech UTAustin | UTAustin | 60 | 6335 | 0.25 | 1584 | 7918 | TECH | Labor | Budgeted Cost |  | 6335
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101500 | Produce RU Cold Plate - Labor | 2019-10-30 | 2019-11-27 | ElectTech UTAustin | UTAustin | 60 | 6335 | 0.25 | 1584 | 7918 | TECH | Labor | Budgeted Units |  | 60
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101600 | Procure Transition Board for RU M&S | 2019-10-30 | 2019-11-13 | Purch 1st $2M sOL | OL | 7935 | 10117 | 0.25 | 2529 | 12646 |  | Nonlabor | Budgeted Cost |  | 10117
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101600 | Procure Transition Board for RU M&S | 2019-10-30 | 2019-11-13 | Purch 1st $2M sOL | OL | 7935 | 10117 | 0.25 | 2529 | 12646 |  | Nonlabor | Budgeted Units |  | 7935
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101700 | Produce RU Cold Plate - M&S | 2019-10-30 | 2019-11-27 | Purch 1st $2M sOL | OL | 15353 | 19575 | 0.25 | 4894 | 24469 |  | Nonlabor | Budgeted Cost |  | 19575
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101700 | Produce RU Cold Plate - M&S | 2019-10-30 | 2019-11-27 | Purch 1st $2M sOL | OL | 15353 | 19575 | 0.25 | 4894 | 24469 |  | Nonlabor | Budgeted Units |  | 15353
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102000 | Test/QA RU - M&S | 2019-12-02 | 2020-01-29 | Purch 1st $2M sOL | OL | 7500 | 9563 | 0.1 | 956 | 10519 |  | Nonlabor | Budgeted Cost |  | 9563
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102000 | Test/QA RU - M&S | 2019-12-02 | 2020-01-29 | Purch 1st $2M sOL | OL | 7500 | 9563 | 0.1 | 956 | 10519 |  | Nonlabor | Budgeted Units |  | 7500
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101601 | Procure Transition Board for RU Labor | 2019-10-30 | 2019-11-13 | ElectTech UTAustin | UTAustin | 8 | 845 | 0.25 | 211 | 1056 | TECH | Labor | Budgeted Cost |  | 845
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101601 | Procure Transition Board for RU Labor | 2019-10-30 | 2019-11-13 | ElectTech UTAustin | UTAustin | 8 | 845 | 0.25 | 211 | 1056 | TECH | Labor | Budgeted Units |  | 8
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101801 | Procure Power Mezzanine for RU Labor | 2019-10-30 | 2019-11-13 | ElectTech UTAustin | UTAustin | 8 | 845 | 0.25 | 211 | 1056 | TECH | Labor | Budgeted Cost |  | 845
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101801 | Procure Power Mezzanine for RU Labor | 2019-10-30 | 2019-11-13 | ElectTech UTAustin | UTAustin | 8 | 845 | 0.25 | 211 | 1056 | TECH | Labor | Budgeted Units |  | 8
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102902 | Ship RU & SamTec Cables from UT Austin to BNL M&S | 2020-09-09 | 2020-09-15 | Purch 1st $2M sOL | OL | 1000 | 1275 | 0.1 | 128 | 1403 |  | Nonlabor | Budgeted Cost |  | 1275
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102902 | Ship RU & SamTec Cables from UT Austin to BNL M&S | 2020-09-09 | 2020-09-15 | Purch 1st $2M sOL | OL | 1000 | 1275 | 0.1 | 128 | 1403 |  | Nonlabor | Budgeted Units |  | 1000
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102901 | Ship RU & SamTec Cables from UT Austin to BNL Labor | 2020-09-09 | 2020-09-15 | ElectTech UTAustin | UTAustin | 4 | 422 | 0.1 | 42 | 465 | TECH | Labor | Budgeted Cost |  | 422
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102901 | Ship RU & SamTec Cables from UT Austin to BNL Labor | 2020-09-09 | 2020-09-15 | ElectTech UTAustin | UTAustin | 4 | 422 | 0.1 | 42 | 465 | TECH | Labor | Budgeted Units |  | 4
WBS: POM02B_3.02.02.02 FELIX 2.0 |  |  |  |  | 2019-09-03 | 2020-06-22 |  |  | 76595 | 110571 |  | 27260 | 137832 |  |  | Budgeted Cost | 4692 | 105879
WBS: POM02B_3.02.02.02 FELIX 2.0 |  |  |  |  | 2019-09-03 | 2020-06-22 |  |  | 76595 | 110571 |  | 27260 | 137832 |  |  | Budgeted Units | 2864 | 73730
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103000 | Produce Felix 2.0 first production unit - Labor | 2019-09-03 | 2019-11-22 | TECH4 LANL | LANL | 16 | 3133 | 0.25 | 783 | 3916 | TECH | Labor | Budgeted Cost | 1099 | 2034
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103000 | Produce Felix 2.0 first production unit - Labor | 2019-09-03 | 2019-11-22 | TECH4 LANL | LANL | 16 | 3133 | 0.25 | 783 | 3916 | TECH | Labor | Budgeted Units | 6 | 10
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103100 | Procure Optical Fiber - Labor | 2019-09-03 | 2019-09-30 | TECH4 LANL | LANL | 2 | 307 | 0.25 | 77 | 384 | TECH | Labor | Budgeted Cost | 307
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103100 | Procure Optical Fiber - Labor | 2019-09-03 | 2019-09-30 | TECH4 LANL | LANL | 2 | 307 | 0.25 | 77 | 384 | TECH | Labor | Budgeted Units | 2
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103400 | Test/QA 1st Felix Unit and Fibers | 2019-11-25 | 2019-12-10 | SCI3 LANL | LANL | 40 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103400 | Test/QA 1st Felix Unit and Fibers | 2019-11-25 | 2019-12-10 | SCI3 LANL | LANL | 40 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  | 40
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103500 | Procure 7 Felix 2.0 Remaining Units -Provide Requirements to Procurement | 2020-03-18 | 2020-03-24 | TECH4 LANL | LANL | 6 | 1266 | 0.25 | 317 | 1583 | TECH | Labor | Budgeted Cost |  | 1266
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103500 | Procure 7 Felix 2.0 Remaining Units -Provide Requirements to Procurement | 2020-03-18 | 2020-03-24 | TECH4 LANL | LANL | 6 | 1266 | 0.25 | 317 | 1583 | TECH | Labor | Budgeted Units |  | 6
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103450 | Procure 57 Optical Fiber Sets - Labor | 2020-03-18 | 2020-04-14 | TECH4 LANL | LANL | 2 | 317 | 0.25 | 79 | 396 | TECH | Labor | Budgeted Cost |  | 317
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103450 | Procure 57 Optical Fiber Sets - Labor | 2020-03-18 | 2020-04-14 | TECH4 LANL | LANL | 2 | 317 | 0.25 | 79 | 396 | TECH | Labor | Budgeted Units |  | 2
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104400 | Test/QA 7 Felix Units and Fibers - Labor | 2020-06-02 | 2020-06-15 | SCI3 LANL | LANL | 43 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104400 | Test/QA 7 Felix Units and Fibers - Labor | 2020-06-02 | 2020-06-15 | SCI3 LANL | LANL | 43 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  | 43
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104400 | Test/QA 7 Felix Units and Fibers - Labor | 2020-06-02 | 2020-06-15 | TECH4 LANL | LANL | 43 | 8507 | 0.25 | 2127 | 10633 | TECH | Labor | Budgeted Cost |  | 8507
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104400 | Test/QA 7 Felix Units and Fibers - Labor | 2020-06-02 | 2020-06-15 | TECH4 LANL | LANL | 43 | 8507 | 0.25 | 2127 | 10633 | TECH | Labor | Budgeted Units |  | 43
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103002 | Produce Felix 2.0 first production unit - M&S | 2019-09-03 | 2019-11-22 | Purch 1st $2M sDOE | DOE | 8000 | 9186 | 0.25 | 2297 | 11483 |  | Nonlabor | Budgeted Cost | 3223 | 5963
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103002 | Produce Felix 2.0 first production unit - M&S | 2019-09-03 | 2019-11-22 | Purch 1st $2M sDOE | DOE | 8000 | 9186 | 0.25 | 2297 | 11483 |  | Nonlabor | Budgeted Units | 2807 | 5193
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104300 | Procure 7 Felix 2.0 Remaining Units - Delivery Acceptance | 2020-05-26 | 2020-06-01 | Purch 1st $2M sDOE | DOE | 56000 | 65054 | 0.25 | 16263 | 81317 |  | Nonlabor | Budgeted Cost |  | 65054
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104300 | Procure 7 Felix 2.0 Remaining Units - Delivery Acceptance | 2020-05-26 | 2020-06-01 | Purch 1st $2M sDOE | DOE | 56000 | 65054 | 0.25 | 16263 | 81317 |  | Nonlabor | Budgeted Units |  | 56000
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104600 | Ship Felix Units and Fibers to BNL | 2020-06-16 | 2020-06-22 | Purch 1st $2M sOL | OL | 2000 | 2550 | 0.1 | 255 | 2805 |  | Nonlabor | Budgeted Cost |  | 2550
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104600 | Ship Felix Units and Fibers to BNL | 2020-06-16 | 2020-06-22 | Purch 1st $2M sOL | OL | 2000 | 2550 | 0.1 | 255 | 2805 |  | Nonlabor | Budgeted Units |  | 2000
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103300 | Procure Optical Fiber - M&S | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 50 | 63 | 0.25 | 16 | 78 |  | Nonlabor | Budgeted Cost | 63
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103300 | Procure Optical Fiber - M&S | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 50 | 63 | 0.25 | 16 | 78 |  | Nonlabor | Budgeted Units | 50
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103460 | Procure 57 Optical Fiber Sets M&S | 2020-03-18 | 2020-04-14 | Purch 1st $2M sOL | OL | 2850 | 3634 | 0.25 | 908 | 4542 |  | Nonlabor | Budgeted Cost |  | 3634
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103460 | Procure 57 Optical Fiber Sets M&S | 2020-03-18 | 2020-04-14 | Purch 1st $2M sOL | OL | 2850 | 3634 | 0.25 | 908 | 4542 |  | Nonlabor | Budgeted Units |  | 2850
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104400 | Test/QA 7 Felix Units and Fibers - Labor | 2020-06-02 | 2020-06-15 | ElectEng UTAustin | UTAustin | 43 | 6993 | 0.25 | 1748 | 8742 | PROF | Labor | Budgeted Cost |  | 6993
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104400 | Test/QA 7 Felix Units and Fibers - Labor | 2020-06-02 | 2020-06-15 | ElectEng UTAustin | UTAustin | 43 | 6993 | 0.25 | 1748 | 8742 | PROF | Labor | Budgeted Units |  | 43
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104500 | Test/QA 7 Felix Units and Fibers - M&S | 2020-06-02 | 2020-06-15 | Purch 1st $2M sOL | OL | 7500 | 9563 | 0.25 | 2391 | 11953 |  | Nonlabor | Budgeted Cost |  | 9563
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104500 | Test/QA 7 Felix Units and Fibers - M&S | 2020-06-02 | 2020-06-15 | Purch 1st $2M sOL | OL | 7500 | 9563 | 0.25 | 2391 | 11953 |  | Nonlabor | Budgeted Units |  | 7500
WBS: POM02B_3.02.02.03 MAPS Power System |  |  |  |  | 2019-09-03 | 2020-04-23 |  |  | 156887 | 246009 |  | 46514 | 292523 |  |  | Budgeted Cost | 36995 | 209013
WBS: POM02B_3.02.02.03 MAPS Power System |  |  |  |  | 2019-09-03 | 2020-04-23 |  |  | 156887 | 246009 |  | 46514 | 292523 |  |  | Budgeted Units | 17512 | 139374
WBS: POM02B_3.02.02.03.01 Power Boards |  |  |  |  | 2019-09-03 | 2020-04-16 |  |  | 79452 | 144329 |  | 33705 | 178034 |  |  | Budgeted Cost | 28783 | 115546
WBS: POM02B_3.02.02.03.01 Power Boards |  |  |  |  | 2019-09-03 | 2020-04-16 |  |  | 79452 | 144329 |  | 33705 | 178034 |  |  | Budgeted Units | 10156 | 69296
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106730 | Test PB - Labor | 2020-02-21 | 2020-03-19 | ELTECH4 LBNL | LBNL | 90 | 10928 | 0.1 | 1093 | 12021 | TECH | Labor | Budgeted Cost |  | 10928
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106730 | Test PB - Labor | 2020-02-21 | 2020-03-19 | ELTECH4 LBNL | LBNL | 90 | 10928 | 0.1 | 1093 | 12021 | TECH | Labor | Budgeted Units |  | 90
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | ELENG3 LBNL | LBNL | 42 | 7749 | 0.25 | 1937 | 9686 | PROF | Labor | Budgeted Cost |  | 7749
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | ELENG3 LBNL | LBNL | 42 | 7749 | 0.25 | 1937 | 9686 | PROF | Labor | Budgeted Units |  | 42
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | POSTD LBNL | LBNL | 18 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | POSTD LBNL | LBNL | 18 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 18
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | STAFFPHYS LBNL | LBNL | 18 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | STAFFPHYS LBNL | LBNL | 18 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  | 18
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | ELTECH4 LBNL | LBNL | 9 | 1122 | 0.25 | 280 | 1402 | TECH | Labor | Budgeted Cost |  | 1122
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | ELTECH4 LBNL | LBNL | 9 | 1122 | 0.25 | 280 | 1402 | TECH | Labor | Budgeted Units |  | 9
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106700 | Procure Production PB - Delivery Acceptance | 2020-02-06 | 2020-02-12 | Purch 1st $2M sDOE | DOE | 60000 | 69700 | 0.25 | 17425 | 87125 |  | Nonlabor | Budgeted Cost |  | 69700
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106700 | Procure Production PB - Delivery Acceptance | 2020-02-06 | 2020-02-12 | Purch 1st $2M sDOE | DOE | 60000 | 69700 | 0.25 | 17425 | 87125 |  | Nonlabor | Budgeted Units |  | 60000
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105700 | Fabricate Break Out Boards (qty?) - M&S | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 6600 | 8250 | 0.25 | 2063 | 10313 |  | Nonlabor | Budgeted Cost | 8250
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105700 | Fabricate Break Out Boards (qty?) - M&S | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 6600 | 8250 | 0.25 | 2063 | 10313 |  | Nonlabor | Budgeted Units | 6600
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105800 | Fabricate PB to Stave Cables - M&S | 2019-10-01 | 2019-10-29 | Purch 1st $2M sOL | OL | 8000 | 10200 | 0.25 | 2550 | 12750 |  | Nonlabor | Budgeted Cost |  | 10200
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105800 | Fabricate PB to Stave Cables - M&S | 2019-10-01 | 2019-10-29 | Purch 1st $2M sOL | OL | 8000 | 10200 | 0.25 | 2550 | 12750 |  | Nonlabor | Budgeted Units |  | 8000
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105100 | Procure Power Distribution (harness) - M&S | 2019-09-03 | 2019-09-27 | Purch 1st $2M sOL | OL | 0 | 0 | 0.25 | 0 | 0 |  | Nonlabor | Budgeted Cost
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105100 | Procure Power Distribution (harness) - M&S | 2019-09-03 | 2019-09-27 | Purch 1st $2M sOL | OL | 0 | 0 | 0.25 | 0 | 0 |  | Nonlabor | Budgeted Units
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106770 | Test PB - M&S | 2020-02-21 | 2020-03-19 | Purch 1st $2M sOL | OL | 0 | 0 | 0.1 | 0 | 0 |  | Nonlabor | Budgeted Cost
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106770 | Test PB - M&S | 2020-02-21 | 2020-03-19 | Purch 1st $2M sOL | OL | 0 | 0 | 0.1 | 0 | 0 |  | Nonlabor | Budgeted Units
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106000 | Fabricate Cold (Cooling) Plates - M&S | 2019-09-03 | 2019-09-16 | Purch 1st $2M sOL | OL | 3420 | 4275 | 0.25 | 1069 | 5344 |  | Nonlabor | Budgeted Cost | 4275
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106000 | Fabricate Cold (Cooling) Plates - M&S | 2019-09-03 | 2019-09-16 | Purch 1st $2M sOL | OL | 3420 | 4275 | 0.25 | 1069 | 5344 |  | Nonlabor | Budgeted Units | 3420
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106100 | Fabricate Cold (Cooling) Plates - Labor | 2019-09-03 | 2019-09-16 | MECHTECH4 LBNL | LBNL | 16 | 2111 | 0.25 | 528 | 2639 | TECH | Labor | Budgeted Cost | 2111
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106100 | Fabricate Cold (Cooling) Plates - Labor | 2019-09-03 | 2019-09-16 | MECHTECH4 LBNL | LBNL | 16 | 2111 | 0.25 | 528 | 2639 | TECH | Labor | Budgeted Units | 16
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105000 | Procure Power Distribution (harness) - Labor | 2019-09-03 | 2019-09-30 | ELTECH4 LBNL | LBNL | 120 | 14147 | 0.25 | 3537 | 17684 | TECH | Labor | Budgeted Cost | 14147
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105000 | Procure Power Distribution (harness) - Labor | 2019-09-03 | 2019-09-30 | ELTECH4 LBNL | LBNL | 120 | 14147 | 0.25 | 3537 | 17684 | TECH | Labor | Budgeted Units | 120
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105801 | Fabricate PB to Stave Cables - Labor | 2019-10-01 | 2019-10-29 | ELTECH4 LBNL | LBNL | 60 | 7286 | 0.25 | 1821 | 9107 | TECH | Labor | Budgeted Cost |  | 7286
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105801 | Fabricate PB to Stave Cables - Labor | 2019-10-01 | 2019-10-29 | ELTECH4 LBNL | LBNL | 60 | 7286 | 0.25 | 1821 | 9107 | TECH | Labor | Budgeted Units |  | 60
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106710 | Assemble PB Labor | 2020-02-13 | 2020-02-20 | ELTECH4 LBNL | LBNL | 30 | 3643 | 0.25 | 911 | 4554 | TECH | Labor | Budgeted Cost |  | 3643
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106710 | Assemble PB Labor | 2020-02-13 | 2020-02-20 | ELTECH4 LBNL | LBNL | 30 | 3643 | 0.25 | 911 | 4554 | TECH | Labor | Budgeted Units |  | 30
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106785 | Ship PB to BNL M&S | 2020-03-20 | 2020-04-16 | Purch 1st $2M sOL | OL | 1000 | 1275 | 0.1 | 128 | 1403 |  | Nonlabor | Budgeted Cost |  | 1275
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106785 | Ship PB to BNL M&S | 2020-03-20 | 2020-04-16 | Purch 1st $2M sOL | OL | 1000 | 1275 | 0.1 | 128 | 1403 |  | Nonlabor | Budgeted Units |  | 1000
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106780 | Ship PB to BNL Labor | 2020-03-20 | 2020-04-16 | ELTECH4 LBNL | LBNL | 30 | 3643 | 0.1 | 364 | 4007 | TECH | Labor | Budgeted Cost |  | 3643
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106780 | Ship PB to BNL Labor | 2020-03-20 | 2020-04-16 | ELTECH4 LBNL | LBNL | 30 | 3643 | 0.1 | 364 | 4007 | TECH | Labor | Budgeted Units |  | 30
WBS: POM02B_3.02.02.03.02 Power Supplies |  |  |  |  | 2019-09-03 | 2020-04-23 |  |  | 77434 | 101680 |  | 12809 | 114489 |  |  | Budgeted Cost | 8212 | 93468
WBS: POM02B_3.02.02.03.02 Power Supplies |  |  |  |  | 2019-09-03 | 2020-04-23 |  |  | 77434 | 101680 |  | 12809 | 114489 |  |  | Budgeted Units | 7356 | 70078
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107700 | test PB with power supplies | 2020-03-27 | 2020-04-09 | ELTECH4 LBNL | LBNL | 40 | 4857 | 0.1 | 486 | 5343 | TECH | Labor | Budgeted Cost |  | 4857
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107700 | test PB with power supplies | 2020-03-27 | 2020-04-09 | ELTECH4 LBNL | LBNL | 40 | 4857 | 0.1 | 486 | 5343 | TECH | Labor | Budgeted Units |  | 40
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107800 | Document Power System | 2020-04-10 | 2020-04-16 | POSTD LBNL | LBNL | 16 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107800 | Document Power System | 2020-04-10 | 2020-04-16 | POSTD LBNL | LBNL | 16 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 16
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107050 | Procure CAEN A2518 Power Module (16) - Provide Requirements to Procurement | 2019-09-03 | 2019-09-09 | POSTD LBNL | LBNL | 209 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107050 | Procure CAEN A2518 Power Module (16) - Provide Requirements to Procurement | 2019-09-03 | 2019-09-09 | POSTD LBNL | LBNL | 209 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Units | 209
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107670 | Procure and terminate PS-to-PB (cabling) - Labor | 2020-02-13 | 2020-03-26 | ELTECH4 LBNL | LBNL | 40 | 4857 | 0.25 | 1214 | 6071 | TECH | Labor | Budgeted Cost |  | 4857
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107670 | Procure and terminate PS-to-PB (cabling) - Labor | 2020-02-13 | 2020-03-26 | ELTECH4 LBNL | LBNL | 40 | 4857 | 0.25 | 1214 | 6071 | TECH | Labor | Budgeted Units |  | 40
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107600 | Procure CAEN A2518Power Module (16) - Delivery Acceptance | 2020-03-20 | 2020-03-26 | Purch 1st $2M sDOE | DOE | 43676 | 50737 | 0.1 | 5074 | 55811 |  | Nonlabor | Budgeted Cost |  | 50737
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107600 | Procure CAEN A2518Power Module (16) - Delivery Acceptance | 2020-03-20 | 2020-03-26 | Purch 1st $2M sDOE | DOE | 43676 | 50737 | 0.1 | 5074 | 55811 |  | Nonlabor | Budgeted Units |  | 43676
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107650 | Procure and terminate PS-to-PB (cabling) - M&S | 2020-02-13 | 2020-03-26 | Purch 1st $2M sOL | OL | 10000 | 12750 | 0.25 | 3188 | 15938 |  | Nonlabor | Budgeted Cost |  | 12750
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107650 | Procure and terminate PS-to-PB (cabling) - M&S | 2020-02-13 | 2020-03-26 | Purch 1st $2M sOL | OL | 10000 | 12750 | 0.25 | 3188 | 15938 |  | Nonlabor | Budgeted Units |  | 10000
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107900 | Ship Power System to BNL - M&S | 2020-04-17 | 2020-04-23 | Purch 1st $2M sOL | OL | 2000 | 2550 | 0.1 | 255 | 2805 |  | Nonlabor | Budgeted Cost |  | 2550
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107900 | Ship Power System to BNL - M&S | 2020-04-17 | 2020-04-23 | Purch 1st $2M sOL | OL | 2000 | 2550 | 0.1 | 255 | 2805 |  | Nonlabor | Budgeted Units |  | 2000
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107610 | Procure CAEN A3484 48V Power Supply | 2019-09-03 | 2019-11-27 | Purch 1st $2M sDOE | DOE | 8607 | 9889 | 0.1 | 989 | 10878 |  | Nonlabor | Budgeted Cost | 3296 | 6593
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107610 | Procure CAEN A3484 48V Power Supply | 2019-09-03 | 2019-11-27 | Purch 1st $2M sDOE | DOE | 8607 | 9889 | 0.1 | 989 | 10878 |  | Nonlabor | Budgeted Units | 2869 | 5738
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107620 | Procure CAEN SY4527 Main Frame | 2019-09-03 | 2019-11-27 | Purch 1st $2M sDOE | DOE | 11620 | 13351 | 0.1 | 1335 | 14686 |  | Nonlabor | Budgeted Cost | 4450 | 8900
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107620 | Procure CAEN SY4527 Main Frame | 2019-09-03 | 2019-11-27 | Purch 1st $2M sDOE | DOE | 11620 | 13351 | 0.1 | 1335 | 14686 |  | Nonlabor | Budgeted Units | 3873 | 7747
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107640 | Procure CAEN A4532 Power Booster | 2019-09-03 | 2019-11-27 | Purch 1st $2M sDOE | DOE | 1216 | 1397 | 0.1 | 140 | 1537 |  | Nonlabor | Budgeted Cost | 466 | 931
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107640 | Procure CAEN A4532 Power Booster | 2019-09-03 | 2019-11-27 | Purch 1st $2M sDOE | DOE | 1216 | 1397 | 0.1 | 140 | 1537 |  | Nonlabor | Budgeted Units | 405 | 811
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107910 | Ship Power System to BNL - Labor | 2020-04-17 | 2020-04-23 | ELTECH4 LBNL | LBNL | 11 | 1292 | 0.1 | 129 | 1421 | TECH | Labor | Budgeted Cost |  | 1292
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107910 | Ship Power System to BNL - Labor | 2020-04-17 | 2020-04-23 | ELTECH4 LBNL | LBNL | 11 | 1292 | 0.1 | 129 | 1421 | TECH | Labor | Budgeted Units |  | 11
WBS: POM02B_3.02.03 MVTX Mechanics and Detector Assembly |  |  |  |  | 2019-09-03 | 2022-03-16 |  |  | 538993 | 1920039 |  | 642119 | 2562157 |  |  | Budgeted Cost | 156644 | 1365369 | 284558 | 113468
WBS: POM02B_3.02.03 MVTX Mechanics and Detector Assembly |  |  |  |  | 2019-09-03 | 2022-03-16 |  |  | 538993 | 1920039 |  | 642119 | 2562157 |  |  | Budgeted Units | 47986 | 386713 | 69367 | 34926
WBS: POM02B_3.02.03.01 Staves |  |  |  |  | 2019-09-03 | 2021-01-22 |  |  | 149361 | 340771 |  | 78245 | 419016 |  |  | Budgeted Cost | 50916 | 176459 | 113396
WBS: POM02B_3.02.03.01 Staves |  |  |  |  | 2019-09-03 | 2021-01-22 |  |  | 149361 | 340771 |  | 78245 | 419016 |  |  | Budgeted Units | 30070 | 85846 | 33444
WBS: POM02B_3.02.03.01.01 Production |  |  |  |  | 2019-09-03 | 2020-09-08 |  |  | 58647 | 72924 |  | 2318 | 75242 |  |  | Budgeted Cost | 14265 | 58660
WBS: POM02B_3.02.03.01.01 Production |  |  |  |  | 2019-09-03 | 2020-09-08 |  |  | 58647 | 72924 |  | 2318 | 75242 |  |  | Budgeted Units | 11389 | 47258
POM02B_3.02.03.01.01 | 1.01 | Production | S108000 | Test/QA Staves at CERN | 2019-09-03 | 2020-09-08 | SCI3 LANL | LANL | 1280 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.01.01 | 1.01 | Production | S108000 | Test/QA Staves at CERN | 2019-09-03 | 2020-09-08 | SCI3 LANL | LANL | 1280 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units | 100 | 1180
POM02B_3.02.03.01.01 | 1.01 | Production | S108300 | CERN Test System - Labor | 2019-09-03 | 2019-09-30 | POSTD LBNL | LBNL | 4 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.01.01 | 1.01 | Production | S108300 | CERN Test System - Labor | 2019-09-03 | 2019-09-30 | POSTD LBNL | LBNL | 4 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units | 4
POM02B_3.02.03.01.01 | 1.01 | Production | S108300 | CERN Test System - Labor | 2019-09-03 | 2019-09-30 | STAFFPHYS LBNL | LBNL | 2 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.01.01 | 1.01 | Production | S108300 | CERN Test System - Labor | 2019-09-03 | 2019-09-30 | STAFFPHYS LBNL | LBNL | 2 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units | 2
POM02B_3.02.03.01.01 | 1.01 | Production | S108100 | CERN Test System - M&S | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 7360 | 9200 | 0.25 | 2300 | 11500 |  | Nonlabor | Budgeted Cost | 9200
POM02B_3.02.03.01.01 | 1.01 | Production | S108100 | CERN Test System - M&S | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 7360 | 9200 | 0.25 | 2300 | 11500 |  | Nonlabor | Budgeted Units | 7360
POM02B_3.02.03.01.01 | 1.01 | Production | S108300 | CERN Test System - Labor | 2019-09-03 | 2019-09-30 | ELENG3 LBNL | LBNL | 0 | 72 | 0.25 | 18 | 90 | PROF | Labor | Budgeted Cost | 72
POM02B_3.02.03.01.01 | 1.01 | Production | S108300 | CERN Test System - Labor | 2019-09-03 | 2019-09-30 | ELENG3 LBNL | LBNL | 0 | 72 | 0.25 | 18 | 90 | PROF | Labor | Budgeted Units | 0
POM02B_3.02.03.01.01 | 1.01 | Production | S108200 | Travel and Per Diem at CERN - M&S | 2019-09-03 | 2020-09-08 | Purch 1st $2M sOL | OL | 50000 | 63652 | 0 | 0 | 63652 |  | Nonlabor | Budgeted Cost | 4992 | 58660
POM02B_3.02.03.01.01 | 1.01 | Production | S108200 | Travel and Per Diem at CERN - M&S | 2019-09-03 | 2020-09-08 | Purch 1st $2M sOL | OL | 50000 | 63652 | 0 | 0 | 63652 |  | Nonlabor | Budgeted Units | 3922 | 46078
WBS: POM02B_3.02.03.01.02 Stave Assembly Tooling |  |  |  |  | 2020-07-29 | 2021-01-22 |  |  | 25264 | 97486 |  | 38994 | 136481 |  |  | Budgeted Cost |  | 31021 | 66465
WBS: POM02B_3.02.03.01.02 Stave Assembly Tooling |  |  |  |  | 2020-07-29 | 2021-01-22 |  |  | 25264 | 97486 |  | 38994 | 136481 |  |  | Budgeted Units |  | 180 | 25084
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108800 | Stave Assembly Tooling - Procure Assembly Fixtures and Tooling - M&S | 2020-10-23 | 2021-01-22 | Purch 1st $2M MIT | OL | 25000 | 51840 | 0.4 | 20736 | 72576 |  | Nonlabor | Budgeted Cost |  |  | 51840
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108800 | Stave Assembly Tooling - Procure Assembly Fixtures and Tooling - M&S | 2020-10-23 | 2021-01-22 | Purch 1st $2M MIT | OL | 25000 | 51840 | 0.4 | 20736 | 72576 |  | Nonlabor | Budgeted Units |  |  | 25000
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108400 | Stave Assembly Tooling - Design | 2020-07-29 | 2020-08-25 | PROF4 MIT | MIT | 80 | 13701 | 0.4 | 5481 | 19182 | PROF | Labor | Budgeted Cost |  | 13701
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108400 | Stave Assembly Tooling - Design | 2020-07-29 | 2020-08-25 | PROF4 MIT | MIT | 80 | 13701 | 0.4 | 5481 | 19182 | PROF | Labor | Budgeted Units |  | 80
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108700 | Stave Assembly Tooling - Final Jig Design | 2020-08-26 | 2020-10-22 | PROF4 MIT | MIT | 160 | 27711 | 0.4 | 11084 | 38796 | PROF | Labor | Budgeted Cost |  | 17319 | 10392
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108700 | Stave Assembly Tooling - Final Jig Design | 2020-08-26 | 2020-10-22 | PROF4 MIT | MIT | 160 | 27711 | 0.4 | 11084 | 38796 | PROF | Labor | Budgeted Units |  | 100 | 60
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108900 | Stave Assembly Tooling - Procure Assembly Fixtures and Tooling - Labor | 2020-10-23 | 2021-01-22 | PROF4 MIT | MIT | 24 | 4234 | 0.4 | 1693 | 5927 | PROF | Labor | Budgeted Cost |  |  | 4234
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108900 | Stave Assembly Tooling - Procure Assembly Fixtures and Tooling - Labor | 2020-10-23 | 2021-01-22 | PROF4 MIT | MIT | 24 | 4234 | 0.4 | 1693 | 5927 | PROF | Labor | Budgeted Units |  |  | 24
WBS: POM02B_3.02.03.01.03 Metrology |  |  |  |  | 2020-07-29 | 2020-12-30 |  |  | 7363 | 75834 |  | 27480 | 103314 |  |  | Budgeted Cost |  | 30918 | 44916
WBS: POM02B_3.02.03.01.03 Metrology |  |  |  |  | 2020-07-29 | 2020-12-30 |  |  | 7363 | 75834 |  | 27480 | 103314 |  |  | Budgeted Units |  | 180 | 7183
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109200 | Procure jigs - M&S | 2020-11-23 | 2020-12-22 | Purch 1st $2M MIT | OL | 5000 | 10368 | 0.4 | 4147 | 14515 |  | Nonlabor | Budgeted Cost |  |  | 10368
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109200 | Procure jigs - M&S | 2020-11-23 | 2020-12-22 | Purch 1st $2M MIT | OL | 5000 | 10368 | 0.4 | 4147 | 14515 |  | Nonlabor | Budgeted Units |  |  | 5000
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109000 | Metrology design | 2020-07-29 | 2020-09-23 | PROF4 MIT | MIT | 160 | 27403 | 0.4 | 10961 | 38364 | PROF | Labor | Budgeted Cost |  | 27403
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109000 | Metrology design | 2020-07-29 | 2020-09-23 | PROF4 MIT | MIT | 160 | 27403 | 0.4 | 10961 | 38364 | PROF | Labor | Budgeted Units |  | 160
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109100 | Design jigs | 2020-09-24 | 2020-11-20 | PROF4 MIT | MIT | 160 | 28122 | 0.4 | 11249 | 39371 | PROF | Labor | Budgeted Cost |  | 3515 | 24607
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109100 | Design jigs | 2020-09-24 | 2020-11-20 | PROF4 MIT | MIT | 160 | 28122 | 0.4 | 11249 | 39371 | PROF | Labor | Budgeted Units |  | 20 | 140
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109300 | Procure jigs - Labor | 2020-11-23 | 2020-12-22 | TECH4 MIT | MIT | 3 | 429 | 0.4 | 172 | 601 | TECH | Labor | Budgeted Cost |  |  | 429
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109300 | Procure jigs - Labor | 2020-11-23 | 2020-12-22 | TECH4 MIT | MIT | 3 | 429 | 0.4 | 172 | 601 | TECH | Labor | Budgeted Units |  |  | 3
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109500 | ship to LBNL - M&S | 2020-12-23 | 2020-12-30 | Purch 1st $2M MIT | OL | 2000 | 4147 | 0.1 | 415 | 4562 |  | Nonlabor | Budgeted Cost |  |  | 4147
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109500 | ship to LBNL - M&S | 2020-12-23 | 2020-12-30 | Purch 1st $2M MIT | OL | 2000 | 4147 | 0.1 | 415 | 4562 |  | Nonlabor | Budgeted Units |  |  | 2000
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109400 | ship to LBNL - Labor | 2020-12-23 | 2020-12-30 | TECH4 MIT | MIT | 40 | 5365 | 0.1 | 536 | 5901 | TECH | Labor | Budgeted Cost |  |  | 5365
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109400 | ship to LBNL - Labor | 2020-12-23 | 2020-12-30 | TECH4 MIT | MIT | 40 | 5365 | 0.1 | 536 | 5901 | TECH | Labor | Budgeted Units |  |  | 40
WBS: POM02B_3.02.03.01.04 Shipping and Storage Containers |  |  |  |  | 2019-09-03 | 2020-10-07 |  |  | 34087 | 63926 |  | 6393 | 70319 |  |  | Budgeted Cost | 36651 | 25260 | 2014
WBS: POM02B_3.02.03.01.04 Shipping and Storage Containers |  |  |  |  | 2019-09-03 | 2020-10-07 |  |  | 34087 | 63926 |  | 6393 | 70319 |  |  | Budgeted Units | 18681 | 14228 | 1177
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109700 | Design shipping container for 21 staves | 2019-09-03 | 2019-09-09 | MECHENG4 LBNL | LBNL | 40 | 9485 | 0.1 | 948 | 10433 | PROF | Labor | Budgeted Cost | 9485
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109700 | Design shipping container for 21 staves | 2019-09-03 | 2019-09-09 | MECHENG4 LBNL | LBNL | 40 | 9485 | 0.1 | 948 | 10433 | PROF | Labor | Budgeted Units | 40
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109610 | Design & Fabricate Storage Cabinets for Staves - Labor | 2019-09-03 | 2019-10-29 | MECHTECH4 LBNL | LBNL | 41 | 5434 | 0.1 | 543 | 5977 | TECH | Labor | Budgeted Cost | 2717 | 2717
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109610 | Design & Fabricate Storage Cabinets for Staves - Labor | 2019-09-03 | 2019-10-29 | MECHTECH4 LBNL | LBNL | 41 | 5434 | 0.1 | 543 | 5977 | TECH | Labor | Budgeted Units | 20 | 20
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109610 | Design & Fabricate Storage Cabinets for Staves - Labor | 2019-09-03 | 2019-10-29 | STAFFPHYS LBNL | LBNL | 78 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109610 | Design & Fabricate Storage Cabinets for Staves - Labor | 2019-09-03 | 2019-10-29 | STAFFPHYS LBNL | LBNL | 78 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units | 39 | 39
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109610 | Design & Fabricate Storage Cabinets for Staves - Labor | 2019-09-03 | 2019-10-29 | POSTD LBNL | LBNL | 156 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109610 | Design & Fabricate Storage Cabinets for Staves - Labor | 2019-09-03 | 2019-10-29 | POSTD LBNL | LBNL | 156 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Units | 78 | 78
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110300 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - Labor | 2020-07-29 | 2020-10-07 | MECHTECH4 LBNL | LBNL | 40 | 5453 | 0.1 | 545 | 5998 | TECH | Labor | Budgeted Cost |  | 4907 | 545
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110300 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - Labor | 2020-07-29 | 2020-10-07 | MECHTECH4 LBNL | LBNL | 40 | 5453 | 0.1 | 545 | 5998 | TECH | Labor | Budgeted Units |  | 36 | 4
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110300 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - Labor | 2020-07-29 | 2020-10-07 | STAFFPHYS LBNL | LBNL | 100 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110300 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - Labor | 2020-07-29 | 2020-10-07 | STAFFPHYS LBNL | LBNL | 100 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units |  | 90 | 10
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110300 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - Labor | 2020-07-29 | 2020-10-07 | POSTD LBNL | LBNL | 132 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110300 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - Labor | 2020-07-29 | 2020-10-07 | POSTD LBNL | LBNL | 132 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Units |  | 119 | 13
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109600 | Design & Fabricate Storage Cabinets for Staves - M&S | 2019-09-03 | 2019-10-29 | Purch 1st $2M sOL | OL | 6992 | 8827 | 0.1 | 883 | 9710 |  | Nonlabor | Budgeted Cost | 4414 | 4414
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109600 | Design & Fabricate Storage Cabinets for Staves - M&S | 2019-09-03 | 2019-10-29 | Purch 1st $2M sOL | OL | 6992 | 8827 | 0.1 | 883 | 9710 |  | Nonlabor | Budgeted Units | 3496 | 3496
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110200 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - M&S | 2020-07-29 | 2020-10-07 | Purch 1st $2M sOL | OL | 11500 | 14692 | 0.1 | 1469 | 16161 |  | Nonlabor | Budgeted Cost |  | 13223 | 1469
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110200 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - M&S | 2020-07-29 | 2020-10-07 | Purch 1st $2M sOL | OL | 11500 | 14692 | 0.1 | 1469 | 16161 |  | Nonlabor | Budgeted Units |  | 10350 | 1150
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110100 | Ship Stave Shipping Devices to CERN | 2019-09-17 | 2019-09-30 | Purch 1st $2M sOL | OL | 5000 | 6250 | 0.1 | 625 | 6875 |  | Nonlabor | Budgeted Cost | 6250
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110100 | Ship Stave Shipping Devices to CERN | 2019-09-17 | 2019-09-30 | Purch 1st $2M sOL | OL | 5000 | 6250 | 0.1 | 625 | 6875 |  | Nonlabor | Budgeted Units | 5000
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109900 | Procure Stave Shipping Plate (84) - Labor | 2019-09-10 | 2019-09-16 | MECHENG3 LBNL | LBNL | 8 | 1286 | 0.1 | 129 | 1415 | PROF | Labor | Budgeted Cost | 1286
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109900 | Procure Stave Shipping Plate (84) - Labor | 2019-09-10 | 2019-09-16 | MECHENG3 LBNL | LBNL | 8 | 1286 | 0.1 | 129 | 1415 | PROF | Labor | Budgeted Units | 8
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110000 | Procure Stave Shipping Plate (84) - M&S | 2019-09-10 | 2019-09-16 | Purch 1st $2M sOL | OL | 10000 | 12500 | 0.1 | 1250 | 13750 |  | Nonlabor | Budgeted Cost | 12500
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110000 | Procure Stave Shipping Plate (84) - M&S | 2019-09-10 | 2019-09-16 | Purch 1st $2M sOL | OL | 10000 | 12500 | 0.1 | 1250 | 13750 |  | Nonlabor | Budgeted Units | 10000
WBS: POM02B_3.02.03.01.05 Shipping the Staves from CERN to LBNL |  |  |  |  | 2019-12-04 | 2020-09-08 |  |  | 24000 | 30600 |  | 3060 | 33660 |  |  | Budgeted Cost |  | 30600
WBS: POM02B_3.02.03.01.05 Shipping the Staves from CERN to LBNL |  |  |  |  | 2019-12-04 | 2020-09-08 |  |  | 24000 | 30600 |  | 3060 | 33660 |  |  | Budgeted Units |  | 24000
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110400 | ship from CERN to LBNL - Batch 1 | 2019-12-04 | 2019-12-12 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Cost |  | 7650
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110400 | ship from CERN to LBNL - Batch 1 | 2019-12-04 | 2019-12-12 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Units |  | 6000
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110500 | ship from CERN to LBNL - Batch 2 | 2020-03-05 | 2020-03-13 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Cost |  | 7650
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110500 | ship from CERN to LBNL - Batch 2 | 2020-03-05 | 2020-03-13 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Units |  | 6000
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110600 | ship from CERN to LBNL - Batch 3 | 2020-06-02 | 2020-06-10 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Cost |  | 7650
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110600 | ship from CERN to LBNL - Batch 3 | 2020-06-02 | 2020-06-10 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Units |  | 6000
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110700 | ship from CERN to LBNL - Batch 4 | 2020-08-28 | 2020-09-08 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Cost |  | 7650
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110700 | ship from CERN to LBNL - Batch 4 | 2020-08-28 | 2020-09-08 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Units |  | 6000
WBS: POM02B_3.02.03.02 Carbon Structures |  |  |  |  | 2019-09-03 | 2022-03-16 |  |  | 352735 | 1329430 |  | 476401 | 1805830 |  |  | Budgeted Cost | 105728 | 1167344 | 33143 | 23214
WBS: POM02B_3.02.03.02 Carbon Structures |  |  |  |  | 2019-09-03 | 2022-03-16 |  |  | 352735 | 1329430 |  | 476401 | 1805830 |  |  | Budgeted Units | 17916 | 299761 | 17557 | 17500
WBS: POM02B_3.02.03.02.01 Mechanics Detector Design |  |  |  |  | 2019-09-03 | 2020-01-29 |  |  | 2080 | 419265 |  | 167706 | 586971 |  |  | Budgeted Cost | 83853 | 335412
WBS: POM02B_3.02.03.02.01 Mechanics Detector Design |  |  |  |  | 2019-09-03 | 2020-01-29 |  |  | 2080 | 419265 |  | 167706 | 586971 |  |  | Budgeted Units | 416 | 1664
POM02B_3.02.03.02.01 | 2.01 | Mechanics Detector Design | S110800 | Develop MVTX inner tracker mechanical model | 2019-09-03 | 2020-01-29 | PROF4 LANL | LANL | 640 | 200199 | 0.4 | 80080 | 280279 | PROF | Labor | Budgeted Cost | 40040 | 160159
POM02B_3.02.03.02.01 | 2.01 | Mechanics Detector Design | S110800 | Develop MVTX inner tracker mechanical model | 2019-09-03 | 2020-01-29 | PROF4 LANL | LANL | 640 | 200199 | 0.4 | 80080 | 280279 | PROF | Labor | Budgeted Units | 128 | 512
POM02B_3.02.03.02.01 | 2.01 | Mechanics Detector Design | S110810 | Develop MVTX inner tracker mechanical model MIT | 2019-09-03 | 2020-01-29 | PROF4 MIT | MIT | 800 | 136216 | 0.4 | 54486 | 190703 | PROF | Labor | Budgeted Cost | 27243 | 108973
POM02B_3.02.03.02.01 | 2.01 | Mechanics Detector Design | S110810 | Develop MVTX inner tracker mechanical model MIT | 2019-09-03 | 2020-01-29 | PROF4 MIT | MIT | 800 | 136216 | 0.4 | 54486 | 190703 | PROF | Labor | Budgeted Units | 160 | 640
POM02B_3.02.03.02.01 | 2.01 | Mechanics Detector Design | S110810 | Develop MVTX inner tracker mechanical model MIT | 2019-09-03 | 2020-01-29 | TECH4 MIT | MIT | 640 | 82849 | 0.4 | 33140 | 115989 | TECH | Labor | Budgeted Cost | 16570 | 66279
POM02B_3.02.03.02.01 | 2.01 | Mechanics Detector Design | S110810 | Develop MVTX inner tracker mechanical model MIT | 2019-09-03 | 2020-01-29 | TECH4 MIT | MIT | 640 | 82849 | 0.4 | 33140 | 115989 | TECH | Labor | Budgeted Units | 128 | 512
WBS: POM02B_3.02.03.02.02 End Wheels |  |  |  |  | 2020-01-30 | 2020-08-19 |  |  | 77124 | 310865 |  | 123465 | 434330 |  |  | Budgeted Cost |  | 310865
WBS: POM02B_3.02.03.02.02 End Wheels |  |  |  |  | 2020-01-30 | 2020-08-19 |  |  | 77124 | 310865 |  | 123465 | 434330 |  |  | Budgeted Units |  | 77124
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111800 | Review End-wheels | 2020-08-18 | 2020-08-19 | PROF4 LANL | LANL | 8 | 2517 | 0.05 | 126 | 2643 | PROF | Labor | Budgeted Cost |  | 2517
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111800 | Review End-wheels | 2020-08-18 | 2020-08-19 | PROF4 LANL | LANL | 8 | 2517 | 0.05 | 126 | 2643 | PROF | Labor | Budgeted Units |  | 8
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111600 | End wheels production and test - Labor | 2020-06-08 | 2020-08-17 | MECHTECH4 LBNL | LBNL | 384 | 52189 | 0.6 | 20876 | 73064 | TECH | Labor | Budgeted Cost |  | 52189
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111600 | End wheels production and test - Labor | 2020-06-08 | 2020-08-17 | MECHTECH4 LBNL | LBNL | 384 | 52189 | 0.6 | 20876 | 73064 | TECH | Labor | Budgeted Units |  | 384
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111600 | End wheels production and test - Labor | 2020-06-08 | 2020-08-17 | MECHENG4 LBNL | LBNL | 384 | 93786 | 0.6 | 37514 | 131300 | PROF | Labor | Budgeted Cost |  | 93786
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111600 | End wheels production and test - Labor | 2020-06-08 | 2020-08-17 | MECHENG4 LBNL | LBNL | 384 | 93786 | 0.6 | 37514 | 131300 | PROF | Labor | Budgeted Units |  | 384
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111700 | End wheels production and test - M&S | 2020-06-08 | 2020-08-17 | Purch 1st $2M sOL | OL | 0 | 0 | 0.1 | 0 | 0 |  | Nonlabor | Budgeted Cost
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111700 | End wheels production and test - M&S | 2020-06-08 | 2020-08-17 | Purch 1st $2M sOL | OL | 0 | 0 | 0.1 | 0 | 0 |  | Nonlabor | Budgeted Units
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111500 | Procure end wheels material - M&S | 2020-06-01 | 2020-06-05 | Purch 1st $2M sOL | OL | 15940 | 20324 | 0.6 | 8129 | 28453 |  | Nonlabor | Budgeted Cost |  | 20324
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111500 | Procure end wheels material - M&S | 2020-06-01 | 2020-06-05 | Purch 1st $2M sOL | OL | 15940 | 20324 | 0.6 | 8129 | 28453 |  | Nonlabor | Budgeted Units |  | 15940
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S110900 | End Weels Tooling Design | 2020-01-30 | 2020-03-12 | MECHENG4 LBNL | LBNL | 140 | 34193 | 0.6 | 13677 | 47870 | PROF | Labor | Budgeted Cost |  | 34193
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S110900 | End Weels Tooling Design | 2020-01-30 | 2020-03-12 | MECHENG4 LBNL | LBNL | 140 | 34193 | 0.6 | 13677 | 47870 | PROF | Labor | Budgeted Units |  | 140
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111000 | End-wheels tooling material - M&S | 2020-03-13 | 2020-04-16 | Purch 1st $2M sDOE | DOE | 60000 | 69700 | 0.6 | 27880 | 97580 |  | Nonlabor | Budgeted Cost |  | 69700
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111000 | End-wheels tooling material - M&S | 2020-03-13 | 2020-04-16 | Purch 1st $2M sDOE | DOE | 60000 | 69700 | 0.6 | 27880 | 97580 |  | Nonlabor | Budgeted Units |  | 60000
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111100 | End-wheels tooling material - Labor | 2020-03-13 | 2020-04-16 | MECHTECH4 LBNL | LBNL | 12 | 1631 | 0.6 | 652 | 2283 | TECH | Labor | Budgeted Cost |  | 1631
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111100 | End-wheels tooling material - Labor | 2020-03-13 | 2020-04-16 | MECHTECH4 LBNL | LBNL | 12 | 1631 | 0.6 | 652 | 2283 | TECH | Labor | Budgeted Units |  | 12
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111200 | End wheels tooling assembly - Labor | 2020-04-17 | 2020-05-29 | MECHTECH4 LBNL | LBNL | 240 | 32618 | 0.6 | 13047 | 45665 | TECH | Labor | Budgeted Cost |  | 32618
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111200 | End wheels tooling assembly - Labor | 2020-04-17 | 2020-05-29 | MECHTECH4 LBNL | LBNL | 240 | 32618 | 0.6 | 13047 | 45665 | TECH | Labor | Budgeted Units |  | 240
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111400 | Procure end wheels material - Labor | 2020-06-01 | 2020-06-05 | MECHENG4 LBNL | LBNL | 16 | 3908 | 0.6 | 1563 | 5471 | PROF | Labor | Budgeted Cost |  | 3908
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111400 | Procure end wheels material - Labor | 2020-06-01 | 2020-06-05 | MECHENG4 LBNL | LBNL | 16 | 3908 | 0.6 | 1563 | 5471 | PROF | Labor | Budgeted Units |  | 16
WBS: POM02B_3.02.03.02.03 Mechanics Fabrication |  |  |  |  | 2019-09-03 | 2022-03-16 |  |  | 263371 | 557207 |  | 178017 | 735223 |  |  | Budgeted Cost | 21875 | 478974 | 33143 | 23214
WBS: POM02B_3.02.03.02.03 Mechanics Fabrication |  |  |  |  | 2019-09-03 | 2022-03-16 |  |  | 263371 | 557207 |  | 178017 | 735223 |  |  | Budgeted Units | 17500 | 210813 | 17557 | 17500
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112600 | Travel LBNL - FY19 | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 17500 | 21875 | 0 | 0 | 21875 |  | Nonlabor | Budgeted Cost | 21875
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112600 | Travel LBNL - FY19 | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 17500 | 21875 | 0 | 0 | 21875 |  | Nonlabor | Budgeted Units | 17500
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112700 | Travel LBNL - FY20 | 2019-10-01 | 2020-09-30 | Purch 1st $2M sOL | OL | 17500 | 22313 | 0 | 0 | 22313 |  | Nonlabor | Budgeted Cost |  | 22313
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112700 | Travel LBNL - FY20 | 2019-10-01 | 2020-09-30 | Purch 1st $2M sOL | OL | 17500 | 22313 | 0 | 0 | 22313 |  | Nonlabor | Budgeted Units |  | 17500
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112800 | Travel LBNL - FY21 | 2020-10-01 | 2021-09-30 | Purch 1st $2M sOL | OL | 17500 | 22759 | 0 | 0 | 22759 |  | Nonlabor | Budgeted Cost |  |  | 22759
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112800 | Travel LBNL - FY21 | 2020-10-01 | 2021-09-30 | Purch 1st $2M sOL | OL | 17500 | 22759 | 0 | 0 | 22759 |  | Nonlabor | Budgeted Units |  |  | 17500
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112900 | Travel LBNL - FY22 | 2021-10-01 | 2022-03-16 | Purch 1st $2M sOL | OL | 17500 | 23214 | 0 | 0 | 23214 |  | Nonlabor | Budgeted Cost |  |  |  | 23214
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112900 | Travel LBNL - FY22 | 2021-10-01 | 2022-03-16 | Purch 1st $2M sOL | OL | 17500 | 23214 | 0 | 0 | 23214 |  | Nonlabor | Budgeted Units |  |  |  | 17500
WBS: POM02B_3.02.03.02.03.01 Cylindrical Support Structure (CYSS) |  |  |  |  | 2020-01-30 | 2020-09-01 |  |  | 76694 | 200808 |  | 80323 | 281131 |  |  | Budgeted Cost |  | 200808
WBS: POM02B_3.02.03.02.03.01 Cylindrical Support Structure (CYSS) |  |  |  |  | 2020-01-30 | 2020-09-01 |  |  | 76694 | 200808 |  | 80323 | 281131 |  |  | Budgeted Units |  | 76694
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113000 | CYSS Tooling Design | 2020-01-30 | 2020-02-27 | MECHENG4 LBNL | LBNL | 96 | 23446 | 0.45 | 9379 | 32825 | PROF | Labor | Budgeted Cost |  | 23446
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113000 | CYSS Tooling Design | 2020-01-30 | 2020-02-27 | MECHENG4 LBNL | LBNL | 96 | 23446 | 0.45 | 9379 | 32825 | PROF | Labor | Budgeted Units |  | 96
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113500 | Procure CYSS Material - Labor | 2020-04-10 | 2020-04-16 | STAFFPHYS LBNL | LBNL | 8 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113500 | Procure CYSS Material - Labor | 2020-04-10 | 2020-04-16 | STAFFPHYS LBNL | LBNL | 8 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Units |  | 8
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113700 | Production & Test CYSS - Labor | 2020-07-29 | 2020-09-01 | MECHTECH4 LBNL | LBNL | 169 | 22963 | 0.45 | 9185 | 32148 | TECH | Labor | Budgeted Cost |  | 22963
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113700 | Production & Test CYSS - Labor | 2020-07-29 | 2020-09-01 | MECHTECH4 LBNL | LBNL | 169 | 22963 | 0.45 | 9185 | 32148 | TECH | Labor | Budgeted Units |  | 169
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113700 | Production & Test CYSS - Labor | 2020-07-29 | 2020-09-01 | MECHENG4 LBNL | LBNL | 169 | 41266 | 0.45 | 16506 | 57772 | PROF | Labor | Budgeted Cost |  | 41266
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113700 | Production & Test CYSS - Labor | 2020-07-29 | 2020-09-01 | MECHENG4 LBNL | LBNL | 169 | 41266 | 0.45 | 16506 | 57772 | PROF | Labor | Budgeted Units |  | 169
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113700 | Production & Test CYSS - Labor | 2020-07-29 | 2020-09-01 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113700 | Production & Test CYSS - Labor | 2020-07-29 | 2020-09-01 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Units |  | 48
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113400 | Procure CYSS Material - M&S | 2020-04-10 | 2020-04-16 | Purch 1st $2M sOL | OL | 15940 | 20324 | 0.45 | 8129 | 28453 |  | Nonlabor | Budgeted Cost |  | 20324
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113400 | Procure CYSS Material - M&S | 2020-04-10 | 2020-04-16 | Purch 1st $2M sOL | OL | 15940 | 20324 | 0.45 | 8129 | 28453 |  | Nonlabor | Budgeted Units |  | 15940
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113100 | CYSS Tooling Material - Labor | 2020-02-28 | 2020-03-19 | STAFFPHYS LBNL | LBNL | 120 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113100 | CYSS Tooling Material - Labor | 2020-02-28 | 2020-03-19 | STAFFPHYS LBNL | LBNL | 120 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Units |  | 120
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113200 | CYSS Tooling Material - M&S | 2020-02-28 | 2020-03-19 | Purch 1st $2M sOL | OL | 30000 | 38250 | 0.45 | 15300 | 53550 |  | Nonlabor | Budgeted Cost |  | 38250
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113200 | CYSS Tooling Material - M&S | 2020-02-28 | 2020-03-19 | Purch 1st $2M sOL | OL | 30000 | 38250 | 0.45 | 15300 | 53550 |  | Nonlabor | Budgeted Units |  | 30000
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113300 | CYSS Tooling Iteration - Labor | 2020-03-20 | 2020-04-09 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113300 | CYSS Tooling Iteration - Labor | 2020-03-20 | 2020-04-09 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Units |  | 24
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113301 | CYSS Tooling Iteration - M&S | 2020-03-20 | 2020-04-09 | Purch 1st $2M sOL | OL | 30000 | 38250 | 0.45 | 15300 | 53550 |  | Nonlabor | Budgeted Cost |  | 38250
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113301 | CYSS Tooling Iteration - M&S | 2020-03-20 | 2020-04-09 | Purch 1st $2M sOL | OL | 30000 | 38250 | 0.45 | 15300 | 53550 |  | Nonlabor | Budgeted Units |  | 30000
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113510 | CYSS Tooling assembly | 2020-04-17 | 2020-05-14 | MECHTECH4 LBNL | LBNL | 120 | 16309 | 0.45 | 6524 | 22833 | TECH | Labor | Budgeted Cost |  | 16309
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113510 | CYSS Tooling assembly | 2020-04-17 | 2020-05-14 | MECHTECH4 LBNL | LBNL | 120 | 16309 | 0.45 | 6524 | 22833 | TECH | Labor | Budgeted Units |  | 120
WBS: POM02B_3.02.03.02.03.02 Service Barrel (SB) |  |  |  |  | 2020-04-10 | 2020-10-07 |  |  | 116677 | 266239 |  | 97693 | 363932 |  |  | Budgeted Cost |  | 255854 | 10385
WBS: POM02B_3.02.03.02.03.02 Service Barrel (SB) |  |  |  |  | 2020-04-10 | 2020-10-07 |  |  | 116677 | 266239 |  | 97693 | 363932 |  |  | Budgeted Units |  | 116619 | 57
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S113900 | Review SB Design-Fabrication Compatibility | 2020-04-10 | 2020-05-07 | MECHENG4 LBNL | LBNL | 51 | 12505 | 0.05 | 625 | 13130 | PROF | Labor | Budgeted Cost |  | 12505
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S113900 | Review SB Design-Fabrication Compatibility | 2020-04-10 | 2020-05-07 | MECHENG4 LBNL | LBNL | 51 | 12505 | 0.05 | 625 | 13130 | PROF | Labor | Budgeted Units |  | 51
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S113900 | Review SB Design-Fabrication Compatibility | 2020-04-10 | 2020-05-07 | STAFFPHYS LBNL | LBNL | 20 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S113900 | Review SB Design-Fabrication Compatibility | 2020-04-10 | 2020-05-07 | STAFFPHYS LBNL | LBNL | 20 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Units |  | 20
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S113900 | Review SB Design-Fabrication Compatibility | 2020-04-10 | 2020-05-07 | POSTD LBNL | LBNL | 20 | 0 | 0.05 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S113900 | Review SB Design-Fabrication Compatibility | 2020-04-10 | 2020-05-07 | POSTD LBNL | LBNL | 20 | 0 | 0.05 | 0 | 0 | STUD | Labor | Budgeted Units |  | 20
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | PROF4 MIT | MIT | 40 | 6782 | 0.05 | 339 | 7121 | PROF | Labor | Budgeted Cost |  | 6782
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | PROF4 MIT | MIT | 40 | 6782 | 0.05 | 339 | 7121 | PROF | Labor | Budgeted Units |  | 40
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114100 | SB Tooling - Labor | 2020-05-22 | 2020-06-26 | MECHENG4 LBNL | LBNL | 160 | 39077 | 0.45 | 15631 | 54708 | PROF | Labor | Budgeted Cost |  | 39077
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114100 | SB Tooling - Labor | 2020-05-22 | 2020-06-26 | MECHENG4 LBNL | LBNL | 160 | 39077 | 0.45 | 15631 | 54708 | PROF | Labor | Budgeted Units |  | 160
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114300 | Procure SB Material - Labor | 2020-06-29 | 2020-07-06 | STAFFPHYS LBNL | LBNL | 8 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114300 | Procure SB Material - Labor | 2020-06-29 | 2020-07-06 | STAFFPHYS LBNL | LBNL | 8 | 0 | 0.45 | 0 | 0 | SCI | Labor | Budgeted Units |  | 8
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114500 | Production & Test SB - Labor | 2020-09-02 | 2020-10-07 | MECHENG4 LBNL | LBNL | 118 | 28953 | 0.45 | 11581 | 40534 | PROF | Labor | Budgeted Cost |  | 23163 | 5791
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114500 | Production & Test SB - Labor | 2020-09-02 | 2020-10-07 | MECHENG4 LBNL | LBNL | 118 | 28953 | 0.45 | 11581 | 40534 | PROF | Labor | Budgeted Units |  | 94 | 24
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114500 | Production & Test SB - Labor | 2020-09-02 | 2020-10-07 | MECHTECH4 LBNL | LBNL | 168 | 22970 | 0.45 | 9188 | 32157 | TECH | Labor | Budgeted Cost |  | 18376 | 4594
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114500 | Production & Test SB - Labor | 2020-09-02 | 2020-10-07 | MECHTECH4 LBNL | LBNL | 168 | 22970 | 0.45 | 9188 | 32157 | TECH | Labor | Budgeted Units |  | 134 | 34
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114400 | Production & Test SB - M&S | 2020-09-02 | 2020-10-07 | Purch 1st $2M sOL | OL | 0 | 0 | 0.45 | 0 | 0 |  | Nonlabor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114400 | Production & Test SB - M&S | 2020-09-02 | 2020-10-07 | Purch 1st $2M sOL | OL | 0 | 0 | 0.45 | 0 | 0 |  | Nonlabor | Budgeted Units
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Units |  | 24
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | MECHENG4 LBNL | LBNL | 24 | 5862 | 0.05 | 293 | 6155 | PROF | Labor | Budgeted Cost |  | 5862
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | MECHENG4 LBNL | LBNL | 24 | 5862 | 0.05 | 293 | 6155 | PROF | Labor | Budgeted Units |  | 24
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | POSTD LBNL | LBNL | 24 | 0 | 0.05 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | POSTD LBNL | LBNL | 24 | 0 | 0.05 | 0 | 0 | STUD | Labor | Budgeted Units |  | 24
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114101 | SB Tooling - M&S | 2020-05-22 | 2020-06-26 | Purch 1st $2M sOL | OL | 40000 | 51000 | 0.45 | 20400 | 71400 |  | Nonlabor | Budgeted Cost |  | 51000
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114101 | SB Tooling - M&S | 2020-05-22 | 2020-06-26 | Purch 1st $2M sOL | OL | 40000 | 51000 | 0.45 | 20400 | 71400 |  | Nonlabor | Budgeted Units |  | 40000
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114100 | SB Tooling - Labor | 2020-05-22 | 2020-06-26 | MECHTECH4 LBNL | LBNL | 80 | 10873 | 0.45 | 4349 | 15222 | TECH | Labor | Budgeted Cost |  | 10873
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114100 | SB Tooling - Labor | 2020-05-22 | 2020-06-26 | MECHTECH4 LBNL | LBNL | 80 | 10873 | 0.45 | 4349 | 15222 | TECH | Labor | Budgeted Units |  | 80
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114200 | Procure SB Material - M&S | 2020-06-29 | 2020-07-06 | Purch 1st $2M sDOE | DOE | 75940 | 88217 | 0.45 | 35287 | 123504 |  | Nonlabor | Budgeted Cost |  | 88217
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114200 | Procure SB Material - M&S | 2020-06-29 | 2020-07-06 | Purch 1st $2M sDOE | DOE | 75940 | 88217 | 0.45 | 35287 | 123504 |  | Nonlabor | Budgeted Units |  | 75940
WBS: POM02B_3.02.03.02.04 MVTX Final Design Review |  |  |  |  | 2020-06-29 | 2020-07-28 |  |  | 10160 | 42093 |  | 7213 | 49306 |  |  | Budgeted Cost |  | 42093
WBS: POM02B_3.02.03.02.04 MVTX Final Design Review |  |  |  |  | 2020-06-29 | 2020-07-28 |  |  | 10160 | 42093 |  | 7213 | 49306 |  |  | Budgeted Units |  | 10160
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114900 | Incorporate MVTX Review Comments LBNL | 2020-07-14 | 2020-07-20 | MECHENG4 LBNL | LBNL | 36 | 8792 | 0.25 | 2198 | 10991 | PROF | Labor | Budgeted Cost |  | 8792
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114900 | Incorporate MVTX Review Comments LBNL | 2020-07-14 | 2020-07-20 | MECHENG4 LBNL | LBNL | 36 | 8792 | 0.25 | 2198 | 10991 | PROF | Labor | Budgeted Units |  | 36
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114800 | MVTX Design Review LBNL - Labor | 2020-06-29 | 2020-07-06 | MECHENG4 LBNL | LBNL | 8 | 1954 | 0.05 | 98 | 2052 | PROF | Labor | Budgeted Cost |  | 1954
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114800 | MVTX Design Review LBNL - Labor | 2020-06-29 | 2020-07-06 | MECHENG4 LBNL | LBNL | 8 | 1954 | 0.05 | 98 | 2052 | PROF | Labor | Budgeted Units |  | 8
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114800 | MVTX Design Review LBNL - Labor | 2020-06-29 | 2020-07-06 | STAFFPHYS LBNL | LBNL | 16 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114800 | MVTX Design Review LBNL - Labor | 2020-06-29 | 2020-07-06 | STAFFPHYS LBNL | LBNL | 16 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Units |  | 16
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114800 | MVTX Design Review LBNL - Labor | 2020-06-29 | 2020-07-06 | SCI3 LANL | LANL | 16 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114800 | MVTX Design Review LBNL - Labor | 2020-06-29 | 2020-07-06 | SCI3 LANL | LANL | 16 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Units |  | 16
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114700 | MVTX Design Review LBNL - M&S | 2020-06-29 | 2020-07-06 | Purch 1st $2M sOL | OL | 5000 | 6375 | 0.1 | 638 | 7013 |  | Nonlabor | Budgeted Cost |  | 6375
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114700 | MVTX Design Review LBNL - M&S | 2020-06-29 | 2020-07-06 | Purch 1st $2M sOL | OL | 5000 | 6375 | 0.1 | 638 | 7013 |  | Nonlabor | Budgeted Units |  | 5000
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114801 | MVTX Design Review LANL - Labor | 2020-07-07 | 2020-07-13 | STAFFPHYS LBNL | LBNL | 8 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114801 | MVTX Design Review LANL - Labor | 2020-07-07 | 2020-07-13 | STAFFPHYS LBNL | LBNL | 8 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Units |  | 8
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114801 | MVTX Design Review LANL - Labor | 2020-07-07 | 2020-07-13 | SCI3 LANL | LANL | 16 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114801 | MVTX Design Review LANL - Labor | 2020-07-07 | 2020-07-13 | SCI3 LANL | LANL | 16 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Units |  | 16
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114801 | MVTX Design Review LANL - Labor | 2020-07-07 | 2020-07-13 | PROF4 LANL | LANL | 16 | 5034 | 0.05 | 252 | 5286 | PROF | Labor | Budgeted Cost |  | 5034
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114801 | MVTX Design Review LANL - Labor | 2020-07-07 | 2020-07-13 | PROF4 LANL | LANL | 16 | 5034 | 0.05 | 252 | 5286 | PROF | Labor | Budgeted Units |  | 16
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114810 | MVTX Design Review LANL - M&S | 2020-07-07 | 2020-07-13 | Purch 1st $2M sOL | OL | 5000 | 6375 | 0.1 | 638 | 7013 |  | Nonlabor | Budgeted Cost |  | 6375
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114810 | MVTX Design Review LANL - M&S | 2020-07-07 | 2020-07-13 | Purch 1st $2M sOL | OL | 5000 | 6375 | 0.1 | 638 | 7013 |  | Nonlabor | Budgeted Units |  | 5000
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114910 | Incorporate MVTX Review Comments LANL | 2020-07-21 | 2020-07-27 | PROF4 LANL | LANL | 36 | 11327 | 0.25 | 2832 | 14159 | PROF | Labor | Budgeted Cost |  | 11327
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114910 | Incorporate MVTX Review Comments LANL | 2020-07-21 | 2020-07-27 | PROF4 LANL | LANL | 36 | 11327 | 0.25 | 2832 | 14159 | PROF | Labor | Budgeted Units |  | 36
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S115000 | Complete Final MVTX Design LBNL | 2020-07-28 | 2020-07-28 | MECHENG4 LBNL | LBNL | 4 | 977 | 0.25 | 244 | 1221 | PROF | Labor | Budgeted Cost |  | 977
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S115000 | Complete Final MVTX Design LBNL | 2020-07-28 | 2020-07-28 | MECHENG4 LBNL | LBNL | 4 | 977 | 0.25 | 244 | 1221 | PROF | Labor | Budgeted Units |  | 4
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S115010 | Complete Final MVTX Design LANL | 2020-07-28 | 2020-07-28 | PROF4 LANL | LANL | 4 | 1259 | 0.25 | 315 | 1573 | PROF | Labor | Budgeted Cost |  | 1259
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S115010 | Complete Final MVTX Design LANL | 2020-07-28 | 2020-07-28 | PROF4 LANL | LANL | 4 | 1259 | 0.25 | 315 | 1573 | PROF | Labor | Budgeted Units |  | 4
WBS: POM02B_3.02.03.03 Barrel Assembly |  |  |  |  | 2020-03-20 | 2021-12-13 |  |  | 36898 | 249839 |  | 87473 | 337311 |  |  | Budgeted Cost |  | 21565 | 138019 | 90254
WBS: POM02B_3.02.03.03 Barrel Assembly |  |  |  |  | 2020-03-20 | 2021-12-13 |  |  | 36898 | 249839 |  | 87473 | 337311 |  |  | Budgeted Units |  | 1106 | 18366 | 17426
WBS: POM02B_3.02.03.03.01 Assembly and Testing |  |  |  |  | 2020-03-20 | 2021-12-13 |  |  | 36898 | 249839 |  | 87473 | 337311 |  |  | Budgeted Cost |  | 21565 | 138019 | 90254
WBS: POM02B_3.02.03.03.01 Assembly and Testing |  |  |  |  | 2020-03-20 | 2021-12-13 |  |  | 36898 | 249839 |  | 87473 | 337311 |  |  | Budgeted Units |  | 1106 | 18366 | 17426
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Cost |  | 1788
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Units |  | 10
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Cost |  | 1272
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Units |  | 8
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Cost |  | 2331
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Units |  | 19
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 96
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  | 48
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 96
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Cost |  | 1788
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Units |  | 10
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Cost |  | 1272
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Units |  | 8
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Cost |  | 2331
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Units |  | 19
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 96
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  | 48
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 96
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Cost |  | 1788
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Units |  | 10
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Cost |  | 1272
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Units |  | 8
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Cost |  | 2331
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Units |  | 19
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 96
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  | 48
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 96
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Cost |  | 1788
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Units |  | 10
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Cost |  | 1272
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Units |  | 8
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Cost |  | 2331
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Units |  | 19
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 96
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  | 48
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  | 96
WBS: POM02B_3.02.03.03.01.01 Layer Assembly and Test |  |  |  |  | 2021-01-25 | 2021-07-30 |  |  | 8221 | 76978 |  | 29836 | 106815 |  |  | Budgeted Cost |  |  | 76978
WBS: POM02B_3.02.03.03.01.01 Layer Assembly and Test |  |  |  |  | 2021-01-25 | 2021-07-30 |  |  | 8221 | 76978 |  | 29836 | 106815 |  |  | Budgeted Units |  |  | 8221
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | MECHENG3 LBNL | LBNL | 16 | 2729 | 0.4 | 1092 | 3820 | PROF | Labor | Budgeted Cost |  |  | 2729
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | MECHENG3 LBNL | LBNL | 16 | 2729 | 0.4 | 1092 | 3820 | PROF | Labor | Budgeted Units |  |  | 16
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | MECHTECH4 LBNL | LBNL | 32 | 4480 | 0.4 | 1792 | 6271 | TECH | Labor | Budgeted Cost |  |  | 4480
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | MECHTECH4 LBNL | LBNL | 32 | 4480 | 0.4 | 1792 | 6271 | TECH | Labor | Budgeted Units |  |  | 32
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | POSTD LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | POSTD LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 160
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | STAFFPHYS LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | STAFFPHYS LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 160
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115700 | Hold Half-Detector Assembly Review (PRR) | 2021-02-23 | 2021-03-01 | MECHENG3 LBNL | LBNL | 16 | 2729 | 0.05 | 136 | 2865 | PROF | Labor | Budgeted Cost |  |  | 2729
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115700 | Hold Half-Detector Assembly Review (PRR) | 2021-02-23 | 2021-03-01 | MECHENG3 LBNL | LBNL | 16 | 2729 | 0.05 | 136 | 2865 | PROF | Labor | Budgeted Units |  |  | 16
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115700 | Hold Half-Detector Assembly Review (PRR) | 2021-02-23 | 2021-03-01 | POSTD LBNL | LBNL | 40 | 0 | 0.05 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115700 | Hold Half-Detector Assembly Review (PRR) | 2021-02-23 | 2021-03-01 | POSTD LBNL | LBNL | 40 | 0 | 0.05 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 40
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115700 | Hold Half-Detector Assembly Review (PRR) | 2021-02-23 | 2021-03-01 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115700 | Hold Half-Detector Assembly Review (PRR) | 2021-02-23 | 2021-03-01 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 40
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | CMMTECH4 LBNL | LBNL | 79 | 11234 | 0.4 | 4494 | 15727 | TECH | Labor | Budgeted Cost |  |  | 11234
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | CMMTECH4 LBNL | LBNL | 79 | 11234 | 0.4 | 4494 | 15727 | TECH | Labor | Budgeted Units |  |  | 79
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | STAFFPHYS LBNL | LBNL | 30 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | STAFFPHYS LBNL | LBNL | 30 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 30
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | POSTD LBNL | LBNL | 120 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | POSTD LBNL | LBNL | 120 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 120
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | GRSTUD LBNL | LBNL | 60 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | GRSTUD LBNL | LBNL | 60 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 60
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | MECHENG3 LBNL | LBNL | 56 | 9551 | 0.4 | 3820 | 13371 | PROF | Labor | Budgeted Cost |  |  | 9551
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | MECHENG3 LBNL | LBNL | 56 | 9551 | 0.4 | 3820 | 13371 | PROF | Labor | Budgeted Units |  |  | 56
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | ELENG3 LBNL | LBNL | 56 | 10744 | 0.4 | 4298 | 15042 | PROF | Labor | Budgeted Cost |  |  | 10744
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | ELENG3 LBNL | LBNL | 56 | 10744 | 0.4 | 4298 | 15042 | PROF | Labor | Budgeted Units |  |  | 56
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | POSTD LBNL | LBNL | 560 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | POSTD LBNL | LBNL | 560 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 560
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | STAFFPHYS LBNL | LBNL | 140 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | STAFFPHYS LBNL | LBNL | 140 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 140
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | ELTECH4 LBNL | LBNL | 112 | 14008 | 0.4 | 5603 | 19611 | TECH | Labor | Budgeted Cost |  |  | 14008
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | ELTECH4 LBNL | LBNL | 112 | 14008 | 0.4 | 5603 | 19611 | TECH | Labor | Budgeted Units |  |  | 112
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | GRSTUD LBNL | LBNL | 560 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | GRSTUD LBNL | LBNL | 560 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 560
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | ELENG3 LBNL | LBNL | 24 | 4605 | 0.4 | 1842 | 6447 | PROF | Labor | Budgeted Cost |  |  | 4605
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | ELENG3 LBNL | LBNL | 24 | 4605 | 0.4 | 1842 | 6447 | PROF | Labor | Budgeted Units |  |  | 24
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | MECHENG3 LBNL | LBNL | 41 | 6958 | 0.4 | 2783 | 9742 | PROF | Labor | Budgeted Cost |  |  | 6958
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | MECHENG3 LBNL | LBNL | 41 | 6958 | 0.4 | 2783 | 9742 | PROF | Labor | Budgeted Units |  |  | 41
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | ELTECH4 LBNL | LBNL | 24 | 3002 | 0.4 | 1201 | 4202 | TECH | Labor | Budgeted Cost |  |  | 3002
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | ELTECH4 LBNL | LBNL | 24 | 3002 | 0.4 | 1201 | 4202 | TECH | Labor | Budgeted Units |  |  | 24
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | POSTD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | POSTD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 240
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | STAFFPHYS LBNL | LBNL | 79 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | STAFFPHYS LBNL | LBNL | 79 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 79
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | GRSTUD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | GRSTUD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 240
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115800 | Install Staves Onto Layer End-Wheels To Form Layers - M&S | 2021-03-02 | 2021-06-08 | Purch 1st $2M sOL | OL | 2760 | 3589 | 0.4 | 1436 | 5025 |  | Nonlabor | Budgeted Cost |  |  | 3589
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115800 | Install Staves Onto Layer End-Wheels To Form Layers - M&S | 2021-03-02 | 2021-06-08 | Purch 1st $2M sOL | OL | 2760 | 3589 | 0.4 | 1436 | 5025 |  | Nonlabor | Budgeted Units |  |  | 2760
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116000 | Test and Rework Layers After Assembly - M&S | 2021-06-09 | 2021-07-14 | Purch 1st $2M sOL | OL | 2576 | 3350 | 0.4 | 1340 | 4690 |  | Nonlabor | Budgeted Cost |  |  | 3350
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116000 | Test and Rework Layers After Assembly - M&S | 2021-06-09 | 2021-07-14 | Purch 1st $2M sOL | OL | 2576 | 3350 | 0.4 | 1340 | 4690 |  | Nonlabor | Budgeted Units |  |  | 2576
WBS: POM02B_3.02.03.03.01.02 Half Barrel #1 Assembly and Test |  |  |  |  | 2021-08-02 | 2021-12-03 |  |  | 13785 | 75436 |  | 26038 | 101474 |  |  | Budgeted Cost |  |  | 37903 | 37533
WBS: POM02B_3.02.03.03.01.02 Half Barrel #1 Assembly and Test |  |  |  |  | 2021-08-02 | 2021-12-03 |  |  | 13785 | 75436 |  | 26038 | 101474 |  |  | Budgeted Units |  |  | 6163 | 7623
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | ELENG3 LBNL | LBNL | 16 | 3070 | 0.4 | 1228 | 4298 | PROF | Labor | Budgeted Cost |  |  | 3070
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | ELENG3 LBNL | LBNL | 16 | 3070 | 0.4 | 1228 | 4298 | PROF | Labor | Budgeted Units |  |  | 16
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | MECHENG3 LBNL | LBNL | 40 | 6822 | 0.4 | 2729 | 9551 | PROF | Labor | Budgeted Cost |  |  | 6822
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | MECHENG3 LBNL | LBNL | 40 | 6822 | 0.4 | 2729 | 9551 | PROF | Labor | Budgeted Units |  |  | 40
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | ELTECH4 LBNL | LBNL | 32 | 4002 | 0.4 | 1601 | 5603 | TECH | Labor | Budgeted Cost |  |  | 4002
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | ELTECH4 LBNL | LBNL | 32 | 4002 | 0.4 | 1601 | 5603 | TECH | Labor | Budgeted Units |  |  | 32
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | POSTD LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | POSTD LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 160
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | STAFFPHYS LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | STAFFPHYS LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 80
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | GRSTUD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | GRSTUD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 80
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | ELENG3 LBNL | LBNL | 24 | 4616 | 0.4 | 1846 | 6462 | PROF | Labor | Budgeted Cost |  |  | 4247 | 369
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | ELENG3 LBNL | LBNL | 24 | 4616 | 0.4 | 1846 | 6462 | PROF | Labor | Budgeted Units |  |  | 22 | 2
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | MECHENG3 LBNL | LBNL | 48 | 8206 | 0.4 | 3282 | 11488 | PROF | Labor | Budgeted Cost |  |  | 7550 | 656
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | MECHENG3 LBNL | LBNL | 48 | 8206 | 0.4 | 3282 | 11488 | PROF | Labor | Budgeted Units |  |  | 44 | 4
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | ELTECH4 LBNL | LBNL | 48 | 6018 | 0.4 | 2407 | 8425 | TECH | Labor | Budgeted Cost |  |  | 5536 | 481
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | ELTECH4 LBNL | LBNL | 48 | 6018 | 0.4 | 2407 | 8425 | TECH | Labor | Budgeted Units |  |  | 44 | 4
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | POSTD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | POSTD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 221 | 19
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | STAFFPHYS LBNL | LBNL | 79 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | STAFFPHYS LBNL | LBNL | 79 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 73 | 6
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | GRSTUD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | GRSTUD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 221 | 19
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | CMMTECH4 LBNL | LBNL | 56 | 8181 | 0.4 | 3273 | 11454 | TECH | Labor | Budgeted Cost |  |  |  | 8181
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | CMMTECH4 LBNL | LBNL | 56 | 8181 | 0.4 | 3273 | 11454 | TECH | Labor | Budgeted Units |  |  |  | 56
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  |  | 40
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | POSTD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | POSTD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 80
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | GRSTUD LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | GRSTUD LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 40
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | ELENG3 LBNL | LBNL | 16 | 3162 | 0.25 | 790 | 3952 | PROF | Labor | Budgeted Cost |  |  |  | 3162
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | ELENG3 LBNL | LBNL | 16 | 3162 | 0.25 | 790 | 3952 | PROF | Labor | Budgeted Units |  |  |  | 16
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | MECHENG3 LBNL | LBNL | 16 | 2811 | 0.25 | 703 | 3513 | PROF | Labor | Budgeted Cost |  |  |  | 2811
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | MECHENG3 LBNL | LBNL | 16 | 2811 | 0.25 | 703 | 3513 | PROF | Labor | Budgeted Units |  |  |  | 16
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | CMMTECH4 LBNL | LBNL | 24 | 3506 | 0.25 | 877 | 4383 | TECH | Labor | Budgeted Cost |  |  |  | 3506
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | CMMTECH4 LBNL | LBNL | 24 | 3506 | 0.25 | 877 | 4383 | TECH | Labor | Budgeted Units |  |  |  | 24
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | POSTD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | POSTD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 160
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | STAFFPHYS LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | STAFFPHYS LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  |  |  | 160
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | MECHTECH4 LBNL | LBNL | 32 | 4614 | 0.25 | 1153 | 5767 | TECH | Labor | Budgeted Cost |  |  |  | 4614
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | MECHTECH4 LBNL | LBNL | 32 | 4614 | 0.25 | 1153 | 5767 | TECH | Labor | Budgeted Units |  |  |  | 32
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | GRSTUD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | GRSTUD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 160
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | MECHENG3 LBNL | LBNL | 16 | 2740 | 0.25 | 685 | 3426 | PROF | Labor | Budgeted Cost |  |  |  | 2740
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | MECHENG3 LBNL | LBNL | 16 | 2740 | 0.25 | 685 | 3426 | PROF | Labor | Budgeted Units |  |  |  | 16
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | MECHTECH4 LBNL | LBNL | 16 | 2249 | 0.25 | 562 | 2812 | TECH | Labor | Budgeted Cost |  |  |  | 2249
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | MECHTECH4 LBNL | LBNL | 16 | 2249 | 0.25 | 562 | 2812 | TECH | Labor | Budgeted Units |  |  |  | 16
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | POSTD LBNL | LBNL | 120 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | POSTD LBNL | LBNL | 120 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 120
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  |  |  | 24
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116400 | Assemble Layers and CYSS into Half Barrel #1 - M&S | 2021-08-02 | 2021-08-27 | Purch 1st $2M sOL | OL | 2760 | 3589 | 0.4 | 1436 | 5025 |  | Nonlabor | Budgeted Cost |  |  | 3589
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116400 | Assemble Layers and CYSS into Half Barrel #1 - M&S | 2021-08-02 | 2021-08-27 | Purch 1st $2M sOL | OL | 2760 | 3589 | 0.4 | 1436 | 5025 |  | Nonlabor | Budgeted Units |  |  | 2760
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116600 | Test and Rework Half Barrel #1 - M&S | 2021-08-30 | 2021-10-04 | Purch 1st $2M sOL | OL | 2576 | 3355 | 0.4 | 1342 | 4698 |  | Nonlabor | Budgeted Cost |  |  | 3087 | 268
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116600 | Test and Rework Half Barrel #1 - M&S | 2021-08-30 | 2021-10-04 | Purch 1st $2M sOL | OL | 2576 | 3355 | 0.4 | 1342 | 4698 |  | Nonlabor | Budgeted Units |  |  | 2370 | 206
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116900 | Validation Of Final Assembly - M&S | 2021-10-20 | 2021-11-09 | Purch 1st $2M sOL | OL | 2576 | 3417 | 0.25 | 854 | 4271 |  | Nonlabor | Budgeted Cost |  |  |  | 3417
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116900 | Validation Of Final Assembly - M&S | 2021-10-20 | 2021-11-09 | Purch 1st $2M sOL | OL | 2576 | 3417 | 0.25 | 854 | 4271 |  | Nonlabor | Budgeted Units |  |  |  | 2576
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117100 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - M&S | 2021-11-10 | 2021-12-03 | Purch 1st $2M sOL | OL | 3827 | 5077 | 0.25 | 1269 | 6346 |  | Nonlabor | Budgeted Cost |  |  |  | 5077
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117100 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - M&S | 2021-11-10 | 2021-12-03 | Purch 1st $2M sOL | OL | 3827 | 5077 | 0.25 | 1269 | 6346 |  | Nonlabor | Budgeted Units |  |  |  | 3827
WBS: POM02B_3.02.03.03.01.03 Half Barrel #2 Assembly and Test |  |  |  |  | 2021-08-30 | 2021-12-13 |  |  | 13785 | 75859 |  | 26207 | 102066 |  |  | Budgeted Cost |  |  | 23138 | 52721
WBS: POM02B_3.02.03.03.01.03 Half Barrel #2 Assembly and Test |  |  |  |  | 2021-08-30 | 2021-12-13 |  |  | 13785 | 75859 |  | 26207 | 102066 |  |  | Budgeted Units |  |  | 3982 | 9804
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | CMMTECH4 LBNL | LBNL | 56 | 8181 | 0.4 | 3273 | 11454 | TECH | Labor | Budgeted Cost |  |  |  | 8181
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | CMMTECH4 LBNL | LBNL | 56 | 8181 | 0.4 | 3273 | 11454 | TECH | Labor | Budgeted Units |  |  |  | 56
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  |  | 40
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | POSTD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | POSTD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 80
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | GRSTUD LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | GRSTUD LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 40
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | ELENG3 LBNL | LBNL | 16 | 3070 | 0.4 | 1228 | 4298 | PROF | Labor | Budgeted Cost |  |  | 3070
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | ELENG3 LBNL | LBNL | 16 | 3070 | 0.4 | 1228 | 4298 | PROF | Labor | Budgeted Units |  |  | 16
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | MECHENG3 LBNL | LBNL | 40 | 6822 | 0.4 | 2729 | 9551 | PROF | Labor | Budgeted Cost |  |  | 6822
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | MECHENG3 LBNL | LBNL | 40 | 6822 | 0.4 | 2729 | 9551 | PROF | Labor | Budgeted Units |  |  | 40
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | ELTECH4 LBNL | LBNL | 32 | 4002 | 0.4 | 1601 | 5603 | TECH | Labor | Budgeted Cost |  |  | 4002
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | ELTECH4 LBNL | LBNL | 32 | 4002 | 0.4 | 1601 | 5603 | TECH | Labor | Budgeted Units |  |  | 32
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | POSTD LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | POSTD LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 160
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | STAFFPHYS LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | STAFFPHYS LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 80
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | GRSTUD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | GRSTUD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 80
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | ELENG3 LBNL | LBNL | 24 | 4708 | 0.4 | 1883 | 6592 | PROF | Labor | Budgeted Cost |  |  | 1177 | 3531
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | ELENG3 LBNL | LBNL | 24 | 4708 | 0.4 | 1883 | 6592 | PROF | Labor | Budgeted Units |  |  | 6 | 18
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | MECHENG3 LBNL | LBNL | 48 | 8371 | 0.4 | 3348 | 11719 | PROF | Labor | Budgeted Cost |  |  | 2093 | 6278
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | MECHENG3 LBNL | LBNL | 48 | 8371 | 0.4 | 3348 | 11719 | PROF | Labor | Budgeted Units |  |  | 12 | 36
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | ELTECH4 LBNL | LBNL | 48 | 6138 | 0.4 | 2455 | 8594 | TECH | Labor | Budgeted Cost |  |  | 1535 | 4604
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | ELTECH4 LBNL | LBNL | 48 | 6138 | 0.4 | 2455 | 8594 | TECH | Labor | Budgeted Units |  |  | 12 | 36
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | POSTD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | POSTD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 60 | 180
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | STAFFPHYS LBNL | LBNL | 79 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | STAFFPHYS LBNL | LBNL | 79 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 20 | 59
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | GRSTUD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | GRSTUD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 60 | 180
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | ELENG3 LBNL | LBNL | 16 | 3162 | 0.25 | 790 | 3952 | PROF | Labor | Budgeted Cost |  |  |  | 3162
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | ELENG3 LBNL | LBNL | 16 | 3162 | 0.25 | 790 | 3952 | PROF | Labor | Budgeted Units |  |  |  | 16
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | MECHENG3 LBNL | LBNL | 16 | 2811 | 0.25 | 703 | 3513 | PROF | Labor | Budgeted Cost |  |  |  | 2811
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | MECHENG3 LBNL | LBNL | 16 | 2811 | 0.25 | 703 | 3513 | PROF | Labor | Budgeted Units |  |  |  | 16
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | CMMTECH4 LBNL | LBNL | 24 | 3506 | 0.25 | 877 | 4383 | TECH | Labor | Budgeted Cost |  |  |  | 3506
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | CMMTECH4 LBNL | LBNL | 24 | 3506 | 0.25 | 877 | 4383 | TECH | Labor | Budgeted Units |  |  |  | 24
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | POSTD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | POSTD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 160
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | STAFFPHYS LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | STAFFPHYS LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  |  |  | 160
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | MECHTECH4 LBNL | LBNL | 32 | 4614 | 0.25 | 1153 | 5767 | TECH | Labor | Budgeted Cost |  |  |  | 4614
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | MECHTECH4 LBNL | LBNL | 32 | 4614 | 0.25 | 1153 | 5767 | TECH | Labor | Budgeted Units |  |  |  | 32
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | GRSTUD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | GRSTUD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 160
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | MECHENG3 LBNL | LBNL | 16 | 2740 | 0.25 | 685 | 3426 | PROF | Labor | Budgeted Cost |  |  |  | 2740
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | MECHENG3 LBNL | LBNL | 16 | 2740 | 0.25 | 685 | 3426 | PROF | Labor | Budgeted Units |  |  |  | 16
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | MECHTECH4 LBNL | LBNL | 16 | 2249 | 0.25 | 562 | 2812 | TECH | Labor | Budgeted Cost |  |  |  | 2249
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | MECHTECH4 LBNL | LBNL | 16 | 2249 | 0.25 | 562 | 2812 | TECH | Labor | Budgeted Units |  |  |  | 16
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | POSTD LBNL | LBNL | 120 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | POSTD LBNL | LBNL | 120 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 120
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Units |  |  |  | 24
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117300 | Assemble Layers and CYSS Into Half Barrel #2 - M&S | 2021-08-30 | 2021-09-23 | Purch 1st $2M sOL | OL | 2760 | 3589 | 0.4 | 1436 | 5025 |  | Nonlabor | Budgeted Cost |  |  | 3589
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117300 | Assemble Layers and CYSS Into Half Barrel #2 - M&S | 2021-08-30 | 2021-09-23 | Purch 1st $2M sOL | OL | 2760 | 3589 | 0.4 | 1436 | 5025 |  | Nonlabor | Budgeted Units |  |  | 2760
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117500 | Test and Rework Half Barrel #2 - M&S | 2021-09-24 | 2021-10-22 | Purch 1st $2M sOL | OL | 2576 | 3400 | 0.4 | 1360 | 4760 |  | Nonlabor | Budgeted Cost |  |  | 850 | 2550
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117500 | Test and Rework Half Barrel #2 - M&S | 2021-09-24 | 2021-10-22 | Purch 1st $2M sOL | OL | 2576 | 3400 | 0.4 | 1360 | 4760 |  | Nonlabor | Budgeted Units |  |  | 644 | 1932
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117800 | Validation Of Final Assembly - M&S | 2021-11-04 | 2021-11-29 | Purch 1st $2M sOL | OL | 2576 | 3417 | 0.25 | 854 | 4271 |  | Nonlabor | Budgeted Cost |  |  |  | 3417
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117800 | Validation Of Final Assembly - M&S | 2021-11-04 | 2021-11-29 | Purch 1st $2M sOL | OL | 2576 | 3417 | 0.25 | 854 | 4271 |  | Nonlabor | Budgeted Units |  |  |  | 2576
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118000 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - M&S | 2021-11-30 | 2021-12-13 | Purch 1st $2M sOL | OL | 3827 | 5077 | 0.25 | 1269 | 6346 |  | Nonlabor | Budgeted Cost |  |  |  | 5077
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118000 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - M&S | 2021-11-30 | 2021-12-13 | Purch 1st $2M sOL | OL | 3827 | 5077 | 0.25 | 1269 | 6346 |  | Nonlabor | Budgeted Units |  |  |  | 3827
WBS: POM02B_3.02.04 MVTX Integration and Infrastructure |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 333024 | 875460 |  | 267862 | 1141205 |  |  | Budgeted Cost | 3200 | 432765 | 424004 | 15491
WBS: POM02B_3.02.04 MVTX Integration and Infrastructure |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 333024 | 875460 |  | 267862 | 1141205 |  |  | Budgeted Units | 2560 | 86273 | 241073 | 3118
POM02B_3.02.04 | 02.04.01 | MVTX Integration and Infrastructure | S118900 | Clean Tent/Room - Delivery Acceptance | 2020-01-21 | 2020-01-27 | Purch 1st $2M sDOE | DOE | 50000 | 58084 | 0.1 | 5808 | 63892 |  | Nonlabor | Budgeted Cost |  | 58084
POM02B_3.02.04 | 02.04.01 | MVTX Integration and Infrastructure | S118900 | Clean Tent/Room - Delivery Acceptance | 2020-01-21 | 2020-01-27 | Purch 1st $2M sDOE | DOE | 50000 | 58084 | 0.1 | 5808 | 63892 |  | Nonlabor | Budgeted Units |  | 50000
WBS: POM02B_3.02.04.01 Cooling System |  |  |  |  | 2020-07-29 | 2021-03-08 |  |  | 87332 | 172233 |  | 54721 | 226954 |  |  | Budgeted Cost |  | 95919 | 76314
WBS: POM02B_3.02.04.01 Cooling System |  |  |  |  | 2020-07-29 | 2021-03-08 |  |  | 87332 | 172233 |  | 54721 | 226954 |  |  | Budgeted Units |  | 27800 | 59532
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119100 | Design Cooling (Modify ALICE Design) | 2020-07-29 | 2020-08-25 | PROF4 MIT | MIT | 80 | 13701 | 0.4 | 5481 | 19182 | PROF | Labor | Budgeted Cost |  | 13701
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119100 | Design Cooling (Modify ALICE Design) | 2020-07-29 | 2020-08-25 | PROF4 MIT | MIT | 80 | 13701 | 0.4 | 5481 | 19182 | PROF | Labor | Budgeted Units |  | 80
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119400 | Final Design of Cooling System | 2020-09-10 | 2020-09-16 | PROF4 MIT | MIT | 40 | 6851 | 0.4 | 2740 | 9591 | PROF | Labor | Budgeted Cost |  | 6851
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119400 | Final Design of Cooling System | 2020-09-10 | 2020-09-16 | PROF4 MIT | MIT | 40 | 6851 | 0.4 | 2740 | 9591 | PROF | Labor | Budgeted Units |  | 40
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119300 | Mock up Testing - Labor | 2020-08-26 | 2020-09-09 | TECH4 MIT | MIT | 60 | 7813 | 0.4 | 3125 | 10938 | TECH | Labor | Budgeted Cost |  | 7813
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119300 | Mock up Testing - Labor | 2020-08-26 | 2020-09-09 | TECH4 MIT | MIT | 60 | 7813 | 0.4 | 3125 | 10938 | TECH | Labor | Budgeted Units |  | 60
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119600 | Procure Cooling Plant - Labor | 2020-10-01 | 2021-03-01 | SCI3 MIT | MIT | 16 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119600 | Procure Cooling Plant - Labor | 2020-10-01 | 2021-03-01 | SCI3 MIT | MIT | 16 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 16
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119600 | Procure Cooling Plant - Labor | 2020-10-01 | 2021-03-01 | TECH4 MIT | MIT | 16 | 2146 | 0.4 | 858 | 3004 | TECH | Labor | Budgeted Cost |  |  | 2146
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119600 | Procure Cooling Plant - Labor | 2020-10-01 | 2021-03-01 | TECH4 MIT | MIT | 16 | 2146 | 0.4 | 858 | 3004 | TECH | Labor | Budgeted Units |  |  | 16
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119700 | Ship Cooling Plant to BNL | 2021-03-02 | 2021-03-08 | Purch 1st $2M MIT | OL | 2000 | 4147 | 0.1 | 415 | 4562 |  | Nonlabor | Budgeted Cost |  |  | 4147
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119700 | Ship Cooling Plant to BNL | 2021-03-02 | 2021-03-08 | Purch 1st $2M MIT | OL | 2000 | 4147 | 0.1 | 415 | 4562 |  | Nonlabor | Budgeted Units |  |  | 2000
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119100 | Design Cooling (Modify ALICE Design) | 2020-07-29 | 2020-08-25 | TECH4 MIT | MIT | 80 | 10417 | 0.4 | 4167 | 14584 | TECH | Labor | Budgeted Cost |  | 10417
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119100 | Design Cooling (Modify ALICE Design) | 2020-07-29 | 2020-08-25 | TECH4 MIT | MIT | 80 | 10417 | 0.4 | 4167 | 14584 | TECH | Labor | Budgeted Units |  | 80
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119200 | Mock up Testing - M&S | 2020-08-26 | 2020-09-09 | Purch 1st $2M MIT | DOE | 20000 | 40659 | 0.4 | 16263 | 56922 |  | Nonlabor | Budgeted Cost |  | 40659
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119200 | Mock up Testing - M&S | 2020-08-26 | 2020-09-09 | Purch 1st $2M MIT | DOE | 20000 | 40659 | 0.4 | 16263 | 56922 |  | Nonlabor | Budgeted Units |  | 20000
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119300 | Mock up Testing - Labor | 2020-08-26 | 2020-09-09 | PROF4 MIT | MIT | 40 | 6782 | 0.4 | 2713 | 9495 | PROF | Labor | Budgeted Cost |  | 6782
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119300 | Mock up Testing - Labor | 2020-08-26 | 2020-09-09 | PROF4 MIT | MIT | 40 | 6782 | 0.4 | 2713 | 9495 | PROF | Labor | Budgeted Units |  | 40
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119000 | Cooling System - MIT Travel | 2020-07-29 | 2021-03-08 | Purch 1st $2M sOL | OL | 25000 | 32321 | 0 | 0 | 32321 |  | Nonlabor | Budgeted Cost |  | 9696 | 22625
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119000 | Cooling System - MIT Travel | 2020-07-29 | 2021-03-08 | Purch 1st $2M sOL | OL | 25000 | 32321 | 0 | 0 | 32321 |  | Nonlabor | Budgeted Units |  | 7500 | 17500
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119500 | Procure Cooling Plant - M&S | 2020-10-01 | 2020-10-01 | Purch 1st $2M sDOE | DOE | 40000 | 47396 | 0.4 | 18958 | 66355 |  | Nonlabor | Budgeted Cost |  |  | 47396
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119500 | Procure Cooling Plant - M&S | 2020-10-01 | 2020-10-01 | Purch 1st $2M sDOE | DOE | 40000 | 47396 | 0.4 | 18958 | 66355 |  | Nonlabor | Budgeted Units |  |  | 40000
WBS: POM02B_3.02.04.02 Safety Systems |  |  |  |  | 2020-09-17 | 2021-04-12 |  |  | 36234 | 154057 |  | 37743 | 189683 |  |  | Budgeted Cost |  | 9170 | 144887
WBS: POM02B_3.02.04.02 Safety Systems |  |  |  |  | 2020-09-17 | 2021-04-12 |  |  | 36234 | 154057 |  | 37743 | 189683 |  |  | Budgeted Units |  | 1906 | 34329
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119900 | Define MVTX Safety and Interlock requirements | 2020-09-17 | 2020-09-30 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119900 | Define MVTX Safety and Interlock requirements | 2020-09-17 | 2020-09-30 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  | 40
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119900 | Define MVTX Safety and Interlock requirements | 2020-09-17 | 2020-09-30 | POSTD LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119900 | Define MVTX Safety and Interlock requirements | 2020-09-17 | 2020-09-30 | POSTD LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  | 40
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119900 | Define MVTX Safety and Interlock requirements | 2020-09-17 | 2020-09-30 | PROF4 MIT | MIT | 40 | 6851 | 0.4 | 2740 | 9591 | PROF | Labor | Budgeted Cost |  | 6851
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119900 | Define MVTX Safety and Interlock requirements | 2020-09-17 | 2020-09-30 | PROF4 MIT | MIT | 40 | 6851 | 0.4 | 2740 | 9591 | PROF | Labor | Budgeted Units |  | 40
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120000 | Review Sensors & Interlocks with BNL ES&H | 2020-10-01 | 2020-10-15 | PROF4 MIT | MIT | 40 | 7056 | 0.05 | 353 | 7409 | PROF | Labor | Budgeted Cost |  |  | 7056
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120000 | Review Sensors & Interlocks with BNL ES&H | 2020-10-01 | 2020-10-15 | PROF4 MIT | MIT | 40 | 7056 | 0.05 | 353 | 7409 | PROF | Labor | Budgeted Units |  |  | 40
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120000 | Review Sensors & Interlocks with BNL ES&H | 2020-10-01 | 2020-10-15 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120000 | Review Sensors & Interlocks with BNL ES&H | 2020-10-01 | 2020-10-15 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 40
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120100 | Design Electronics Safety System | 2020-10-16 | 2020-11-13 | STAFFPHYS LBNL | LBNL | 103 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120100 | Design Electronics Safety System | 2020-10-16 | 2020-11-13 | STAFFPHYS LBNL | LBNL | 103 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 103
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120100 | Design Electronics Safety System | 2020-10-16 | 2020-11-13 | POSTD LBNL | LBNL | 103 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120100 | Design Electronics Safety System | 2020-10-16 | 2020-11-13 | POSTD LBNL | LBNL | 103 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Units |  |  | 103
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120100 | Design Electronics Safety System | 2020-10-16 | 2020-11-13 | PROF4 MIT | MIT | 82 | 14516 | 0.4 | 5807 | 20323 | PROF | Labor | Budgeted Cost |  |  | 14516
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120100 | Design Electronics Safety System | 2020-10-16 | 2020-11-13 | PROF4 MIT | MIT | 82 | 14516 | 0.4 | 5807 | 20323 | PROF | Labor | Budgeted Units |  |  | 82
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120200 | Design Cooling Interlocks | 2020-11-16 | 2020-12-30 | PROF4 MIT | MIT | 120 | 21169 | 0.4 | 8467 | 29636 | PROF | Labor | Budgeted Cost |  |  | 21169
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120200 | Design Cooling Interlocks | 2020-11-16 | 2020-12-30 | PROF4 MIT | MIT | 120 | 21169 | 0.4 | 8467 | 29636 | PROF | Labor | Budgeted Units |  |  | 120
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120500 | Test Safety Systems at MIT | 2021-03-02 | 2021-03-22 | TECH4 MIT | MIT | 120 | 16094 | 0.4 | 6438 | 22532 | TECH | Labor | Budgeted Cost |  |  | 16094
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120500 | Test Safety Systems at MIT | 2021-03-02 | 2021-03-22 | TECH4 MIT | MIT | 120 | 16094 | 0.4 | 6438 | 22532 | TECH | Labor | Budgeted Units |  |  | 120
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120500 | Test Safety Systems at MIT | 2021-03-02 | 2021-03-22 | PROF4 MIT | MIT | 41 | 7197 | 0.4 | 2879 | 10076 | PROF | Labor | Budgeted Cost |  |  | 7197
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120500 | Test Safety Systems at MIT | 2021-03-02 | 2021-03-22 | PROF4 MIT | MIT | 41 | 7197 | 0.4 | 2879 | 10076 | PROF | Labor | Budgeted Units |  |  | 41
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120700 | Test Safety Systems at BNL | 2021-03-30 | 2021-04-12 | TECH4 MIT | MIT | 80 | 10729 | 0.1 | 1073 | 11802 | TECH | Labor | Budgeted Cost |  |  | 10729
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120700 | Test Safety Systems at BNL | 2021-03-30 | 2021-04-12 | TECH4 MIT | MIT | 80 | 10729 | 0.1 | 1073 | 11802 | TECH | Labor | Budgeted Units |  |  | 80
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120700 | Test Safety Systems at BNL | 2021-03-30 | 2021-04-12 | PROF4 MIT | MIT | 80 | 14112 | 0.1 | 1411 | 15524 | PROF | Labor | Budgeted Cost |  |  | 14112
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120700 | Test Safety Systems at BNL | 2021-03-30 | 2021-04-12 | PROF4 MIT | MIT | 80 | 14112 | 0.1 | 1411 | 15524 | PROF | Labor | Budgeted Units |  |  | 80
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120400 | Procure Safety Systems - Labor | 2020-12-31 | 2021-03-01 | TECH4 MIT | MIT | 16 | 2146 | 0.4 | 858 | 3004 | TECH | Labor | Budgeted Cost |  |  | 2146
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120400 | Procure Safety Systems - Labor | 2020-12-31 | 2021-03-01 | TECH4 MIT | MIT | 16 | 2146 | 0.4 | 858 | 3004 | TECH | Labor | Budgeted Units |  |  | 16
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120400 | Procure Safety Systems - Labor | 2020-12-31 | 2021-03-01 | PROF4 MIT | MIT | 42 | 7338 | 0.4 | 2935 | 10274 | PROF | Labor | Budgeted Cost |  |  | 7338
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120400 | Procure Safety Systems - Labor | 2020-12-31 | 2021-03-01 | PROF4 MIT | MIT | 42 | 7338 | 0.4 | 2935 | 10274 | PROF | Labor | Budgeted Units |  |  | 42
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120600 | Ship Safety Systems to BNL | 2021-03-23 | 2021-03-29 | Purch 1st $2M MIT | OL | 200 | 415 | 0.1 | 41 | 456 |  | Nonlabor | Budgeted Cost |  |  | 415
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120600 | Ship Safety Systems to BNL | 2021-03-23 | 2021-03-29 | Purch 1st $2M MIT | OL | 200 | 415 | 0.1 | 41 | 456 |  | Nonlabor | Budgeted Units |  |  | 200
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119800 | Safety Systems - MIT Travel | 2020-09-17 | 2021-04-12 | Purch 1st $2M sOL | OL | 25000 | 32467 | 0 | 0 | 32467 |  | Nonlabor | Budgeted Cost |  | 2319 | 30148
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119800 | Safety Systems - MIT Travel | 2020-09-17 | 2021-04-12 | Purch 1st $2M sOL | OL | 25000 | 32467 | 0 | 0 | 32467 |  | Nonlabor | Budgeted Units |  | 1786 | 23214
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120300 | Procure Safety Systems - M&S | 2020-12-31 | 2021-03-01 | Purch 1st $2M sDOE | DOE | 10000 | 11849 | 0.4 | 4740 | 16589 |  | Nonlabor | Budgeted Cost |  |  | 11849
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120300 | Procure Safety Systems - M&S | 2020-12-31 | 2021-03-01 | Purch 1st $2M sDOE | DOE | 10000 | 11849 | 0.4 | 4740 | 16589 |  | Nonlabor | Budgeted Units |  |  | 10000
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | SCI3 MIT |  | 12 | 0 |  |  |  | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | SCI3 MIT |  | 12 | 0 |  |  |  | SCI | Labor | Budgeted Units |  |  | 12
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | STAFFPHYS LBNL |  | 12 | 0 |  |  |  | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | STAFFPHYS LBNL |  | 12 | 0 |  |  |  | SCI | Labor | Budgeted Units |  |  | 12
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | SCI3 LANL |  | 12 | 0 |  |  |  | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | SCI3 LANL |  | 12 | 0 |  |  |  | SCI | Labor | Budgeted Units |  |  | 12
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | PROF4 MIT |  | 12 | 2117 |  |  |  | PROF | Labor | Budgeted Cost |  |  | 2117
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | PROF4 MIT |  | 12 | 2117 |  |  |  | PROF | Labor | Budgeted Units |  |  | 12
WBS: POM02B_3.02.04.03 Service Barrel Support Frame & MVTX Interface to sPHENIX |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 158282 | 431797 |  | 163661 | 595458 |  |  | Budgeted Cost | 3200 | 240526 | 185017 | 3054
WBS: POM02B_3.02.04.03 Service Barrel Support Frame & MVTX Interface to sPHENIX |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 158282 | 431797 |  | 163661 | 595458 |  |  | Budgeted Units | 2560 | 6368 | 147052 | 2302
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122700 | Procure Insertion System - Delivery Acceptance | 2021-02-16 | 2021-02-22 | Purch 1st $2M sDOE | DOE | 40000 | 47396 | 0.4 | 18958 | 66355 |  | Nonlabor | Budgeted Cost |  |  | 47396
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122700 | Procure Insertion System - Delivery Acceptance | 2021-02-16 | 2021-02-22 | Purch 1st $2M sDOE | DOE | 40000 | 47396 | 0.4 | 18958 | 66355 |  | Nonlabor | Budgeted Units |  |  | 40000
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122800 | ship to BNL - M&S | 2021-02-23 | 2021-03-01 | Purch 1st $2M MIT | OL | 2000 | 4147 | 0.1 | 415 | 4562 |  | Nonlabor | Budgeted Cost |  |  | 4147
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122800 | ship to BNL - M&S | 2021-02-23 | 2021-03-01 | Purch 1st $2M MIT | OL | 2000 | 4147 | 0.1 | 415 | 4562 |  | Nonlabor | Budgeted Units |  |  | 2000
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S120800 | Travel FY19 | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 2560 | 3200 | 0 | 0 | 3200 |  | Nonlabor | Budgeted Cost | 3200
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S120800 | Travel FY19 | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 2560 | 3200 | 0 | 0 | 3200 |  | Nonlabor | Budgeted Units | 2560
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121000 | Travel FY20 | 2019-10-01 | 2020-09-30 | Purch 1st $2M sOL | OL | 5000 | 6375 | 0 | 0 | 6375 |  | Nonlabor | Budgeted Cost |  | 6375
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121000 | Travel FY20 | 2019-10-01 | 2020-09-30 | Purch 1st $2M sOL | OL | 5000 | 6375 | 0 | 0 | 6375 |  | Nonlabor | Budgeted Units |  | 5000
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122000 | Travel FY21 | 2020-10-01 | 2021-09-30 | Purch 1st $2M sOL | OL | 5000 | 6503 | 0 | 0 | 6503 |  | Nonlabor | Budgeted Cost |  |  | 6503
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122000 | Travel FY21 | 2020-10-01 | 2021-09-30 | Purch 1st $2M sOL | OL | 5000 | 6503 | 0 | 0 | 6503 |  | Nonlabor | Budgeted Units |  |  | 5000
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S123000 | Travel FY22 | 2021-10-01 | 2022-03-17 | Purch 1st $2M sOL | OL | 2302 | 3054 | 0 | 0 | 3054 |  | Nonlabor | Budgeted Cost |  |  |  | 3054
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S123000 | Travel FY22 | 2021-10-01 | 2022-03-17 | Purch 1st $2M sOL | OL | 2302 | 3054 | 0 | 0 | 3054 |  | Nonlabor | Budgeted Units |  |  |  | 2302
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S120900 | Design Interface to sPHENIX | 2019-12-24 | 2020-06-22 | PROF4 MIT | MIT | 1000 | 171268 | 0.4 | 68507 | 239775 | PROF | Labor | Budgeted Cost |  | 171268
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S120900 | Design Interface to sPHENIX | 2019-12-24 | 2020-06-22 | PROF4 MIT | MIT | 1000 | 171268 | 0.4 | 68507 | 239775 | PROF | Labor | Budgeted Units |  | 1000
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121800 | Design Insertion System | 2020-07-29 | 2020-10-07 | PROF4 MIT | MIT | 400 | 68713 | 0.4 | 27485 | 96198 | PROF | Labor | Budgeted Cost |  | 61841 | 6871
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121800 | Design Insertion System | 2020-07-29 | 2020-10-07 | PROF4 MIT | MIT | 400 | 68713 | 0.4 | 27485 | 96198 | PROF | Labor | Budgeted Units |  | 360 | 40
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122900 | ship to BNL - Labor | 2021-02-23 | 2021-03-01 | TECH4 MIT | MIT | 4 | 536 | 0.1 | 54 | 590 | TECH | Labor | Budgeted Cost |  |  | 536
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122900 | ship to BNL - Labor | 2021-02-23 | 2021-03-01 | TECH4 MIT | MIT | 4 | 536 | 0.1 | 54 | 590 | TECH | Labor | Budgeted Units |  |  | 4
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121100 | Procure Support Structure -Provide Requirements to Procurement | 2020-07-29 | 2020-08-04 | TECH4 MIT | MIT | 8 | 1042 | 0.4 | 417 | 1458 | TECH | Labor | Budgeted Cost |  | 1042
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121100 | Procure Support Structure -Provide Requirements to Procurement | 2020-07-29 | 2020-08-04 | TECH4 MIT | MIT | 8 | 1042 | 0.4 | 417 | 1458 | TECH | Labor | Budgeted Units |  | 8
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122100 | Procure Insertion System -Provide Requirements to Procurement | 2020-10-08 | 2020-10-15 | TECH4 MIT | MIT | 8 | 1073 | 0.4 | 429 | 1502 | TECH | Labor | Budgeted Cost |  |  | 1073
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122100 | Procure Insertion System -Provide Requirements to Procurement | 2020-10-08 | 2020-10-15 | TECH4 MIT | MIT | 8 | 1073 | 0.4 | 429 | 1502 | TECH | Labor | Budgeted Units |  |  | 8
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121700 | Procure Support Structure - Delivery Acceptance | 2020-12-02 | 2020-12-02 | Purch 1st $2M sDOE | DOE | 100000 | 118490 | 0.4 | 47396 | 165887 |  | Nonlabor | Budgeted Cost |  |  | 118490
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121700 | Procure Support Structure - Delivery Acceptance | 2020-12-02 | 2020-12-02 | Purch 1st $2M sDOE | DOE | 100000 | 118490 | 0.4 | 47396 | 165887 |  | Nonlabor | Budgeted Units |  |  | 100000
WBS: POM02B_3.02.04.04 Half detector Assembly Readout and Cooling Test at BNL |  |  |  |  | 2020-04-24 | 2022-03-17 |  |  | 1176 | 59290 |  | 5929 | 65219 |  |  | Budgeted Cost |  | 29067 | 17786 | 12437
WBS: POM02B_3.02.04.04 Half detector Assembly Readout and Cooling Test at BNL |  |  |  |  | 2020-04-24 | 2022-03-17 |  |  | 1176 | 59290 |  | 5929 | 65219 |  |  | Budgeted Units |  | 200 | 160 | 816
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123500 | Test Half Barrel #1 | 2021-12-06 | 2021-12-27 | MECHENG4 LBNL | LBNL | 24 | 6219 | 0.1 | 622 | 6840 | PROF | Labor | Budgeted Cost |  |  |  | 6219
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123500 | Test Half Barrel #1 | 2021-12-06 | 2021-12-27 | MECHENG4 LBNL | LBNL | 24 | 6219 | 0.1 | 622 | 6840 | PROF | Labor | Budgeted Units |  |  |  | 24
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123500 | Test Half Barrel #1 | 2021-12-06 | 2021-12-27 | POSTD LBNL | LBNL | 120 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123500 | Test Half Barrel #1 | 2021-12-06 | 2021-12-27 | POSTD LBNL | LBNL | 120 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 120
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123500 | Test Half Barrel #1 | 2021-12-06 | 2021-12-27 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123500 | Test Half Barrel #1 | 2021-12-06 | 2021-12-27 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units |  |  |  | 24
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123600 | Test Half Barrel #2 | 2021-12-28 | 2022-01-19 | MECHENG4 LBNL | LBNL | 24 | 6219 | 0.1 | 622 | 6840 | PROF | Labor | Budgeted Cost |  |  |  | 6219
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123600 | Test Half Barrel #2 | 2021-12-28 | 2022-01-19 | MECHENG4 LBNL | LBNL | 24 | 6219 | 0.1 | 622 | 6840 | PROF | Labor | Budgeted Units |  |  |  | 24
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123600 | Test Half Barrel #2 | 2021-12-28 | 2022-01-19 | POSTD LBNL | LBNL | 120 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123600 | Test Half Barrel #2 | 2021-12-28 | 2022-01-19 | POSTD LBNL | LBNL | 120 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Units |  |  |  | 120
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123600 | Test Half Barrel #2 | 2021-12-28 | 2022-01-19 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123600 | Test Half Barrel #2 | 2021-12-28 | 2022-01-19 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units |  |  |  | 24
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | TECH4 MIT | MIT | 80 | 10729 | 0.1 | 1073 | 11802 | TECH | Labor | Budgeted Cost |  |  | 10729
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | TECH4 MIT | MIT | 80 | 10729 | 0.1 | 1073 | 11802 | TECH | Labor | Budgeted Units |  |  | 80
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | SCI3 MIT | MIT | 40 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | SCI3 MIT | MIT | 40 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units |  |  | 40
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123700 | MVTX Full System Test at BNL | 2022-01-20 | 2022-03-17 | SCI3 LANL | LANL | 480 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123700 | MVTX Full System Test at BNL | 2022-01-20 | 2022-03-17 | SCI3 LANL | LANL | 480 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units |  |  |  | 480
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123100 | Test RU at BNL | 2020-09-16 | 2020-09-29 | SCI3 LANL | LANL | 32 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123100 | Test RU at BNL | 2020-09-16 | 2020-09-29 | SCI3 LANL | LANL | 32 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units |  | 32
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123100 | Test RU at BNL | 2020-09-16 | 2020-09-29 | PROF4 LANL | LANL | 32 | 10069 | 0.1 | 1007 | 11075 | PROF | Labor | Budgeted Cost |  | 10069
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123100 | Test RU at BNL | 2020-09-16 | 2020-09-29 | PROF4 LANL | LANL | 32 | 10069 | 0.1 | 1007 | 11075 | PROF | Labor | Budgeted Units |  | 32
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123200 | Test FELIX at BNL | 2020-06-23 | 2020-07-07 | SCI3 LANL | LANL | 32 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123200 | Test FELIX at BNL | 2020-06-23 | 2020-07-07 | SCI3 LANL | LANL | 32 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Units |  | 32
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123200 | Test FELIX at BNL | 2020-06-23 | 2020-07-07 | PROF4 LANL | LANL | 32 | 10069 | 0.1 | 1007 | 11075 | PROF | Labor | Budgeted Cost |  | 10069
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123200 | Test FELIX at BNL | 2020-06-23 | 2020-07-07 | PROF4 LANL | LANL | 32 | 10069 | 0.1 | 1007 | 11075 | PROF | Labor | Budgeted Units |  | 32
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123300 | Test PS at BNL | 2020-04-24 | 2020-05-07 | POSTD LBNL | LBNL | 20 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123300 | Test PS at BNL | 2020-04-24 | 2020-05-07 | POSTD LBNL | LBNL | 20 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Units |  | 20
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123300 | Test PS at BNL | 2020-04-24 | 2020-05-07 | ELENG3 LBNL | LBNL | 20 | 3726 | 0.1 | 373 | 4098 | PROF | Labor | Budgeted Cost |  | 3726
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123300 | Test PS at BNL | 2020-04-24 | 2020-05-07 | ELENG3 LBNL | LBNL | 20 | 3726 | 0.1 | 373 | 4098 | PROF | Labor | Budgeted Units |  | 20
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123100 | Test RU at BNL | 2020-09-16 | 2020-09-29 | ElectEng UTAustin | UTAustin | 16 | 2602 | 0.1 | 260 | 2862 | PROF | Labor | Budgeted Cost |  | 2602
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123100 | Test RU at BNL | 2020-09-16 | 2020-09-29 | ElectEng UTAustin | UTAustin | 16 | 2602 | 0.1 | 260 | 2862 | PROF | Labor | Budgeted Units |  | 16
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123200 | Test FELIX at BNL | 2020-06-23 | 2020-07-07 | ElectEng UTAustin | UTAustin | 16 | 2602 | 0.1 | 260 | 2862 | PROF | Labor | Budgeted Cost |  | 2602
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123200 | Test FELIX at BNL | 2020-06-23 | 2020-07-07 | ElectEng UTAustin | UTAustin | 16 | 2602 | 0.1 | 260 | 2862 | PROF | Labor | Budgeted Units |  | 16
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | PROF4 MIT | MIT | 40 | 7056 | 0.1 | 706 | 7762 | PROF | Labor | Budgeted Cost |  |  | 7056
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | PROF4 MIT | MIT | 40 | 7056 | 0.1 | 706 | 7762 | PROF | Labor | Budgeted Units |  |  | 40
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | PROF4 MIT | MIT | 40 | 7056 | 0.1 | 706 | 7762 | PROF | Labor | Budgeted Cost |  |  | 7056
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | PROF4 MIT | MIT | 40 | 7056 | 0.1 | 706 | 7762 | PROF | Labor | Budgeted Units |  |  | 40

## Aug 14
WBS | BNL_WBS_Hierarchical | WBS Name | Activity ID | Activity Name | Start | Finish | Resource ID | BNL_RAU_Institution | Budgeted Units | Budgeted Cost | EU Factor | EU $ of Burd Esc | Burd $ Esc w EU | sPHENIX Resource Category | Resource Type | Spreadsheet Field | FY19 | FY20 | FY21 | FY22
Project: POM02B_3 POM02 sPHENIX WBS 3.02 Preliminary Baseline [MVTX] |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 1211867 | 3690618 | 81.45 | 985666 | 4676283 |  |  | Budgeted Cost | 181258 | 2360904 | 918158 | 230297
WBS: POM02B_3.02 MVTX |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 1211867 | 3690618 | 81.45 | 985666 | 4676283 |  |  | Budgeted Cost | 181258 | 2360904 | 918158 | 230297
WBS: POM02B_3.02.01 MVTX Project Management |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 37798 | 544602 | 0 | 0 | 544602 |  |  | Budgeted Cost | 23540 | 210128 | 209596 | 101338
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100600 | Project Manager | 2019-09-03 | 2022-03-17 | MGR LANL | LANL | 1238 | 398112 | 0 | 0 | 398112 | MGR | Labor | Budgeted Cost | 12579 | 157861 | 157232 | 70440
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100700 | Mechanical Integration Engineer | 2019-09-03 | 2022-03-17 | PROF4 LANL | LANL | 310 | 99657 | 0 | 0 | 99657 | PROF | Labor | Budgeted Cost | 3149 | 39516 | 39359 | 17633
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100800 | Electronics Integration Engineer | 2019-09-03 | 2022-03-17 | PROF4 LANL | LANL | 0 | 0 | 0 | 0 | 0 | PROF | Labor | Budgeted Cost
POM02B_3.02.01 | 2.01 | MVTX Project Management | S100900 | Travel FY19 | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 6250 | 7813 | 0 | 0 | 7813 |  | Nonlabor | Budgeted Cost | 7813
POM02B_3.02.01 | 2.01 | MVTX Project Management | S101100 | Travel FY20 | 2019-10-01 | 2020-09-30 | Purch 1st $2M sOL | OL | 10000 | 12750 | 0 | 0 | 12750 |  | Nonlabor | Budgeted Cost |  | 12750
POM02B_3.02.01 | 2.01 | MVTX Project Management | S101200 | Travel FY21 | 2020-10-01 | 2021-09-30 | Purch 1st $2M sOL | OL | 10000 | 13005 | 0 | 0 | 13005 |  | Nonlabor | Budgeted Cost |  |  | 13005
POM02B_3.02.01 | 2.01 | MVTX Project Management | S101300 | Travel FY22 | 2021-10-01 | 2022-03-17 | Purch 1st $2M sOL | OL | 10000 | 13265 | 0 | 0 | 13265 |  | Nonlabor | Budgeted Cost |  |  |  | 13265
WBS: POM02B_3.02.02 MVTX Electronics |  |  |  |  | 2019-09-03 | 2020-09-15 |  |  | 303491 | 569582 | 11.15 | 101642 | 671224 |  |  | Budgeted Cost | 41687 | 527895
WBS: POM02B_3.02.02.01 Readout Unit (RU) |  |  |  |  | 2019-10-30 | 2020-09-15 |  |  | 70010 | 213002 | 2.6 | 27867 | 240870 |  |  | Budgeted Cost |  | 213002
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101900 | Test/QA RU - Labor | 2019-12-02 | 2020-01-29 | SCI3 LANL | LANL | 100 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101900 | Test/QA RU - Labor | 2019-12-02 | 2020-01-29 | ElectTech UTAustin | UTAustin | 320 | 33784 | 0.1 | 3378 | 37163 | TECH | Labor | Budgeted Cost |  | 33784
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102100 | Procure 60 SamTec Cables -Provide Requirements to Procurement | 2020-01-30 | 2020-02-05 | TECH4 LANL | LANL | 5 | 950 | 0.1 | 95 | 1045 | TECH | Labor | Budgeted Cost |  | 950
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102800 | Test/QA SamTec Cables Check if still needed | 2020-07-07 | 2020-08-31 | SCI3 LANL | LANL | 320 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102800 | Test/QA SamTec Cables Check if still needed | 2020-07-07 | 2020-08-31 | ElectTech UTAustin | UTAustin | 320 | 33784 | 0.1 | 3378 | 37163 | TECH | Labor | Budgeted Cost |  | 33784
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102700 | Procure 60 SamTec Cables - Delivery Acceptance | 2020-06-29 | 2020-07-06 | Purch 1st $2M sDOE | DOE | 30000 | 34850 | 0.1 | 3485 | 38335 |  | Nonlabor | Budgeted Cost |  | 34850
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102900 | Ship RU & SamTec Cables from CERN to UT Austin | 2020-09-01 | 2020-09-08 | Purch 1st $2M sOL | OL | 2000 | 2550 | 0.1 | 255 | 2805 |  | Nonlabor | Budgeted Cost |  | 2550
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101800 | Procure Power Mezzanine for RU M&S | 2019-10-30 | 2019-11-13 | Purch 1st $2M sOL | OL | 4757 | 6065 | 0.25 | 1516 | 7581 |  | Nonlabor | Budgeted Cost |  | 6065
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102800 | Test/QA SamTec Cables Check if still needed | 2020-07-07 | 2020-08-31 | ElectEng UTAustin | UTAustin | 320 | 52043 | 0.1 | 5204 | 57247 | PROF | Labor | Budgeted Cost |  | 52043
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101500 | Produce RU Cold Plate - Labor | 2019-10-30 | 2019-11-27 | ElectTech UTAustin | UTAustin | 60 | 6335 | 0.25 | 1584 | 7918 | TECH | Labor | Budgeted Cost |  | 6335
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101600 | Procure Transition Board for RU M&S | 2019-10-30 | 2019-11-13 | Purch 1st $2M sOL | OL | 7935 | 10117 | 0.25 | 2529 | 12646 |  | Nonlabor | Budgeted Cost |  | 10117
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101700 | Produce RU Cold Plate - M&S | 2019-10-30 | 2019-11-27 | Purch 1st $2M sOL | OL | 15353 | 19575 | 0.25 | 4894 | 24469 |  | Nonlabor | Budgeted Cost |  | 19575
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102000 | Test/QA RU - M&S | 2019-12-02 | 2020-01-29 | Purch 1st $2M sOL | OL | 7500 | 9563 | 0.1 | 956 | 10519 |  | Nonlabor | Budgeted Cost |  | 9563
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101601 | Procure Transition Board for RU Labor | 2019-10-30 | 2019-11-13 | ElectTech UTAustin | UTAustin | 8 | 845 | 0.25 | 211 | 1056 | TECH | Labor | Budgeted Cost |  | 845
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S101801 | Procure Power Mezzanine for RU Labor | 2019-10-30 | 2019-11-13 | ElectTech UTAustin | UTAustin | 8 | 845 | 0.25 | 211 | 1056 | TECH | Labor | Budgeted Cost |  | 845
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102902 | Ship RU & SamTec Cables from UT Austin to BNL M&S | 2020-09-09 | 2020-09-15 | Purch 1st $2M sOL | OL | 1000 | 1275 | 0.1 | 128 | 1403 |  | Nonlabor | Budgeted Cost |  | 1275
POM02B_3.02.02.01 | 02.02.01 | Readout Unit (RU) | S102901 | Ship RU & SamTec Cables from UT Austin to BNL Labor | 2020-09-09 | 2020-09-15 | ElectTech UTAustin | UTAustin | 4 | 422 | 0.1 | 42 | 465 | TECH | Labor | Budgeted Cost |  | 422
WBS: POM02B_3.02.02.02 FELIX 2.0 |  |  |  |  | 2019-09-03 | 2020-06-22 |  |  | 76595 | 110571 | 3.35 | 27260 | 137832 |  |  | Budgeted Cost | 4692 | 105879
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103000 | Produce Felix 2.0 first production unit - Labor | 2019-09-03 | 2019-11-22 | TECH4 LANL | LANL | 16 | 3133 | 0.25 | 783 | 3916 | TECH | Labor | Budgeted Cost | 1099 | 2034
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103100 | Procure Optical Fiber - Labor | 2019-09-03 | 2019-09-30 | TECH4 LANL | LANL | 2 | 307 | 0.25 | 77 | 384 | TECH | Labor | Budgeted Cost | 307
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103400 | Test/QA 1st Felix Unit and Fibers | 2019-11-25 | 2019-12-10 | SCI3 LANL | LANL | 40 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103500 | Procure 7 Felix 2.0 Remaining Units -Provide Requirements to Procurement | 2020-03-18 | 2020-03-24 | TECH4 LANL | LANL | 6 | 1266 | 0.25 | 317 | 1583 | TECH | Labor | Budgeted Cost |  | 1266
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103450 | Procure 57 Optical Fiber Sets - Labor | 2020-03-18 | 2020-04-14 | TECH4 LANL | LANL | 2 | 317 | 0.25 | 79 | 396 | TECH | Labor | Budgeted Cost |  | 317
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104400 | Test/QA 7 Felix Units and Fibers - Labor | 2020-06-02 | 2020-06-15 | SCI3 LANL | LANL | 43 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104400 | Test/QA 7 Felix Units and Fibers - Labor | 2020-06-02 | 2020-06-15 | TECH4 LANL | LANL | 43 | 8507 | 0.25 | 2127 | 10633 | TECH | Labor | Budgeted Cost |  | 8507
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103002 | Produce Felix 2.0 first production unit - M&S | 2019-09-03 | 2019-11-22 | Purch 1st $2M sDOE | DOE | 8000 | 9186 | 0.25 | 2297 | 11483 |  | Nonlabor | Budgeted Cost | 3223 | 5963
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104300 | Procure 7 Felix 2.0 Remaining Units - Delivery Acceptance | 2020-05-26 | 2020-06-01 | Purch 1st $2M sDOE | DOE | 56000 | 65054 | 0.25 | 16263 | 81317 |  | Nonlabor | Budgeted Cost |  | 65054
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104600 | Ship Felix Units and Fibers to BNL | 2020-06-16 | 2020-06-22 | Purch 1st $2M sOL | OL | 2000 | 2550 | 0.1 | 255 | 2805 |  | Nonlabor | Budgeted Cost |  | 2550
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103300 | Procure Optical Fiber - M&S | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 50 | 63 | 0.25 | 16 | 78 |  | Nonlabor | Budgeted Cost | 63
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S103460 | Procure 57 Optical Fiber Sets M&S | 2020-03-18 | 2020-04-14 | Purch 1st $2M sOL | OL | 2850 | 3634 | 0.25 | 908 | 4542 |  | Nonlabor | Budgeted Cost |  | 3634
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104400 | Test/QA 7 Felix Units and Fibers - Labor | 2020-06-02 | 2020-06-15 | ElectEng UTAustin | UTAustin | 43 | 6993 | 0.25 | 1748 | 8742 | PROF | Labor | Budgeted Cost |  | 6993
POM02B_3.02.02.02 | 02.02.02 | FELIX 2.0 | S104500 | Test/QA 7 Felix Units and Fibers - M&S | 2020-06-02 | 2020-06-15 | Purch 1st $2M sOL | OL | 7500 | 9563 | 0.25 | 2391 | 11953 |  | Nonlabor | Budgeted Cost |  | 9563
WBS: POM02B_3.02.02.03 MAPS Power System |  |  |  |  | 2019-09-03 | 2020-04-23 |  |  | 156887 | 246009 | 5.2 | 46514 | 292523 |  |  | Budgeted Cost | 36995 | 209013
WBS: POM02B_3.02.02.03.01 Power Boards |  |  |  |  | 2019-09-03 | 2020-04-16 |  |  | 79452 | 144329 | 3.65 | 33705 | 178034 |  |  | Budgeted Cost | 28783 | 115546
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106730 | Test PB - Labor | 2020-02-21 | 2020-03-19 | ELTECH4 LBNL | LBNL | 90 | 10928 | 0.1 | 1093 | 12021 | TECH | Labor | Budgeted Cost |  | 10928
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | ELENG3 LBNL | LBNL | 42 | 7749 | 0.25 | 1937 | 9686 | PROF | Labor | Budgeted Cost |  | 7749
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | POSTD LBNL | LBNL | 18 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | STAFFPHYS LBNL | LBNL | 18 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106160 | Procure Production PB -Provide Requirements to Procurement | 2019-10-01 | 2019-10-07 | ELTECH4 LBNL | LBNL | 9 | 1122 | 0.25 | 280 | 1402 | TECH | Labor | Budgeted Cost |  | 1122
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106700 | Procure Production PB - Delivery Acceptance | 2020-02-06 | 2020-02-12 | Purch 1st $2M sDOE | DOE | 60000 | 69700 | 0.25 | 17425 | 87125 |  | Nonlabor | Budgeted Cost |  | 69700
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105700 | Fabricate Break Out Boards (qty?) - M&S | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 6600 | 8250 | 0.25 | 2063 | 10313 |  | Nonlabor | Budgeted Cost | 8250
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105800 | Fabricate PB to Stave Cables - M&S | 2019-10-01 | 2019-10-29 | Purch 1st $2M sOL | OL | 8000 | 10200 | 0.25 | 2550 | 12750 |  | Nonlabor | Budgeted Cost |  | 10200
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105100 | Procure Power Distribution (harness) - M&S | 2019-09-03 | 2019-09-27 | Purch 1st $2M sOL | OL | 0 | 0 | 0.25 | 0 | 0 |  | Nonlabor | Budgeted Cost
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106770 | Test PB - M&S | 2020-02-21 | 2020-03-19 | Purch 1st $2M sOL | OL | 0 | 0 | 0.1 | 0 | 0 |  | Nonlabor | Budgeted Cost
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106000 | Fabricate Cold (Cooling) Plates - M&S | 2019-09-03 | 2019-09-16 | Purch 1st $2M sOL | OL | 3420 | 4275 | 0.25 | 1069 | 5344 |  | Nonlabor | Budgeted Cost | 4275
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106100 | Fabricate Cold (Cooling) Plates - Labor | 2019-09-03 | 2019-09-16 | MECHTECH4 LBNL | LBNL | 16 | 2111 | 0.25 | 528 | 2639 | TECH | Labor | Budgeted Cost | 2111
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105000 | Procure Power Distribution (harness) - Labor | 2019-09-03 | 2019-09-30 | ELTECH4 LBNL | LBNL | 120 | 14147 | 0.25 | 3537 | 17684 | TECH | Labor | Budgeted Cost | 14147
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S105801 | Fabricate PB to Stave Cables - Labor | 2019-10-01 | 2019-10-29 | ELTECH4 LBNL | LBNL | 60 | 7286 | 0.25 | 1821 | 9107 | TECH | Labor | Budgeted Cost |  | 7286
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106710 | Assemble PB Labor | 2020-02-13 | 2020-02-20 | ELTECH4 LBNL | LBNL | 30 | 3643 | 0.25 | 911 | 4554 | TECH | Labor | Budgeted Cost |  | 3643
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106785 | Ship PB to BNL M&S | 2020-03-20 | 2020-04-16 | Purch 1st $2M sOL | OL | 1000 | 1275 | 0.1 | 128 | 1403 |  | Nonlabor | Budgeted Cost |  | 1275
POM02B_3.02.02.03.01 | 02.02.03.01 | Power Boards | S106780 | Ship PB to BNL Labor | 2020-03-20 | 2020-04-16 | ELTECH4 LBNL | LBNL | 30 | 3643 | 0.1 | 364 | 4007 | TECH | Labor | Budgeted Cost |  | 3643
WBS: POM02B_3.02.02.03.02 Power Supplies |  |  |  |  | 2019-09-03 | 2020-04-23 |  |  | 77434 | 101680 | 1.55 | 12809 | 114489 |  |  | Budgeted Cost | 8212 | 93468
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107700 | test PB with power supplies | 2020-03-27 | 2020-04-09 | ELTECH4 LBNL | LBNL | 40 | 4857 | 0.1 | 486 | 5343 | TECH | Labor | Budgeted Cost |  | 4857
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107800 | Document Power System | 2020-04-10 | 2020-04-16 | POSTD LBNL | LBNL | 16 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107050 | Procure CAEN A2518 Power Module (16) - Provide Requirements to Procurement | 2019-09-03 | 2019-09-09 | POSTD LBNL | LBNL | 209 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107670 | Procure and terminate PS-to-PB (cabling) - Labor | 2020-02-13 | 2020-03-26 | ELTECH4 LBNL | LBNL | 40 | 4857 | 0.25 | 1214 | 6071 | TECH | Labor | Budgeted Cost |  | 4857
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107600 | Procure CAEN A2518Power Module (16) - Delivery Acceptance | 2020-03-20 | 2020-03-26 | Purch 1st $2M sDOE | DOE | 43676 | 50737 | 0.1 | 5074 | 55811 |  | Nonlabor | Budgeted Cost |  | 50737
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107650 | Procure and terminate PS-to-PB (cabling) - M&S | 2020-02-13 | 2020-03-26 | Purch 1st $2M sOL | OL | 10000 | 12750 | 0.25 | 3188 | 15938 |  | Nonlabor | Budgeted Cost |  | 12750
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107900 | Ship Power System to BNL - M&S | 2020-04-17 | 2020-04-23 | Purch 1st $2M sOL | OL | 2000 | 2550 | 0.1 | 255 | 2805 |  | Nonlabor | Budgeted Cost |  | 2550
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107610 | Procure CAEN A3484 48V Power Supply | 2019-09-03 | 2019-11-27 | Purch 1st $2M sDOE | DOE | 8607 | 9889 | 0.1 | 989 | 10878 |  | Nonlabor | Budgeted Cost | 3296 | 6593
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107620 | Procure CAEN SY4527 Main Frame | 2019-09-03 | 2019-11-27 | Purch 1st $2M sDOE | DOE | 11620 | 13351 | 0.1 | 1335 | 14686 |  | Nonlabor | Budgeted Cost | 4450 | 8900
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107640 | Procure CAEN A4532 Power Booster | 2019-09-03 | 2019-11-27 | Purch 1st $2M sDOE | DOE | 1216 | 1397 | 0.1 | 140 | 1537 |  | Nonlabor | Budgeted Cost | 466 | 931
POM02B_3.02.02.03.02 | 02.02.03.02 | Power Supplies | S107910 | Ship Power System to BNL - Labor | 2020-04-17 | 2020-04-23 | ELTECH4 LBNL | LBNL | 11 | 1292 | 0.1 | 129 | 1421 | TECH | Labor | Budgeted Cost |  | 1292
WBS: POM02B_3.02.03 MVTX Mechanics and Detector Assembly |  |  |  |  | 2019-09-03 | 2022-03-16 |  |  | 537553 | 1700973 | 56.9 | 616162 | 2317135 |  |  | Budgeted Cost | 112831 | 1190116 | 284558 | 113468
WBS: POM02B_3.02.03.01 Staves |  |  |  |  | 2019-09-03 | 2021-01-22 |  |  | 149361 | 340771 | 6.25 | 78245 | 419016 |  |  | Budgeted Cost | 50916 | 176459 | 113396
WBS: POM02B_3.02.03.01.01 Production |  |  |  |  | 2019-09-03 | 2020-09-08 |  |  | 58647 | 72924 | 1.25 | 2318 | 75242 |  |  | Budgeted Cost | 14265 | 58660
POM02B_3.02.03.01.01 | 1.01 | Production | S108000 | Test/QA Staves at CERN | 2019-09-03 | 2020-09-08 | SCI3 LANL | LANL | 1280 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.01.01 | 1.01 | Production | S108300 | CERN Test System - Labor | 2019-09-03 | 2019-09-30 | POSTD LBNL | LBNL | 4 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.01.01 | 1.01 | Production | S108300 | CERN Test System - Labor | 2019-09-03 | 2019-09-30 | STAFFPHYS LBNL | LBNL | 2 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.01.01 | 1.01 | Production | S108100 | CERN Test System - M&S | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 7360 | 9200 | 0.25 | 2300 | 11500 |  | Nonlabor | Budgeted Cost | 9200
POM02B_3.02.03.01.01 | 1.01 | Production | S108300 | CERN Test System - Labor | 2019-09-03 | 2019-09-30 | ELENG3 LBNL | LBNL | 0 | 72 | 0.25 | 18 | 90 | PROF | Labor | Budgeted Cost | 72
POM02B_3.02.03.01.01 | 1.01 | Production | S108200 | Travel and Per Diem at CERN - M&S | 2019-09-03 | 2020-09-08 | Purch 1st $2M sOL | OL | 50000 | 63652 | 0 | 0 | 63652 |  | Nonlabor | Budgeted Cost | 4992 | 58660
WBS: POM02B_3.02.03.01.02 Stave Assembly Tooling |  |  |  |  | 2020-07-29 | 2021-01-22 |  |  | 25264 | 97486 | 1.6 | 38994 | 136481 |  |  | Budgeted Cost |  | 31021 | 66465
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108800 | Stave Assembly Tooling - Procure Assembly Fixtures and Tooling - M&S | 2020-10-23 | 2021-01-22 | Purch 1st $2M MIT | OL | 25000 | 51840 | 0.4 | 20736 | 72576 |  | Nonlabor | Budgeted Cost |  |  | 51840
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108400 | Stave Assembly Tooling - Design | 2020-07-29 | 2020-08-25 | PROF4 MIT | MIT | 80 | 13701 | 0.4 | 5481 | 19182 | PROF | Labor | Budgeted Cost |  | 13701
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108700 | Stave Assembly Tooling - Final Jig Design | 2020-08-26 | 2020-10-22 | PROF4 MIT | MIT | 160 | 27711 | 0.4 | 11084 | 38796 | PROF | Labor | Budgeted Cost |  | 17319 | 10392
POM02B_3.02.03.01.02 | 1.02 | Stave Assembly Tooling | S108900 | Stave Assembly Tooling - Procure Assembly Fixtures and Tooling - Labor | 2020-10-23 | 2021-01-22 | PROF4 MIT | MIT | 24 | 4234 | 0.4 | 1693 | 5927 | PROF | Labor | Budgeted Cost |  |  | 4234
WBS: POM02B_3.02.03.01.03 Metrology |  |  |  |  | 2020-07-29 | 2020-12-30 |  |  | 7363 | 75834 | 1.8 | 27480 | 103314 |  |  | Budgeted Cost |  | 30918 | 44916
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109200 | Procure jigs - M&S | 2020-11-23 | 2020-12-22 | Purch 1st $2M MIT | OL | 5000 | 10368 | 0.4 | 4147 | 14515 |  | Nonlabor | Budgeted Cost |  |  | 10368
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109000 | Metrology design | 2020-07-29 | 2020-09-23 | PROF4 MIT | MIT | 160 | 27403 | 0.4 | 10961 | 38364 | PROF | Labor | Budgeted Cost |  | 27403
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109100 | Design jigs | 2020-09-24 | 2020-11-20 | PROF4 MIT | MIT | 160 | 28122 | 0.4 | 11249 | 39371 | PROF | Labor | Budgeted Cost |  | 3515 | 24607
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109300 | Procure jigs - Labor | 2020-11-23 | 2020-12-22 | TECH4 MIT | MIT | 3 | 429 | 0.4 | 172 | 601 | TECH | Labor | Budgeted Cost |  |  | 429
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109500 | ship to LBNL - M&S | 2020-12-23 | 2020-12-30 | Purch 1st $2M MIT | OL | 2000 | 4147 | 0.1 | 415 | 4562 |  | Nonlabor | Budgeted Cost |  |  | 4147
POM02B_3.02.03.01.03 | 1.03 | Metrology | S109400 | ship to LBNL - Labor | 2020-12-23 | 2020-12-30 | TECH4 MIT | MIT | 40 | 5365 | 0.1 | 536 | 5901 | TECH | Labor | Budgeted Cost |  |  | 5365
WBS: POM02B_3.02.03.01.04 Shipping and Storage Containers |  |  |  |  | 2019-09-03 | 2020-10-07 |  |  | 34087 | 63926 | 1.2 | 6393 | 70319 |  |  | Budgeted Cost | 36651 | 25260 | 2014
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109700 | Design shipping container for 21 staves | 2019-09-03 | 2019-09-09 | MECHENG4 LBNL | LBNL | 40 | 9485 | 0.1 | 948 | 10433 | PROF | Labor | Budgeted Cost | 9485
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109610 | Design & Fabricate Storage Cabinets for Staves - Labor | 2019-09-03 | 2019-10-29 | MECHTECH4 LBNL | LBNL | 41 | 5434 | 0.1 | 543 | 5977 | TECH | Labor | Budgeted Cost | 2717 | 2717
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109610 | Design & Fabricate Storage Cabinets for Staves - Labor | 2019-09-03 | 2019-10-29 | STAFFPHYS LBNL | LBNL | 78 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109610 | Design & Fabricate Storage Cabinets for Staves - Labor | 2019-09-03 | 2019-10-29 | POSTD LBNL | LBNL | 156 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110300 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - Labor | 2020-07-29 | 2020-10-07 | MECHTECH4 LBNL | LBNL | 40 | 5453 | 0.1 | 545 | 5998 | TECH | Labor | Budgeted Cost |  | 4907 | 545
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110300 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - Labor | 2020-07-29 | 2020-10-07 | STAFFPHYS LBNL | LBNL | 100 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110300 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - Labor | 2020-07-29 | 2020-10-07 | POSTD LBNL | LBNL | 132 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109600 | Design & Fabricate Storage Cabinets for Staves - M&S | 2019-09-03 | 2019-10-29 | Purch 1st $2M sOL | OL | 6992 | 8827 | 0.1 | 883 | 9710 |  | Nonlabor | Budgeted Cost | 4414 | 4414
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110200 | Design & Fabricate Shipping and Storage Containers (Half-Barrels) - M&S | 2020-07-29 | 2020-10-07 | Purch 1st $2M sOL | OL | 11500 | 14692 | 0.1 | 1469 | 16161 |  | Nonlabor | Budgeted Cost |  | 13223 | 1469
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110100 | Ship Stave Shipping Devices to CERN | 2019-09-17 | 2019-09-30 | Purch 1st $2M sOL | OL | 5000 | 6250 | 0.1 | 625 | 6875 |  | Nonlabor | Budgeted Cost | 6250
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S109900 | Procure Stave Shipping Plate (84) - Labor | 2019-09-10 | 2019-09-16 | MECHENG3 LBNL | LBNL | 8 | 1286 | 0.1 | 129 | 1415 | PROF | Labor | Budgeted Cost | 1286
POM02B_3.02.03.01.04 | 1.04 | Shipping and Storage Containers | S110000 | Procure Stave Shipping Plate (84) - M&S | 2019-09-10 | 2019-09-16 | Purch 1st $2M sOL | OL | 10000 | 12500 | 0.1 | 1250 | 13750 |  | Nonlabor | Budgeted Cost | 12500
WBS: POM02B_3.02.03.01.05 Shipping the Staves from CERN to LBNL |  |  |  |  | 2019-12-04 | 2020-09-08 |  |  | 24000 | 30600 | 0.4 | 3060 | 33660 |  |  | Budgeted Cost |  | 30600
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110400 | ship from CERN to LBNL - Batch 1 | 2019-12-04 | 2019-12-12 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Cost |  | 7650
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110500 | ship from CERN to LBNL - Batch 2 | 2020-03-05 | 2020-03-13 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Cost |  | 7650
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110600 | ship from CERN to LBNL - Batch 3 | 2020-06-02 | 2020-06-10 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Cost |  | 7650
POM02B_3.02.03.01.05 | 1.05 | Shipping the Staves from CERN to LBNL | S110700 | ship from CERN to LBNL - Batch 4 | 2020-08-28 | 2020-09-08 | Purch 1st $2M sOL | OL | 6000 | 7650 | 0.1 | 765 | 8415 |  | Nonlabor | Budgeted Cost |  | 7650
WBS: POM02B_3.02.03.02 Carbon Structures |  |  |  |  | 2019-09-03 | 2022-03-16 |  |  | 351295 | 1110364 | 14.8 | 450444 | 1560808 |  |  | Budgeted Cost | 61915 | 992092 | 33143 | 23214
WBS: POM02B_3.02.03.02.01 Mechanics Detector Design |  |  |  |  | 2019-09-03 | 2020-01-29 |  |  | 640 | 200199 | 0.4 | 80080 | 280279 |  |  | Budgeted Cost | 40040 | 160159
POM02B_3.02.03.02.01 | 2.01 | Mechanics Detector Design | S110800 | Develop MVTX inner tracker mechanical model | 2019-09-03 | 2020-01-29 | PROF4 LANL | LANL | 640 | 200199 | 0.4 | 80080 | 280279 | PROF | Labor | Budgeted Cost | 40040 | 160159
WBS: POM02B_3.02.03.02.02 End Wheels |  |  |  |  | 2020-01-30 | 2020-08-19 |  |  | 77124 | 310865 | 4.95 | 185134 | 495999 |  |  | Budgeted Cost |  | 310865
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111800 | Review End-wheels | 2020-08-18 | 2020-08-19 | PROF4 LANL | LANL | 8 | 2517 | 0.05 | 126 | 2643 | PROF | Labor | Budgeted Cost |  | 2517
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111600 | End wheels production and test - Labor | 2020-06-08 | 2020-08-17 | MECHTECH4 LBNL | LBNL | 384 | 52189 | 0.6 | 31313 | 83502 | TECH | Labor | Budgeted Cost |  | 52189
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111600 | End wheels production and test - Labor | 2020-06-08 | 2020-08-17 | MECHENG4 LBNL | LBNL | 384 | 93786 | 0.6 | 56271 | 150057 | PROF | Labor | Budgeted Cost |  | 93786
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111700 | End wheels production and test - M&S | 2020-06-08 | 2020-08-17 | Purch 1st $2M sOL | OL | 0 | 0 | 0.1 | 0 | 0 |  | Nonlabor | Budgeted Cost
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111500 | Procure end wheels material - M&S | 2020-06-01 | 2020-06-05 | Purch 1st $2M sOL | OL | 15940 | 20324 | 0.6 | 12194 | 32518 |  | Nonlabor | Budgeted Cost |  | 20324
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S110900 | End Weels Tooling Design | 2020-01-30 | 2020-03-12 | MECHENG4 LBNL | LBNL | 140 | 34193 | 0.6 | 20516 | 54708 | PROF | Labor | Budgeted Cost |  | 34193
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111000 | End-wheels tooling material - M&S | 2020-03-13 | 2020-04-16 | Purch 1st $2M sDOE | DOE | 60000 | 69700 | 0.6 | 41820 | 111520 |  | Nonlabor | Budgeted Cost |  | 69700
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111100 | End-wheels tooling material - Labor | 2020-03-13 | 2020-04-16 | MECHTECH4 LBNL | LBNL | 12 | 1631 | 0.6 | 979 | 2609 | TECH | Labor | Budgeted Cost |  | 1631
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111200 | End wheels tooling assembly - Labor | 2020-04-17 | 2020-05-29 | MECHTECH4 LBNL | LBNL | 240 | 32618 | 0.6 | 19571 | 52189 | TECH | Labor | Budgeted Cost |  | 32618
POM02B_3.02.03.02.02 | 2.02 | End Wheels | S111400 | Procure end wheels material - Labor | 2020-06-01 | 2020-06-05 | MECHENG4 LBNL | LBNL | 16 | 3908 | 0.6 | 2345 | 6252 | PROF | Labor | Budgeted Cost |  | 3908
WBS: POM02B_3.02.03.02.03 Mechanics Fabrication |  |  |  |  | 2019-09-03 | 2022-03-16 |  |  | 263371 | 557207 | 7.95 | 178017 | 735223 |  |  | Budgeted Cost | 21875 | 478974 | 33143 | 23214
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112600 | Travel LBNL - FY19 | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 17500 | 21875 | 0 | 0 | 21875 |  | Nonlabor | Budgeted Cost | 21875
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112700 | Travel LBNL - FY20 | 2019-10-01 | 2020-09-30 | Purch 1st $2M sOL | OL | 17500 | 22313 | 0 | 0 | 22313 |  | Nonlabor | Budgeted Cost |  | 22313
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112800 | Travel LBNL - FY21 | 2020-10-01 | 2021-09-30 | Purch 1st $2M sOL | OL | 17500 | 22759 | 0 | 0 | 22759 |  | Nonlabor | Budgeted Cost |  |  | 22759
POM02B_3.02.03.02.03 | 2.03 | Mechanics Fabrication | S112900 | Travel LBNL - FY22 | 2021-10-01 | 2022-03-16 | Purch 1st $2M sOL | OL | 17500 | 23214 | 0 | 0 | 23214 |  | Nonlabor | Budgeted Cost |  |  |  | 23214
WBS: POM02B_3.02.03.02.03.01 Cylindrical Support Structure (CYSS) |  |  |  |  | 2020-01-30 | 2020-09-01 |  |  | 76694 | 200808 | 4.4 | 80323 | 281131 |  |  | Budgeted Cost |  | 200808
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113000 | CYSS Tooling Design | 2020-01-30 | 2020-02-27 | MECHENG4 LBNL | LBNL | 96 | 23446 | 0.4 | 9379 | 32825 | PROF | Labor | Budgeted Cost |  | 23446
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113500 | Procure CYSS Material - Labor | 2020-04-10 | 2020-04-16 | STAFFPHYS LBNL | LBNL | 8 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113700 | Production & Test CYSS - Labor | 2020-07-29 | 2020-09-01 | MECHTECH4 LBNL | LBNL | 169 | 22963 | 0.4 | 9185 | 32148 | TECH | Labor | Budgeted Cost |  | 22963
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113700 | Production & Test CYSS - Labor | 2020-07-29 | 2020-09-01 | MECHENG4 LBNL | LBNL | 169 | 41266 | 0.4 | 16506 | 57772 | PROF | Labor | Budgeted Cost |  | 41266
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113700 | Production & Test CYSS - Labor | 2020-07-29 | 2020-09-01 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113400 | Procure CYSS Material - M&S | 2020-04-10 | 2020-04-16 | Purch 1st $2M sOL | OL | 15940 | 20324 | 0.4 | 8129 | 28453 |  | Nonlabor | Budgeted Cost |  | 20324
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113100 | CYSS Tooling Material - Labor | 2020-02-28 | 2020-03-19 | STAFFPHYS LBNL | LBNL | 120 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113200 | CYSS Tooling Material - M&S | 2020-02-28 | 2020-03-19 | Purch 1st $2M sOL | OL | 30000 | 38250 | 0.4 | 15300 | 53550 |  | Nonlabor | Budgeted Cost |  | 38250
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113300 | CYSS Tooling Iteration - Labor | 2020-03-20 | 2020-04-09 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113301 | CYSS Tooling Iteration - M&S | 2020-03-20 | 2020-04-09 | Purch 1st $2M sOL | OL | 30000 | 38250 | 0.4 | 15300 | 53550 |  | Nonlabor | Budgeted Cost |  | 38250
POM02B_3.02.03.02.03.01 | 02.03.01 | Cylindrical Support Structure (CYSS) | S113510 | CYSS Tooling assembly | 2020-04-17 | 2020-05-14 | MECHTECH4 LBNL | LBNL | 120 | 16309 | 0.4 | 6524 | 22833 | TECH | Labor | Budgeted Cost |  | 16309
WBS: POM02B_3.02.03.02.03.02 Service Barrel (SB) |  |  |  |  | 2020-04-10 | 2020-10-07 |  |  | 116677 | 266239 | 3.55 | 97693 | 363932 |  |  | Budgeted Cost |  | 255854 | 10385
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S113900 | Review SB Design-Fabrication Compatibility | 2020-04-10 | 2020-05-07 | MECHENG4 LBNL | LBNL | 51 | 12505 | 0.05 | 625 | 13130 | PROF | Labor | Budgeted Cost |  | 12505
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S113900 | Review SB Design-Fabrication Compatibility | 2020-04-10 | 2020-05-07 | STAFFPHYS LBNL | LBNL | 20 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S113900 | Review SB Design-Fabrication Compatibility | 2020-04-10 | 2020-05-07 | POSTD LBNL | LBNL | 20 | 0 | 0.05 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | PROF4 MIT | MIT | 40 | 6782 | 0.05 | 339 | 7121 | PROF | Labor | Budgeted Cost |  | 6782
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114100 | SB Tooling - Labor | 2020-05-22 | 2020-06-26 | MECHENG4 LBNL | LBNL | 160 | 39077 | 0.4 | 15631 | 54708 | PROF | Labor | Budgeted Cost |  | 39077
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114300 | Procure SB Material - Labor | 2020-06-29 | 2020-07-06 | STAFFPHYS LBNL | LBNL | 8 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114500 | Production & Test SB - Labor | 2020-09-02 | 2020-10-07 | MECHENG4 LBNL | LBNL | 118 | 28953 | 0.4 | 11581 | 40534 | PROF | Labor | Budgeted Cost |  | 23163 | 5791
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114500 | Production & Test SB - Labor | 2020-09-02 | 2020-10-07 | MECHTECH4 LBNL | LBNL | 168 | 22970 | 0.4 | 9188 | 32157 | TECH | Labor | Budgeted Cost |  | 18376 | 4594
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114400 | Production & Test SB - M&S | 2020-09-02 | 2020-10-07 | Purch 1st $2M sOL | OL | 0 | 0 | 0.4 | 0 | 0 |  | Nonlabor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | MECHENG4 LBNL | LBNL | 24 | 5862 | 0.05 | 293 | 6155 | PROF | Labor | Budgeted Cost |  | 5862
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114000 | Hold SB Review (PRR) | 2020-05-08 | 2020-05-21 | POSTD LBNL | LBNL | 24 | 0 | 0.05 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114101 | SB Tooling - M&S | 2020-05-22 | 2020-06-26 | Purch 1st $2M sOL | OL | 40000 | 51000 | 0.4 | 20400 | 71400 |  | Nonlabor | Budgeted Cost |  | 51000
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114100 | SB Tooling - Labor | 2020-05-22 | 2020-06-26 | MECHTECH4 LBNL | LBNL | 80 | 10873 | 0.4 | 4349 | 15222 | TECH | Labor | Budgeted Cost |  | 10873
POM02B_3.02.03.02.03.02 | 02.03.02 | Service Barrel (SB) | S114200 | Procure SB Material - M&S | 2020-06-29 | 2020-07-06 | Purch 1st $2M sDOE | DOE | 75940 | 88217 | 0.4 | 35287 | 123504 |  | Nonlabor | Budgeted Cost |  | 88217
WBS: POM02B_3.02.03.02.04 MVTX Final Design Review |  |  |  |  | 2020-06-29 | 2020-07-28 |  |  | 10160 | 42093 | 1.5 | 7213 | 49306 |  |  | Budgeted Cost |  | 42093
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114900 | Incorporate MVTX Review Comments LBNL | 2020-07-14 | 2020-07-20 | MECHENG4 LBNL | LBNL | 36 | 8792 | 0.25 | 2198 | 10991 | PROF | Labor | Budgeted Cost |  | 8792
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114800 | MVTX Design Review LBNL - Labor | 2020-06-29 | 2020-07-06 | MECHENG4 LBNL | LBNL | 8 | 1954 | 0.05 | 98 | 2052 | PROF | Labor | Budgeted Cost |  | 1954
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114800 | MVTX Design Review LBNL - Labor | 2020-06-29 | 2020-07-06 | STAFFPHYS LBNL | LBNL | 16 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114800 | MVTX Design Review LBNL - Labor | 2020-06-29 | 2020-07-06 | SCI3 LANL | LANL | 16 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114700 | MVTX Design Review LBNL - M&S | 2020-06-29 | 2020-07-06 | Purch 1st $2M sOL | OL | 5000 | 6375 | 0.1 | 638 | 7013 |  | Nonlabor | Budgeted Cost |  | 6375
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114801 | MVTX Design Review LANL - Labor | 2020-07-07 | 2020-07-13 | STAFFPHYS LBNL | LBNL | 8 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114801 | MVTX Design Review LANL - Labor | 2020-07-07 | 2020-07-13 | SCI3 LANL | LANL | 16 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114801 | MVTX Design Review LANL - Labor | 2020-07-07 | 2020-07-13 | PROF4 LANL | LANL | 16 | 5034 | 0.05 | 252 | 5286 | PROF | Labor | Budgeted Cost |  | 5034
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114810 | MVTX Design Review LANL - M&S | 2020-07-07 | 2020-07-13 | Purch 1st $2M sOL | OL | 5000 | 6375 | 0.1 | 638 | 7013 |  | Nonlabor | Budgeted Cost |  | 6375
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S114910 | Incorporate MVTX Review Comments LANL | 2020-07-21 | 2020-07-27 | PROF4 LANL | LANL | 36 | 11327 | 0.25 | 2832 | 14159 | PROF | Labor | Budgeted Cost |  | 11327
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S115000 | Complete Final MVTX Design LBNL | 2020-07-28 | 2020-07-28 | MECHENG4 LBNL | LBNL | 4 | 977 | 0.25 | 244 | 1221 | PROF | Labor | Budgeted Cost |  | 977
POM02B_3.02.03.02.04 | 2.04 | MVTX Final Design Review | S115010 | Complete Final MVTX Design LANL | 2020-07-28 | 2020-07-28 | PROF4 LANL | LANL | 4 | 1259 | 0.25 | 315 | 1573 | PROF | Labor | Budgeted Cost |  | 1259
WBS: POM02B_3.02.03.03 Barrel Assembly |  |  |  |  | 2020-03-20 | 2021-12-13 |  |  | 36898 | 249839 | 35.85 | 87473 | 337311 |  |  | Budgeted Cost |  | 21565 | 138019 | 90254
WBS: POM02B_3.02.03.03.01 Assembly and Testing |  |  |  |  | 2020-03-20 | 2021-12-13 |  |  | 36898 | 249839 | 35.85 | 87473 | 337311 |  |  | Budgeted Cost |  | 21565 | 138019 | 90254
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Cost |  | 1788
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Cost |  | 1272
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Cost |  | 2331
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115100 | Test and Rework Staves - Batch 1 | 2020-03-20 | 2020-04-09 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Cost |  | 1788
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Cost |  | 1272
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Cost |  | 2331
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115200 | Test and Rework Staves - Batch 2 | 2020-04-10 | 2020-04-30 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Cost |  | 1788
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Cost |  | 1272
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Cost |  | 2331
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115300 | Test and Rework Staves - Batch 3 | 2020-06-11 | 2020-07-01 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | ELENG3 LBNL | LBNL | 10 | 1788 | 0.25 | 447 | 2235 | PROF | Labor | Budgeted Cost |  | 1788
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | MECHENG3 LBNL | LBNL | 8 | 1272 | 0.25 | 318 | 1590 | PROF | Labor | Budgeted Cost |  | 1272
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | ELTECH4 LBNL | LBNL | 19 | 2331 | 0.25 | 583 | 2914 | TECH | Labor | Budgeted Cost |  | 2331
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | POSTD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | STAFFPHYS LBNL | LBNL | 48 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01 | 3.01 | Assembly and Testing | S115500 | Test and Rework Staves - Batch 4 | 2020-09-09 | 2020-09-29 | GRSTUD LBNL | LBNL | 96 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
WBS: POM02B_3.02.03.03.01.01 Layer Assembly and Test |  |  |  |  | 2021-01-25 | 2021-07-30 |  |  | 8221 | 76978 | 8.95 | 29836 | 106815 |  |  | Budgeted Cost |  |  | 76978
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | MECHENG3 LBNL | LBNL | 16 | 2729 | 0.4 | 1092 | 3820 | PROF | Labor | Budgeted Cost |  |  | 2729
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | MECHTECH4 LBNL | LBNL | 32 | 4480 | 0.4 | 1792 | 6271 | TECH | Labor | Budgeted Cost |  |  | 4480
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | POSTD LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115600 | Test Installation of Staves onto Layer End-Wheels | 2021-01-25 | 2021-02-22 | STAFFPHYS LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115700 | Hold Half-Detector Assembly Review (PRR) | 2021-02-23 | 2021-03-01 | MECHENG3 LBNL | LBNL | 16 | 2729 | 0.05 | 136 | 2865 | PROF | Labor | Budgeted Cost |  |  | 2729
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115700 | Hold Half-Detector Assembly Review (PRR) | 2021-02-23 | 2021-03-01 | POSTD LBNL | LBNL | 40 | 0 | 0.05 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115700 | Hold Half-Detector Assembly Review (PRR) | 2021-02-23 | 2021-03-01 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | CMMTECH4 LBNL | LBNL | 79 | 11234 | 0.4 | 4494 | 15727 | TECH | Labor | Budgeted Cost |  |  | 11234
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | STAFFPHYS LBNL | LBNL | 30 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | POSTD LBNL | LBNL | 120 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116200 | Perform Half-Detector Metrology On Layers | 2021-07-15 | 2021-07-30 | GRSTUD LBNL | LBNL | 60 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | MECHENG3 LBNL | LBNL | 56 | 9551 | 0.4 | 3820 | 13371 | PROF | Labor | Budgeted Cost |  |  | 9551
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | ELENG3 LBNL | LBNL | 56 | 10744 | 0.4 | 4298 | 15042 | PROF | Labor | Budgeted Cost |  |  | 10744
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | POSTD LBNL | LBNL | 560 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | STAFFPHYS LBNL | LBNL | 140 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | ELTECH4 LBNL | LBNL | 112 | 14008 | 0.4 | 5603 | 19611 | TECH | Labor | Budgeted Cost |  |  | 14008
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115900 | Install Staves Onto Layer End-Wheels To Form Layers - Labor | 2021-03-02 | 2021-06-08 | GRSTUD LBNL | LBNL | 560 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | ELENG3 LBNL | LBNL | 24 | 4605 | 0.4 | 1842 | 6447 | PROF | Labor | Budgeted Cost |  |  | 4605
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | MECHENG3 LBNL | LBNL | 41 | 6958 | 0.4 | 2783 | 9742 | PROF | Labor | Budgeted Cost |  |  | 6958
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | ELTECH4 LBNL | LBNL | 24 | 3002 | 0.4 | 1201 | 4202 | TECH | Labor | Budgeted Cost |  |  | 3002
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | POSTD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | STAFFPHYS LBNL | LBNL | 79 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116100 | Test and Rework Layers After Assembly - Labor | 2021-06-09 | 2021-07-14 | GRSTUD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S115800 | Install Staves Onto Layer End-Wheels To Form Layers - M&S | 2021-03-02 | 2021-06-08 | Purch 1st $2M sOL | OL | 2760 | 3589 | 0.4 | 1436 | 5025 |  | Nonlabor | Budgeted Cost |  |  | 3589
POM02B_3.02.03.03.01.01 | 03.01.01 | Layer Assembly and Test | S116000 | Test and Rework Layers After Assembly - M&S | 2021-06-09 | 2021-07-14 | Purch 1st $2M sOL | OL | 2576 | 3350 | 0.4 | 1340 | 4690 |  | Nonlabor | Budgeted Cost |  |  | 3350
WBS: POM02B_3.02.03.03.01.02 Half Barrel #1 Assembly and Test |  |  |  |  | 2021-08-02 | 2021-12-03 |  |  | 13785 | 75436 | 10.45 | 26038 | 101474 |  |  | Budgeted Cost |  |  | 37903 | 37533
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | ELENG3 LBNL | LBNL | 16 | 3070 | 0.4 | 1228 | 4298 | PROF | Labor | Budgeted Cost |  |  | 3070
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | MECHENG3 LBNL | LBNL | 40 | 6822 | 0.4 | 2729 | 9551 | PROF | Labor | Budgeted Cost |  |  | 6822
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | ELTECH4 LBNL | LBNL | 32 | 4002 | 0.4 | 1601 | 5603 | TECH | Labor | Budgeted Cost |  |  | 4002
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | POSTD LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | STAFFPHYS LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116500 | Assemble Layers and CYSS into Half Barrel #1 - Labor | 2021-08-02 | 2021-08-27 | GRSTUD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | ELENG3 LBNL | LBNL | 24 | 4616 | 0.4 | 1846 | 6462 | PROF | Labor | Budgeted Cost |  |  | 4247 | 369
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | MECHENG3 LBNL | LBNL | 48 | 8206 | 0.4 | 3282 | 11488 | PROF | Labor | Budgeted Cost |  |  | 7550 | 656
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | ELTECH4 LBNL | LBNL | 48 | 6018 | 0.4 | 2407 | 8425 | TECH | Labor | Budgeted Cost |  |  | 5536 | 481
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | POSTD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | STAFFPHYS LBNL | LBNL | 79 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116700 | Test and Rework Half Barrel #1 - Labor | 2021-08-30 | 2021-10-04 | GRSTUD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | CMMTECH4 LBNL | LBNL | 56 | 8181 | 0.4 | 3273 | 11454 | TECH | Labor | Budgeted Cost |  |  |  | 8181
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | POSTD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116800 | Perform Half Barrel #1 Metrology On Final Assembly - Labor | 2021-10-05 | 2021-10-19 | GRSTUD LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | ELENG3 LBNL | LBNL | 16 | 3162 | 0.25 | 790 | 3952 | PROF | Labor | Budgeted Cost |  |  |  | 3162
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | MECHENG3 LBNL | LBNL | 16 | 2811 | 0.25 | 703 | 3513 | PROF | Labor | Budgeted Cost |  |  |  | 2811
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | CMMTECH4 LBNL | LBNL | 24 | 3506 | 0.25 | 877 | 4383 | TECH | Labor | Budgeted Cost |  |  |  | 3506
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | POSTD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | STAFFPHYS LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | MECHTECH4 LBNL | LBNL | 32 | 4614 | 0.25 | 1153 | 5767 | TECH | Labor | Budgeted Cost |  |  |  | 4614
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117000 | Validation Of Final Assembly - Labor | 2021-10-20 | 2021-11-09 | GRSTUD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | MECHENG3 LBNL | LBNL | 16 | 2740 | 0.25 | 685 | 3426 | PROF | Labor | Budgeted Cost |  |  |  | 2740
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | MECHTECH4 LBNL | LBNL | 16 | 2249 | 0.25 | 562 | 2812 | TECH | Labor | Budgeted Cost |  |  |  | 2249
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | POSTD LBNL | LBNL | 120 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117200 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - Labor | 2021-11-10 | 2021-12-03 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116400 | Assemble Layers and CYSS into Half Barrel #1 - M&S | 2021-08-02 | 2021-08-27 | Purch 1st $2M sOL | OL | 2760 | 3589 | 0.4 | 1436 | 5025 |  | Nonlabor | Budgeted Cost |  |  | 3589
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116600 | Test and Rework Half Barrel #1 - M&S | 2021-08-30 | 2021-10-04 | Purch 1st $2M sOL | OL | 2576 | 3355 | 0.4 | 1342 | 4698 |  | Nonlabor | Budgeted Cost |  |  | 3087 | 268
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S116900 | Validation Of Final Assembly - M&S | 2021-10-20 | 2021-11-09 | Purch 1st $2M sOL | OL | 2576 | 3417 | 0.25 | 854 | 4271 |  | Nonlabor | Budgeted Cost |  |  |  | 3417
POM02B_3.02.03.03.01.02 | 03.01.02 | Half Barrel #1 Assembly and Test | S117100 | Pack/Ship Final Assemblies of Half Barrel #1 To BNL - M&S | 2021-11-10 | 2021-12-03 | Purch 1st $2M sOL | OL | 3827 | 5077 | 0.25 | 1269 | 6346 |  | Nonlabor | Budgeted Cost |  |  |  | 5077
WBS: POM02B_3.02.03.03.01.03 Half Barrel #2 Assembly and Test |  |  |  |  | 2021-08-30 | 2021-12-13 |  |  | 13785 | 75859 | 10.45 | 26207 | 102066 |  |  | Budgeted Cost |  |  | 23138 | 52721
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | CMMTECH4 LBNL | LBNL | 56 | 8181 | 0.4 | 3273 | 11454 | TECH | Labor | Budgeted Cost |  |  |  | 8181
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | POSTD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117700 | Perform Half Barrel #2 Metrology On Final Assembly | 2021-10-25 | 2021-11-03 | GRSTUD LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | ELENG3 LBNL | LBNL | 16 | 3070 | 0.4 | 1228 | 4298 | PROF | Labor | Budgeted Cost |  |  | 3070
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | MECHENG3 LBNL | LBNL | 40 | 6822 | 0.4 | 2729 | 9551 | PROF | Labor | Budgeted Cost |  |  | 6822
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | ELTECH4 LBNL | LBNL | 32 | 4002 | 0.4 | 1601 | 5603 | TECH | Labor | Budgeted Cost |  |  | 4002
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | POSTD LBNL | LBNL | 160 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | STAFFPHYS LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117400 | Assemble Layers and CYSS Into Half Barrel #2 - Labor | 2021-08-30 | 2021-09-23 | GRSTUD LBNL | LBNL | 80 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | ELENG3 LBNL | LBNL | 24 | 4708 | 0.4 | 1883 | 6592 | PROF | Labor | Budgeted Cost |  |  | 1177 | 3531
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | MECHENG3 LBNL | LBNL | 48 | 8371 | 0.4 | 3348 | 11719 | PROF | Labor | Budgeted Cost |  |  | 2093 | 6278
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | ELTECH4 LBNL | LBNL | 48 | 6138 | 0.4 | 2455 | 8594 | TECH | Labor | Budgeted Cost |  |  | 1535 | 4604
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | POSTD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | STAFFPHYS LBNL | LBNL | 79 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117600 | Test and Rework Half Barrel #2 - Labor | 2021-09-24 | 2021-10-22 | GRSTUD LBNL | LBNL | 240 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | ELENG3 LBNL | LBNL | 16 | 3162 | 0.25 | 790 | 3952 | PROF | Labor | Budgeted Cost |  |  |  | 3162
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | MECHENG3 LBNL | LBNL | 16 | 2811 | 0.25 | 703 | 3513 | PROF | Labor | Budgeted Cost |  |  |  | 2811
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | CMMTECH4 LBNL | LBNL | 24 | 3506 | 0.25 | 877 | 4383 | TECH | Labor | Budgeted Cost |  |  |  | 3506
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | POSTD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | STAFFPHYS LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | MECHTECH4 LBNL | LBNL | 32 | 4614 | 0.25 | 1153 | 5767 | TECH | Labor | Budgeted Cost |  |  |  | 4614
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117900 | Validation Of Final Assembly - Labor | 2021-11-04 | 2021-11-29 | GRSTUD LBNL | LBNL | 160 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | MECHENG3 LBNL | LBNL | 16 | 2740 | 0.25 | 685 | 3426 | PROF | Labor | Budgeted Cost |  |  |  | 2740
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | MECHTECH4 LBNL | LBNL | 16 | 2249 | 0.25 | 562 | 2812 | TECH | Labor | Budgeted Cost |  |  |  | 2249
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | POSTD LBNL | LBNL | 120 | 0 | 0.25 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118100 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - Labor | 2021-11-30 | 2021-12-13 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.25 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117300 | Assemble Layers and CYSS Into Half Barrel #2 - M&S | 2021-08-30 | 2021-09-23 | Purch 1st $2M sOL | OL | 2760 | 3589 | 0.4 | 1436 | 5025 |  | Nonlabor | Budgeted Cost |  |  | 3589
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117500 | Test and Rework Half Barrel #2 - M&S | 2021-09-24 | 2021-10-22 | Purch 1st $2M sOL | OL | 2576 | 3400 | 0.4 | 1360 | 4760 |  | Nonlabor | Budgeted Cost |  |  | 850 | 2550
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S117800 | Validation Of Final Assembly - M&S | 2021-11-04 | 2021-11-29 | Purch 1st $2M sOL | OL | 2576 | 3417 | 0.25 | 854 | 4271 |  | Nonlabor | Budgeted Cost |  |  |  | 3417
POM02B_3.02.03.03.01.03 | 03.01.03 | Half Barrel #2 Assembly and Test | S118000 | Pack/Ship Final Assemblies of Half Barrel #2 to BNL - M&S | 2021-11-30 | 2021-12-13 | Purch 1st $2M sOL | OL | 3827 | 5077 | 0.25 | 1269 | 6346 |  | Nonlabor | Budgeted Cost |  |  |  | 5077
WBS: POM02B_3.02.04 MVTX Integration and Infrastructure |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 333024 | 875460 | 13.4 | 267862 | 1143322 |  |  | Budgeted Cost | 3200 | 432765 | 424004 | 15491
POM02B_3.02.04 | 02.04.01 | MVTX Integration and Infrastructure | S118900 | Clean Tent/Room - Delivery Acceptance | 2020-01-21 | 2020-01-27 | Purch 1st $2M sDOE | DOE | 50000 | 58084 | 0.1 | 5808 | 63892 |  | Nonlabor | Budgeted Cost |  | 58084
WBS: POM02B_3.02.04.01 Cooling System |  |  |  |  | 2020-07-29 | 2021-03-08 |  |  | 87332 | 172233 | 3.7 | 54721 | 226954 |  |  | Budgeted Cost |  | 95919 | 76314
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119100 | Design Cooling (Modify ALICE Design) | 2020-07-29 | 2020-08-25 | PROF4 MIT | MIT | 80 | 13701 | 0.4 | 5481 | 19182 | PROF | Labor | Budgeted Cost |  | 13701
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119400 | Final Design of Cooling System | 2020-09-10 | 2020-09-16 | PROF4 MIT | MIT | 40 | 6851 | 0.4 | 2740 | 9591 | PROF | Labor | Budgeted Cost |  | 6851
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119300 | Mock up Testing - Labor | 2020-08-26 | 2020-09-09 | TECH4 MIT | MIT | 60 | 7813 | 0.4 | 3125 | 10938 | TECH | Labor | Budgeted Cost |  | 7813
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119600 | Procure Cooling Plant - Labor | 2020-10-01 | 2021-03-01 | SCI3 MIT | MIT | 16 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119600 | Procure Cooling Plant - Labor | 2020-10-01 | 2021-03-01 | TECH4 MIT | MIT | 16 | 2146 | 0.4 | 858 | 3004 | TECH | Labor | Budgeted Cost |  |  | 2146
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119700 | Ship Cooling Plant to BNL | 2021-03-02 | 2021-03-08 | Purch 1st $2M MIT | OL | 2000 | 4147 | 0.1 | 415 | 4562 |  | Nonlabor | Budgeted Cost |  |  | 4147
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119100 | Design Cooling (Modify ALICE Design) | 2020-07-29 | 2020-08-25 | TECH4 MIT | MIT | 80 | 10417 | 0.4 | 4167 | 14584 | TECH | Labor | Budgeted Cost |  | 10417
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119200 | Mock up Testing - M&S | 2020-08-26 | 2020-09-09 | Purch 1st $2M MIT | DOE | 20000 | 40659 | 0.4 | 16263 | 56922 |  | Nonlabor | Budgeted Cost |  | 40659
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119300 | Mock up Testing - Labor | 2020-08-26 | 2020-09-09 | PROF4 MIT | MIT | 40 | 6782 | 0.4 | 2713 | 9495 | PROF | Labor | Budgeted Cost |  | 6782
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119000 | Cooling System - MIT Travel | 2020-07-29 | 2021-03-08 | Purch 1st $2M sOL | OL | 25000 | 32321 | 0 | 0 | 32321 |  | Nonlabor | Budgeted Cost |  | 9696 | 22625
POM02B_3.02.04.01 | 02.04.01 | Cooling System | S119500 | Procure Cooling Plant - M&S | 2020-10-01 | 2020-10-01 | Purch 1st $2M sDOE | DOE | 40000 | 47396 | 0.4 | 18958 | 66355 |  | Nonlabor | Budgeted Cost |  |  | 47396
WBS: POM02B_3.02.04.02 Safety Systems |  |  |  |  | 2020-09-17 | 2021-04-12 |  |  | 36234 | 154057 | 5.2 | 37743 | 191800 |  |  | Budgeted Cost |  | 9170 | 144887
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119900 | Define MVTX Safety and Interlock requirements | 2020-09-17 | 2020-09-30 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119900 | Define MVTX Safety and Interlock requirements | 2020-09-17 | 2020-09-30 | POSTD LBNL | LBNL | 40 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119900 | Define MVTX Safety and Interlock requirements | 2020-09-17 | 2020-09-30 | PROF4 MIT | MIT | 40 | 6851 | 0.4 | 2740 | 9591 | PROF | Labor | Budgeted Cost |  | 6851
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120000 | Review Sensors & Interlocks with BNL ES&H | 2020-10-01 | 2020-10-15 | PROF4 MIT | MIT | 40 | 7056 | 0.05 | 353 | 7409 | PROF | Labor | Budgeted Cost |  |  | 7056
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120000 | Review Sensors & Interlocks with BNL ES&H | 2020-10-01 | 2020-10-15 | STAFFPHYS LBNL | LBNL | 40 | 0 | 0.05 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120100 | Design Electronics Safety System | 2020-10-16 | 2020-11-13 | STAFFPHYS LBNL | LBNL | 103 | 0 | 0.4 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120100 | Design Electronics Safety System | 2020-10-16 | 2020-11-13 | POSTD LBNL | LBNL | 103 | 0 | 0.4 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120100 | Design Electronics Safety System | 2020-10-16 | 2020-11-13 | PROF4 MIT | MIT | 82 | 14516 | 0.4 | 5807 | 20323 | PROF | Labor | Budgeted Cost |  |  | 14516
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120200 | Design Cooling Interlocks | 2020-11-16 | 2020-12-30 | PROF4 MIT | MIT | 120 | 21169 | 0.4 | 8467 | 29636 | PROF | Labor | Budgeted Cost |  |  | 21169
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120500 | Test Safety Systems at MIT | 2021-03-02 | 2021-03-22 | TECH4 MIT | MIT | 120 | 16094 | 0.4 | 6438 | 22532 | TECH | Labor | Budgeted Cost |  |  | 16094
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120500 | Test Safety Systems at MIT | 2021-03-02 | 2021-03-22 | PROF4 MIT | MIT | 41 | 7197 | 0.4 | 2879 | 10076 | PROF | Labor | Budgeted Cost |  |  | 7197
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120700 | Test Safety Systems at BNL | 2021-03-30 | 2021-04-12 | TECH4 MIT | MIT | 80 | 10729 | 0.1 | 1073 | 11802 | TECH | Labor | Budgeted Cost |  |  | 10729
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120700 | Test Safety Systems at BNL | 2021-03-30 | 2021-04-12 | PROF4 MIT | MIT | 80 | 14112 | 0.1 | 1411 | 15524 | PROF | Labor | Budgeted Cost |  |  | 14112
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120400 | Procure Safety Systems - Labor | 2020-12-31 | 2021-03-01 | TECH4 MIT | MIT | 16 | 2146 | 0.4 | 858 | 3004 | TECH | Labor | Budgeted Cost |  |  | 2146
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120400 | Procure Safety Systems - Labor | 2020-12-31 | 2021-03-01 | PROF4 MIT | MIT | 42 | 7338 | 0.4 | 2935 | 10274 | PROF | Labor | Budgeted Cost |  |  | 7338
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120600 | Ship Safety Systems to BNL | 2021-03-23 | 2021-03-29 | Purch 1st $2M MIT | OL | 200 | 415 | 0.1 | 41 | 456 |  | Nonlabor | Budgeted Cost |  |  | 415
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S119800 | Safety Systems - MIT Travel | 2020-09-17 | 2021-04-12 | Purch 1st $2M sOL | OL | 25000 | 32467 | 0 | 0 | 32467 |  | Nonlabor | Budgeted Cost |  | 2319 | 30148
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120300 | Procure Safety Systems - M&S | 2020-12-31 | 2021-03-01 | Purch 1st $2M sDOE | DOE | 10000 | 11849 | 0.4 | 4740 | 16589 |  | Nonlabor | Budgeted Cost |  |  | 11849
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | SCI3 MIT |  | 12 | 0 |  | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | STAFFPHYS LBNL |  | 12 | 0 |  | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | SCI3 LANL |  | 12 | 0 |  | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.02 | 02.04.02 | Safety Systems | S120550 | Review Safety Systems | 2021-03-02 | 2021-03-08 | PROF4 MIT |  | 12 | 2117 |  | 0 | 2117 | PROF | Labor | Budgeted Cost |  |  | 2117
WBS: POM02B_3.02.04.03 Service Barrel Support Frame & MVTX Interface to sPHENIX |  |  |  |  | 2019-09-03 | 2022-03-17 |  |  | 158282 | 431797 | 2.6 | 163661 | 595458 |  |  | Budgeted Cost | 3200 | 240526 | 185017 | 3054
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122700 | Procure Insertion System - Delivery Acceptance | 2021-02-16 | 2021-02-22 | Purch 1st $2M sDOE | DOE | 40000 | 47396 | 0.4 | 18958 | 66355 |  | Nonlabor | Budgeted Cost |  |  | 47396
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122800 | ship to BNL - M&S | 2021-02-23 | 2021-03-01 | Purch 1st $2M MIT | OL | 2000 | 4147 | 0.1 | 415 | 4562 |  | Nonlabor | Budgeted Cost |  |  | 4147
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S120800 | Travel FY19 | 2019-09-03 | 2019-09-30 | Purch 1st $2M sOL | OL | 2560 | 3200 | 0 | 0 | 3200 |  | Nonlabor | Budgeted Cost | 3200
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121000 | Travel FY20 | 2019-10-01 | 2020-09-30 | Purch 1st $2M sOL | OL | 5000 | 6375 | 0 | 0 | 6375 |  | Nonlabor | Budgeted Cost |  | 6375
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122000 | Travel FY21 | 2020-10-01 | 2021-09-30 | Purch 1st $2M sOL | OL | 5000 | 6503 | 0 | 0 | 6503 |  | Nonlabor | Budgeted Cost |  |  | 6503
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S123000 | Travel FY22 | 2021-10-01 | 2022-03-17 | Purch 1st $2M sOL | OL | 2302 | 3054 | 0 | 0 | 3054 |  | Nonlabor | Budgeted Cost |  |  |  | 3054
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S120900 | Design Interface to sPHENIX | 2019-12-24 | 2020-06-22 | PROF4 MIT | MIT | 1000 | 171268 | 0.4 | 68507 | 239775 | PROF | Labor | Budgeted Cost |  | 171268
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121800 | Design Insertion System | 2020-07-29 | 2020-10-07 | PROF4 MIT | MIT | 400 | 68713 | 0.4 | 27485 | 96198 | PROF | Labor | Budgeted Cost |  | 61841 | 6871
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122900 | ship to BNL - Labor | 2021-02-23 | 2021-03-01 | TECH4 MIT | MIT | 4 | 536 | 0.1 | 54 | 590 | TECH | Labor | Budgeted Cost |  |  | 536
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121100 | Procure Support Structure -Provide Requirements to Procurement | 2020-07-29 | 2020-08-04 | TECH4 MIT | MIT | 8 | 1042 | 0.4 | 417 | 1458 | TECH | Labor | Budgeted Cost |  | 1042
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S122100 | Procure Insertion System -Provide Requirements to Procurement | 2020-10-08 | 2020-10-15 | TECH4 MIT | MIT | 8 | 1073 | 0.4 | 429 | 1502 | TECH | Labor | Budgeted Cost |  |  | 1073
POM02B_3.02.04.03 | 02.04.03 | Service Barrel Support Frame & MVTX Interface to sPHENIX | S121700 | Procure Support Structure - Delivery Acceptance | 2020-12-02 | 2020-12-02 | Purch 1st $2M sDOE | DOE | 100000 | 118490 | 0.4 | 47396 | 165887 |  | Nonlabor | Budgeted Cost |  |  | 118490
WBS: POM02B_3.02.04.04 Half detector Assembly Readout and Cooling Test at BNL |  |  |  |  | 2020-04-24 | 2022-03-17 |  |  | 1176 | 59290 | 1.8 | 5929 | 65219 |  |  | Budgeted Cost |  | 29067 | 17786 | 12437
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123500 | Test Half Barrel #1 | 2021-12-06 | 2021-12-27 | MECHENG4 LBNL | LBNL | 24 | 6219 | 0.1 | 622 | 6840 | PROF | Labor | Budgeted Cost |  |  |  | 6219
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123500 | Test Half Barrel #1 | 2021-12-06 | 2021-12-27 | POSTD LBNL | LBNL | 120 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123500 | Test Half Barrel #1 | 2021-12-06 | 2021-12-27 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123600 | Test Half Barrel #2 | 2021-12-28 | 2022-01-19 | MECHENG4 LBNL | LBNL | 24 | 6219 | 0.1 | 622 | 6840 | PROF | Labor | Budgeted Cost |  |  |  | 6219
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123600 | Test Half Barrel #2 | 2021-12-28 | 2022-01-19 | POSTD LBNL | LBNL | 120 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123600 | Test Half Barrel #2 | 2021-12-28 | 2022-01-19 | STAFFPHYS LBNL | LBNL | 24 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | TECH4 MIT | MIT | 80 | 10729 | 0.1 | 1073 | 11802 | TECH | Labor | Budgeted Cost |  |  | 10729
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | SCI3 MIT | MIT | 40 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123700 | MVTX Full System Test at BNL | 2022-01-20 | 2022-03-17 | SCI3 LANL | LANL | 480 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123100 | Test RU at BNL | 2020-09-16 | 2020-09-29 | SCI3 LANL | LANL | 32 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123100 | Test RU at BNL | 2020-09-16 | 2020-09-29 | PROF4 LANL | LANL | 32 | 10069 | 0.1 | 1007 | 11075 | PROF | Labor | Budgeted Cost |  | 10069
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123200 | Test FELIX at BNL | 2020-06-23 | 2020-07-07 | SCI3 LANL | LANL | 32 | 0 | 0.1 | 0 | 0 | SCI | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123200 | Test FELIX at BNL | 2020-06-23 | 2020-07-07 | PROF4 LANL | LANL | 32 | 10069 | 0.1 | 1007 | 11075 | PROF | Labor | Budgeted Cost |  | 10069
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123300 | Test PS at BNL | 2020-04-24 | 2020-05-07 | POSTD LBNL | LBNL | 20 | 0 | 0.1 | 0 | 0 | STUD | Labor | Budgeted Cost
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123300 | Test PS at BNL | 2020-04-24 | 2020-05-07 | ELENG3 LBNL | LBNL | 20 | 3726 | 0.1 | 373 | 4098 | PROF | Labor | Budgeted Cost |  | 3726
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123100 | Test RU at BNL | 2020-09-16 | 2020-09-29 | ElectEng UTAustin | UTAustin | 16 | 2602 | 0.1 | 260 | 2862 | PROF | Labor | Budgeted Cost |  | 2602
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123200 | Test FELIX at BNL | 2020-06-23 | 2020-07-07 | ElectEng UTAustin | UTAustin | 16 | 2602 | 0.1 | 260 | 2862 | PROF | Labor | Budgeted Cost |  | 2602
POM02B_3.02.04.04 | 02.04.04 | Half detector Assembly Readout and Cooling Test at BNL | S123400 | Assemble & Test Cooling System at BNL | 2021-03-09 | 2021-03-29 | PROF4 MIT | MIT | 40 | 7056 | 0.1 | 706 | 7762 | PROF | Labor | Budgeted Cost |  |  | 7056