## Slide 1: Review Documents
WBS, BOE
PMP
sPHENIX/MVTX Risk Register
MVTX P6
MVTX full proposal
Review charge
Previous Review reports
  4/2019
  7/2018

## Slide 2: sPHENIX MVTX Cost and Schedule Review MVTX Overview
Ming Liu, LANL
July 29-30, 2019
BNL

## Slide 3: Outline
Physics of MVTX
Project scope
Costs, schedules & risk register
R&D highlights and risk mitigations
Previous review recommendations
Issues and concerns

## Slide 4: MVTX Enabes Exciting Science
sPHENIX is the next flagship heavy ion physics experiment in the US (NSAC LRP2015)
  Jets
  Upsilons
  B-jets and B hadrons
MVTX will complete QGP heavy flavor physics
  Precision study of the “inner workings of QGP”(LRP15)
  Unambiguous determination of key parameters of QGP properties and interactions
complement & extend current and future RHIC and LHC QGP programs
sPHENIX 3 Physics Pillars
Jets
Upsilons
B
D
PRL 108 (2012) 022301
http://arxiv.org/pdf/1501.06197v1.pdf

## Slide 5: The sPHENIX 3rd Science Pillar
Heavy quarks – unique probe of QGP w/ new scales, mc, mb
  Study mass dependence
    Jet quenching & energy loss
    Flow – interaction with medium
  Access QGP properties
    Temperature, density, coupling, transport coefficients, viscosity etc.
MeV
1
10
102
103
104
mu md
LQCD
TQGP
mc
mb
Tc
ms
“B meson and b-jet modification”
“B meson and b-jet flow”

## Slide 6: MVTX Detector – Modified from ALICE/ITS Design
3-layer sensor barrel
- 48 staves, 432 chips
Service cone: signal, power, cooling
and mechanical support
MVTX
parameters
End-Wheel
CYSS: Cylindrical Shell Structure
Extended power FPC

## Slide 7: Scope of the MVTX Project – WBS 3.2
MVTX sensor & Electronics
  Readout Integration
    Frontend: ALICE/ITS RU
    Backend: ATLAS FELIX
  Detector assembly in US: ~$5M
    QA & assembly
      RU boards @UT-A
      Half detectors @LBNL
      FELIX boards @LANL/BNL,
      Ancillary systems - “adopt” ALICE ITS system
      Power, slow control & monitoring etc.
Mechanical system
  Modify ALICE/ITS mechanical structures
    End Wheels
    Cylindrical structure shells
    Service half barrels
  Mechanical system integration,
    Design & simulations, MIT/LANL
    Composite structure production, LBNL
    Non-composite structure, MIT
    Installation tooling etc., BNL/LANL/MIT/LBNL
  Adopt ALICE cooling plant design
    Modifications to fit sPHENIX, MIT/BNL
  Production @CERN: $1.36M, a separate BNL project
  - 84 ALICE/ITS-IB (modified) staves from CERN
    Acceptance test @LBNL, 48+spares(2-inner layers+)
  - 60 ALICE/ITS-RU from CERN
    Acceptance test @UT-Austin, 48+spares(12)

## Slide 8: MVTX Readout, Power and Controls
Power Board
Flex PCB Filtering Capacitors
Samtec Twinax “FireFly”, ~10m
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN bus
CAEN Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
sPHENIX Data Aggregation Module(DAM)
Jo’s talk

## Slide 9: MVTX Global Mechanical System Integration
L = 350.0 cm
MVTX system preliminary design, with two parts:
  Part-1: from MVTX to PP-1b, all power PCB, 40cm
  Part-2: length TBD later, from PP-1b to PP-2
TPC
TPC
R= 209.6cm
INTT
MVTX
PP-1a:
short signal cables
PP-2:
Signal and power cables
PP-1b:
power cables
Service Barrel
Walt and Camelia’ talks

## Slide 10: Preliminary Mechanical Design Completed
https://indico.bnl.gov/event/6377/
MVTX, INTT, TPC …
Camelia’ talk

## Slide 11: MVTX Organization Chart

## Slide 12: Cost Drivers
Dave and Irina’s talks

## Slide 13: Schedules & Milestones

## Slide 14: MVTX Schedules and Milestones (3/2019)
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Install half barrels
@sPHENIX IR
Ready for beam;
sPHENIX day-1 run
FELIX
production
Barrel Assembly & Testing @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Global integration
/interface design
design & procure
interface to
sPHENIX rails
Design & procure
sPHENIX rails
Funding delays –
Stave production delayed at CERN
- Impact on following test & assembly
- preparation work @LBNL, UT-A
Lack of R&D $ for mech. design work
- MIT, LBNL, LANL
- “advanced cash” running out MIT, LANL
Running low in schedule contingency …

## Slide 15: Project Status & Highlights
Confirmed long SamTec readout cables recently – last key integration R&D
  11.4m long cables, > 10m desired length
MVTX mechanical design: excellent progress
  Asked for quotes from outside companies based on preliminary designs
  sPHENIX integration workfest scheduled 7/10 @BNL, MVTX/INTT/TPC…
Release of early R&D fund in progress
  MVTX mechanical engineering design, MIT/LANL
  Preparation for Stave and RU acceptance test, LBNL, UT-Austin
MVTX Cost & Schedule Review – we are ready for full production
  July 29-30 @BNL
  WBS, PMP, Risk Registry, P6 being updated
Stave and RU production at CERN
  DOE Fund arrived at UTK/US-ALICE
  Procurement in progress
    CERN is ready to proceed with stave production
    60 MVTX/sPHENIX RUs delivered to CERN
  Power mezzanine and transition boards produced at UT-A

## Slide 16: Engineering & Technology Readiness
Sensor modification and system integration
  MVTX & INTT integration
Readout Electronics
  RU, PU, FELIX, Readout cable
  Power system
Mechanical system
  Detector design
  Service & integration
Detector assembly

## Slide 17: Very Successful Test Beam @Fermilab 5/20-25, 6/17-22, 2019
4 staves
2 RUv1.1
1 PU
1 FELIX Server + RCDAQ
sPHENIX GTM
11.4m Custom SamTec Cable
Negative pressured cooling for staves
120GeV p-beam
10kHz (30kHz)
Beam intensity:
30k ~ 120k ppp
RU-2: 1 stave
RU-1: 3 staves
FELIX
GTM
SamTec: 11.4m
(2.6m+8.8m)
5m SamTec
Data & Control
Beam Trigger
4-stave telescope
Timing & Trigger
RCDAQ
Online Monitoring
- 1 fully functioning
9-chip stave;
- 3 staves with a few
broken sensors
A full system with final sensor/readout* hardware:
Multi-Stave + Multi-RU -> FELIX readout demonstrated
sPHENIX GTM integrated
Long readout SamTec cable certified
Cooling system demonstrated
* RUv1.1 identical to the final RUv2 electrically

## Slide 18: 2019 MVTX Test Setup
From view
Stave housing (four staves)
beam
Stave housing sits on a motion table which can be moved in (x, y) plane perpendicular to the nominal beam direction. It can also be rotated (+40, -40) degrees (see photo on right). Operation was done at counting house.

## Slide 19: MVTX Readout and Power Cable Route
sPHENIX MVTX: 7.9+m
  Cable-A: 1.4 m
  Cable-B: 6.5+ m
  Power cable:4.7+ m
PWR
RU
PU
Desired <~10m;
Tested 11.4m
BNL has approved “non-halogen free” cables for sPHENIX

## Slide 20: Detector Misalignment & Hit Spatial Resolution
Typically staves offset by,
Horizontally: 20 x 30um = 600 um
Vertically: 5 x 30 um = 150 um
Hit spatial resolution:
peak_sigma_core = 0.55 (pixel size ) =15 um
Chip spatial resolution = 15/sqrt(2) = 11 um
Ref plane
Delta_X/Y

## Slide 21: Recommendations from April Director’s Review

## Slide 22
Report from April BNL PD2/3 Reviews: Silicon Detectors - MVTX, INTT

## Slide 23
MVTX Risks - all in P6 now
WBS, PMP documents updated
Schedule & Labor profile updated in P6
(Glenn, Irina )
Need project fund NOW to meet the goals!

## Slide 24: Issues and Concerns
Need project fund NOW to meet the goals!

## Slide 25: Summary
MVTX is ready to receive fund for the project
  Electrical system is ready for production
  Preliminary detector mechanical design completed
  Preliminary sPHENIX mechanical system integration developed
Costs, schedules and risk register integrated into sPHENIX P6
Project management plan developed

## Slide 26: Back Up

## Slide 27: MVTX Schedules and Milestones (3/2019)
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Install half barrels
@sPHENIX IR
Ready for beam;
sPHENIX day-1 run
FELIX
production
Barrel Assembly & Testing @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Global integration
/interface design
design & procure
interface to
sPHENIX rails
Design & procure
sPHENIX rails
Funding delays –
Stave production delayed at CERN
- Impact on following test & assembly
- preparation work @LBNL, UT-A
Lack of R&D $ for mech. desgin work
- MIT, LBNL, LANL
- “advanced cash” running out MIT, LANL
Running low in schedule contingency …

## Slide 28: The TB Team @Fermilab
Matt, Hubert, Cameron, Gerd, Zongze,
Xuan, Xiaochun, photo by Ming
Sho, AlexT
Not shown: Sanghoon, Yasser, Martin, Walt,
Abel. Chris …
Data taking shift in the evenings: 7PM – 7AM
Beam: every other Monday –Friday 8:00AM – 8AM

## Slide 29: MVTX 4-Stave Telescope

## Slide 30
Beam angle: 0
(eta ~0)
Beam angle: 40
(eta ~1)
MVTX 4-Stave Telescope
Offline analysis in progress: all TB data in RCF
https://wiki.bnl.gov/sPHENIX/index.php/MAPS-based_Vertex_Detector_(MVTX)

## Slide 31: Tested New MVTX Long SamTec Readout Cables 8.8m + 2.6m = 11.4m (10m desired for sPHENIX; ALICE 8m cables)

## Slide 33: Offline Analysis: Cluster size vs Angle
@ 0-degree
Cluster Size ~ 2.4
@ 40-deg
Cluster Size ~ 3.0
To calibrate MC simulations and tracking
Stave geometry, alignment
Clustering

## Slide 34: Staves - General layout
Staves: detector modules consisting of a Hybrid Integrated Circuit (HIC) mounted on carbon fiber mechanical support structure
HIC: a row of 9 ALPIDE sensors wire-bonded to a Flexible Printed Circuit (FPC). Area covered by the chips: 15x271.2 mm2, including a gap of 150 μm between adjacent chips.
Mechanical support: single light structure composed of a Space Frame, providing the required stiffness, and a Cold Plate, high-thermal conductivity carbon fiber sheet with embedded polyamide cooling pipes.
Heat Dissipation – The ALPIDE sensors dissipate only 40 mW/cm2.
FPC
9 sensors
Space frame
Cold plate
Stave prototype
Stave design developed by ALICE at no cost for MVTX project
Possible modifications (see Walter’s talk)

## Slide 35: backup

## Slide 36: The L3 Component

## Slide 37: L3 Technical Overview
Emphasize any technical issues that still need to be resolved. If all has been decided put it on the slide.

## Slide 38: L3 Scope
What are you building?
Where you fit in the L2

## Slide 39: L3 Collaborators

## Slide 40: Schedule Drivers

## Slide 41: Cost Drivers

## Slide 42: Status and Highlights
Recent technical accomplishments

## Slide 43: Issues and Concerns