## Slide 1: Review Documents
WBS, BOE
PMP
sPHENIX/MVTX Risk Register
MVTX P6
MVTX full proposal
Review charge
Previous Review reports
  4/2019
  7/2018

## Slide 2: sPHENIX MVTX Cost and Schedule Review MVTX Overview
Ming Liu, LANL
July 29-30, 2019
BNL

## Slide 3: Outline
Physics of MVTX
Project scope
Costs, schedules & risk register
R&D highlights and risk mitigations
Previous review recommendations
Issues and concerns

## Slide 4: MVTX Enables Exciting Science
sPHENIX is the next flagship heavy ion physics experiment in the US (NSAC LRP2015)
  Jets
  Upsilons
  B-jets and B hadrons
MVTX will complete QGP heavy flavor physics
  Precision study of the “inner workings of QGP”(LRP15)
  Unambiguous determination of key parameters of QGP properties and interactions
complement & extend current and future RHIC and LHC QGP programs
sPHENIX 3 Physics Pillars
Jets
Upsilons
B
D
PRL 108 (2012) 022301
http://arxiv.org/pdf/1501.06197v1.pdf

## Slide 5: The sPHENIX 3rd Science Pillar
Heavy quarks – unique probe of QGP w/ new scales, mc, mb
  Study mass dependence
    Jet quenching & energy loss
    Flow – interaction with medium
  Access QGP properties
    Temperature, density, coupling, transport coefficients, viscosity etc.
MeV
1
10
102
103
104
mu md
LQCD
TQGP
mc
mb
Tc
ms
“B meson and b-jet modification”
“B meson and b-jet flow”

## Slide 6: MVTX Detector – Modified from ALICE/ITS Design
3-layer sensor barrel
- 48 staves, 432 chips
Service cone: signal, power, cooling
and mechanical support
MVTX
parameters
End-Wheel
CYSS: Cylindrical Shell Structure
Extended power FPC

## Slide 7: Scope of the MVTX Project – WBS 3.2
MVTX sensor & Electronics
  Readout Integration
    Frontend: ALICE/ITS RU
    Backend: ATLAS FELIX
  Detector assembly in US: ~$5M
    QA & assembly
      RU boards @UT-A
      Half detectors @LBNL
      FELIX boards @LANL/BNL,
  Ancillary systems - “adopt” ALICE ITS system
    Power, slow control & monitoring etc.
Mechanical system
  Modify ALICE/ITS mechanical structures
    End Wheels
    Cylindrical structure shells
    Service half barrels
  Mechanical system integration,
    Design & simulations, MIT/LANL
    Composite structure production, LBNL
    Non-composite structure, MIT
    Installation tooling etc., BNL/LANL/MIT/LBNL
  Adopt ALICE cooling plant design
    Modifications to fit sPHENIX, MIT/BNL
  Stave & RU Production @CERN: a separate BNL project
  - 84 ALICE/ITS-IB (modified) staves from CERN;
  48+spares(2-inner layers+10%)
  - 60 ALICE/ITS-RU from CERN
  48+spares(12, 25%)

## Slide 8: MVTX Readout, Power and Controls
Power Board
Flex PCB Filtering Capacitors
Samtec Twinax “FireFly”, ~10m
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN bus
CAEN Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
sPHENIX Data Aggregation Module(DAM)
Jo’s talk

## Slide 9: MVTX Global Mechanical System Integration
L = 350.0 cm
MVTX system preliminary design, with two parts:
  Part-1: from MVTX to PP-2, all power PCB, 40cm
  Part-2: length TBD later, from PP-2 to PP-3
TPC
TPC
R= 209.6cm
INTT
MVTX
PP-1:
short signal cables
PP-3:
Signal and power cables
PP-2:
power cables
Service Barrel
Walt and Camelia’ talks

## Slide 10: Preliminary Mechanical Design Completed
https://indico.bnl.gov/event/6377/
MVTX, INTT, TPC …
Camelia’ talk

## Slide 11: MVTX Organization Chart

## Slide 12: Collaborators
22+ institutions,
US and abroad
Active joint efforts with
ALICE ITS group
LANL
LBNL
CCNU
MIT
Yonsei
…

## Slide 13: Cost Drivers
Mechanical system:
Detector carbon structures
Service & integration
Electronics:
Backend
Power system
Dave talk

## Slide 14: Schedules & Milestones
Technically driven schedule
  Day-1 physics
  CERN production
  Fund available as needed
Funding delay
  R&D
  Production
  Preparation
Low schedule contingency
Early R&D by LANL LDRD

## Slide 15: Project Status & Highlights
Tested full stave readout chain with the final electronics at Fermilab Test Beam
  Tested long SamTec readout cables recently – last key integration R&D
  11.4m long cables, 10m desired
MVTX mechanical design: excellent progress
  Asked for quotes from outside companies based on preliminary designs
  sPHENIX integration workfest held 7/10 @BNL, MVTX/INTT/TPC
Release of early R&D fund in progress
  MVTX mechanical engineering design, MIT/LANL
  Preparation for Stave and RU acceptance test, LBNL, UT-Austin
MVTX Cost & Schedule Review – we are ready for full production
  WBS, PMP, Risk Registry updated
  Fully integrated into sPHENIX P6
Stave and RU production at CERN, in progress
  DOE Fund arrived at UTK/US-ALICE
  Procurement in progress
    CERN is ready to proceed with stave production
    60 MVTX/sPHENIX RUs delivered to CERN
  Power mezzanine and transition boards produced at UT-A

## Slide 16: Engineering & Technology Readiness
Stave modification and system integration - done
  MVTX & INTT integration
Readout Electronics - done
  RU, PU, FELIX, Readout cable
  Power system
Mechanical system – preliminary design available
  Detector design
  Service & integration
Detector assembly and installation – plan developed
  Follow ALICE ITS procedures

## Slide 17: Very Successful Test Beam @Fermilab 5/20-25, 6/17-22, 2019
4 staves
2 RUv1.1
1 PU
1 FELIX Server + RCDAQ
sPHENIX GTM
11.4m Custom SamTec Cable
Negative pressured cooling for staves
120GeV p-beam
10kHz (30kHz)
Beam intensity:
30k ~ 120k ppp
RU-2: 1 stave
RU-1: 3 staves
FELIX
GTM
SamTec: 11.4m
(2.6m+8.8m)
5m SamTec
Data & Control
Beam Trigger
4-stave telescope
Timing & Trigger
sPHENIX
RCDAQ
Online Monitoring
- 1 fully functioning
9-chip stave;
- 3 staves with a few
broken sensors
A full system with final sensor/readout* hardware:
Multi-Stave + Multi-RU -> FELIX readout demonstrated
sPHENIX GTM integrated
Long readout SamTec cable certified
Cooling system demonstrated
* RUv1.1 identical to the final RUv2 electrically

## Slide 18: 2019 MVTX Test Beam Setup @Fermilab
From view
Stave housing (four staves)
beam
Stave housing sits on a motion table which can be moved in (x, y) plane perpendicular to the nominal beam direction. It can also be rotated (+40, -40) degrees (see photo on right). Operation was done at counting house.

## Slide 19: Long Custom MVTX Readout Cables Tested
sPHENIX MVTX: 7.9+m
  Cable-A: 1.4 m
  Cable-B: 6.5+ m
  Power cable:4.7+ m
PWR
RU
PU
Desired <~10m;
Tested 11.4m
BNL has approved “non-halogen free” cables for sPHENIX

## Slide 20: Detector Misalignment & Hit Spatial Resolution Study
Typically staves offset by,
Horizontally: 20 x 30um = 600 um
Vertically: 5 x 30 um = 150 um
Hit spatial resolution:
Peak_sigma_core = 0.55 (pixel size ) =15 um
Chip spatial resolution = 15/sqrt(2) = 11 um
(same as 2018 TB results)
Ref plane
Delta_X/Y

## Slide 21: Recommendations from April Director’s Review

## Slide 22
Report from April BNL Director’s PD2/3 Reviews: Silicon Detectors - MVTX, INTT
MVTX Risks fully integrated into sPHENIX,
- Irina’s talk
MVTX PMP fully
developed
WBS & Critical Paths etc. documented in P6
- 3-D mock-up demonstrated;
- Detailed FTE profile in P6
sPHENIX follows the same ITS/IB stave QA Gold/Silver standard, about 50-50 for ITS;
Latest production had higher yield of gold, ~>65%

## Slide 23
MVTX Risks, WBS/BOE integrated into sPHENIX
Critical path and milestones in P6
PMP documents updated, change control et.
Schedule & Labor profile updated in P6
Early R&D funding needs submitted to BNL,
MIT, LBNL, LANL, UT-A, work in progress
BNL owns/oversees the contingency
Stave handling follows ITS practice to avoid
possible metal particulate generation
- Report to sPHENIX office on progress and issues
Need project funding NOW!

## Slide 24: Issues and Concerns
Lack of early funding for critical R&D to reduce risk & contingency
  Carbon structure design, MIT, LANL
  Carbon structure cost estimate, LBNL
  Preparation for Stave and RU acceptance and QA in US, LBNL, UT-Austin
Funding delay and reduced schedule contingency
  Stave and RU production delayed
  Delays in preparation for Stave and RU test
Carbon structure production cost and schedule
  LBNL, other production activities/ATLAS
  Explore other production sites, Italy, France, Korea, US …
  High contingency in cost, ~40%
MVTX mechanical integration
  Beam pipe modification
  High contingency in design cost, ~40%
MVTX readout integration
  sPHENIX DAQ and Trigger system not final yet

## Slide 25: Summary
MVTX is ready to receive fund for the project
  Electrical system is ready for production
  Preliminary detector mechanical design completed
  Preliminary sPHENIX mechanical system integration developed
Costs, schedules and risk register integrated into sPHENIX P6
Project management plan developed, baseline change control etc. defined
Funding is critical to meet the day-1 goal
We are ready to start the project

## Slide 26: Back Up & References

## Slide 27: MVTX Full Proposal
Pre-proposal submitted to DOE, 2/2017
  Follow-up discussions with DOE and BNL managers
  Weekly proj. leaders’ meeting, BNL/LANL/LBNL/MIT
Full proposal submitted to BNL ALD, Feb 2018
  Expanded science + Cost & Schedule
  Assumed funding starts in FY18
A growing collaboration
  22+ institutions from US and abroad
Adapt ALICE ITS Upgrade Inner Barrel 3-layer MAPS detector
  Mini. risk, Max. Physics
Precision vertexing for b-jet/B-hadron tagging in HI with high efficiency and high purity
B-jet modification in QGP at low-medium pT to determine QGP properties, study mass-dependence on collisional vs radiative energy loss, flow etc.
Early R&D by LANL LDRD, $5M, FY17-19, readout, mechanical design and physics; established LANL-ALICE MoU in 12/2016 for joint R&D and training

## Slide 28
7/23/2019, V3

## Slide 32
MVTX Labor FTE by FY, Institution

## Slide 36
MVTX
MVTX

## Slide 37: MVTX Schedules and Milestones (3/2019)
CY-2018 | 2019 | 2020 | 2021 | 2022 | 2023
Stave & RU
production
Power system
production
Detector mechanics design & production, global interface to sPHENIX
Service barrel
design & production
End Wheels
CYSS
Half barrel #1
Half barrel #2
Half barrels
arrive @BNL
MVTX installation & commissioning @BNL
RU, FELIX, PS, cables etc.
Install half barrels
@sPHENIX IR
Ready for beam;
sPHENIX day-1 run
FELIX
production
Barrel Assembly & Testing @LBNL
sPHENIX: CD1/3a PD2/3
MVTX
1st collisions
Installation
Global integration
/interface design
design & procure
interface to
sPHENIX rails
Design & procure
sPHENIX rails
Funding delays –
Stave production delayed at CERN
- Impact on following test & assembly
- preparation work @LBNL, UT-A
Lack of R&D $ for mech. desgin work
- MIT, LBNL, LANL
- “advanced cash” running out MIT, LANL
Running low in schedule contingency …

## Slide 38: MVTX: Monolithic-Active-Pixel-Sensor-based VerTeX Detector
sPHENIX Inner Tracking
“Adopt” ALICE/ITS
Mini. risk,
Max. physics
sPHENIX@RHIC (2023+)
ALICE ITS Upgrade @CERN;
Inner Tracker System (2021+)
Key integration tasks:
Readout
Mechanics
MVTX could also be a day-1 EIC detector

## Slide 39: B-Hadron & b-Jet Tagging
Physics Reminder
Detected using the long lifetime of bottom quark hadrons:
  Displaced tracks
  Large 2nd vertex invariant mass
Need high precision tracking and vertex determination – MVTX!
Need excellent jet detection capabilities – sPHENIX!

## Slide 40: Monolithic-Active-Pixel-Sensors (MAPS) The next Generation State of the Art Pixel Tracker
Advantages of ALICE MAPS/ALPIDE:
  Very fine pitch (28x28 μm)
  High efficiency (>99%) and low noise (<10-6)
  Time resolution, as high as ~5 μs
  Ultra-thin/low mass, 50μm (~0.3% X0)
  On-pixel digitization, low power dissipation
An ideal detector for QGP physics!
50 μm
28 μm
ALPIDE design
FPC
9 Chips
Cooling plate
A 9-chip MAPS stave, 1.5 x 27cm2

## Slide 41: ALPIDE/MAPS Operation
Well fit sPHENIX/RHIC environment, 10MHz Clock (LHC 40MHz)
DV=Q/C
v
t
PIX_IN
tr> 100 μs
tf~= 10 ns
OUT_D
STROBE
~5-6 ms
~5-6 μs
v
t
OUT_A
threshold
sPHENIX trigger latency: ~4 μs
shaping time: 2, 5, 10 … μs

## Slide 42: MVTX Full Readout Chain Demonstrated 2018 TB@Fermilab
Readout Unit configures Stave using USB interface
FELIX distributes clock to Readout Unit
Readout Unit distributes clock to the Stave
Stave is triggered, sends data at 1.2Gb/s
Configured GBT link to recover clock from FELIX
Readout Unit receives the data and sends the data to FELIX over fiber using GBT link
FELIX packs data, stores it on disk using RCDAQ - the sPHENIX data format and software
Readout
Unit
Stave
FELIX
Server + FELIX
Readout Unit + Stave

## Slide 43: MVTX Test Beam at Fermilab 02/20-03/10, 2018
Goals:
  Test full readout chain
  Evaluate ALPIDE sensor performance
Experimental setup
  A 4-sensor telescope
  Full readout chain: MAPS+RU+FELIX+RCDAQ
Parasitic with INTT run
Very productive & collaborative
120 GeV
proton
4-sensor
Telescope

## Slide 44: Fermilab Test Beam Results (I)
4-hit track
Cluster size: 2.1 ~ 2.4
Mostly single tracks
4-sensor telescope
# of tracks per event
Cluster size
120 GeV proton beam
Beautiful analysis done by Sanghoon and Darren + others

## Slide 45: Fermilab Test Beam Results (II)
Hit Efficiency > 99.5%
Pixel size (~28um)
Hit Spatial Resolution: < 5 um

## Slide 46: The TB Team @Fermilab, 2019
Matt, Hubert, Cameron, Gerd, Zongze,
Xuan, Xiaochun, photo by Ming
Sho, AlexT
Not shown: Sanghoon, Yasser, Martin, Walt,
Abel. Chris …
Data taking shift in the evenings: 7PM – 7AM
Beam: every other Monday –Friday 8:00AM – 8AM

## Slide 47: MVTX 4-Stave Telescope

## Slide 48
Beam angle: 0
(eta ~0)
Beam angle: 40
(eta ~1)
MVTX 4-Stave Telescope
Offline analysis in progress: all TB data in RCF
https://wiki.bnl.gov/sPHENIX/index.php/MAPS-based_Vertex_Detector_(MVTX)

## Slide 49: Tested New MVTX Long SamTec Readout Cables 8.8m + 2.6m = 11.4m (10m desired for sPHENIX; ALICE 8m cables)

## Slide 50: Offline Analysis: Cluster size vs Angle
@ 0-degree
Cluster Size ~ 2.4
@ 40-deg
Cluster Size ~ 3.0
To calibrate MC simulations and tracking
Stave geometry, alignment
Clustering

## Slide 51: Staves - General layout
Staves: detector modules consisting of a Hybrid Integrated Circuit (HIC) mounted on carbon fiber mechanical support structure
HIC: a row of 9 ALPIDE sensors wire-bonded to a Flexible Printed Circuit (FPC). Area covered by the chips: 15x271.2 mm2, including a gap of 150 μm between adjacent chips.
Mechanical support: single light structure composed of a Space Frame, providing the required stiffness, and a Cold Plate, high-thermal conductivity carbon fiber sheet with embedded polyamide cooling pipes.
Heat Dissipation – The ALPIDE sensors dissipate only 40 mW/cm2.
FPC
9 sensors
Space frame
Cold plate
Stave prototype
Stave design developed by ALICE at no cost for MVTX project
Possible modifications (see Walter’s talk)

## Slide 52: sPHENIX DAQ Architecture
DCM
DCM
DCM
DCM2
SEB
SEB
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Rack Room
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
Event Builder
SEB
EBDC
FELIX
EBDC
FELIX
EBDC
FELIX
Network
Switch
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
Buffer Box
Buffer Box
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
To the
RACF/HPSS
Calorimeters,
INTT, MBD
TPC, MVTX
SEB Sub-Event Buffer
EBDC Event Buffer and Data Compressor
ATP Assembles events and compresses data
Buffer Box data interim storage before sending data to the computing center

## Slide 53: Backup - 2

## Slide 54: The L3 Component

## Slide 55: L3 Technical Overview
Emphasize any technical issues that still need to be resolved. If all has been decided put it on the slide.

## Slide 56: L3 Scope
What are you building?
Where you fit in the L2

## Slide 57: L3 Collaborators

## Slide 58: Schedule Drivers

## Slide 59: Cost Drivers

## Slide 60: Status and Highlights
Recent technical accomplishments

## Slide 61: Issues and Concerns