## Slide 1: Review Documents Available on the Agenda Page
MVTX BOE
MVTX PMP
sPHENIX/MVTX Risk Register
MVTX P6 dump, w/ Gantt Chart
MVTX full proposal
RU acceptance QA plan
Stave acceptance QA plan
MVTX Pre-P6 WBS Dictionary
MVTX C&S Review Charge
Previous Review reports
  BNL Director’s Review 4/2019
https://indico.bnl.gov/event/6544/

## Slide 2: Today’s Presentations
Overview of the MVTX's Place in sPHENIX- Ed
MVTX Overview – Ming, #1-4
Cost & Schedule – Dave, #1-4
MVTX in sPHENIX P6 and Risk Registry – Irina, #2-4
MVTX mechanical design – Walt, #1-3
MVTX Service Barrel and Integration – Camelia, #1-3
MVTX Detector QA and Assembly – Yuan, #1-3
MVTX Readout – Jo, #1-3
R&D and Beam Test Results – Cameron, #1,2
Summary – Ming, #4

## Slide 3: sPHENIX MVTX Cost and Schedule Review MVTX Overview
Ming Liu, LANL
July 29-30, 2019
BNL

## Slide 4: Outline
Physics of MVTX
Project scope, PMP
Costs, schedules & risk register
R&D highlights
Previous review recommendations
Issues and concerns

## Slide 5: MVTX Enables Exciting Science
sPHENIX is the next flagship heavy ion physics experiment in the US (NSAC LRP2015)
  Jets
  Upsilons
MVTX: Open heavy flavor physics – the 3rd physics pillar
  Precision study of the “inner workings of QGP”(LRP15)
  Quantitative determination of key parameters of QGP properties and interactions
sPHENIX 3 Physics Pillars
Jets
Upsilons
B
D
PRL 108 (2012) 022301
http://arxiv.org/pdf/1501.06197v1.pdf

## Slide 6: The sPHENIX 3rd Science Pillar
Heavy quarks – unique probe of QGP w/ new scales, mc, mb
Study mass dependence
  Jet quenching & energy loss
  Flow – interaction with medium
Access QGP properties
  temperature and momentum dependence of QGP transport parameters
MeV
1
10
102
103
104
mu md
LQCD
TQGP
mc
mb
Tc
ms
“B meson and b-jet modification”
“B meson and b-jet flow”
From MVTX
proposal

## Slide 7: Monolithic-Active-Pixel-Sensors (MAPS) The next Generation State of the Art Pixel Tracker
Advantages of ALICE MAPS/ALPIDE:
  Very fine pitch (28x28 μm)
  High efficiency (>99%) and low noise (<10-6)
  Time resolution, as high as ~5 μs
  Ultra-thin/low mass, 50μm (~0.3% X0)
  On-pixel digitization, low power dissipation
An ideal detector for QGP physics!
50 μm
28 μm
ALPIDE design
FPC
9 Chips
Cooling plate
Power density < 40 mW/cm2
A 9-chip MAPS stave, 1.5 x 27cm2

## Slide 8: MVTX Detector – Modified from ALICE/ITS Design
MVTX parameters: L = 271 mm
Service Barrel
CYSS: Cylindrical
Shell Structure
End-Wheels
3-layer sensor barrel
- 48 staves, 432 chips
All electronics are “as built” by ALICE/ATLAS
Modify the ALICE mechanics to fit it in sPHENIX

## Slide 9: Scope of the MVTX Project – WBS 3.02
Electronics (3.02.02)
  Readout Integration
    RU QA & assembly @UT-A
    Backend: ATLAS FELIX
    FELIX boards @LANL/BNL
    Frontend RU services: daughter cards, transition boards, cables etc.
  Ancillary systems - “adopt” ALICE ITS system
    Power, slow control & monitoring etc.
Mechanical system
  MVTX detector mechanical structures (3.02.03)
    Design & simulations
    End Wheels
    Cylindrical support structure
    Service barrels
  Mechanical system integration (3.02.04)
    Service barrel support & interface to sPHENIX
    Installation tooling etc.
    Adopt ALICE cooling parameters
    Detector safety
  Detector assembly (3.02.03.03)
    Stave QA & detector assembly @LBNL
BNL provides Staves & RUs, w/o cost to MVTX project:
- 84 ALICE/ITS-IB (modified) staves from CERN;
48+spares(2-inner layers+10%)
- 60 ALICE/ITS-RU from CERN
48+spares(12, 25%)
Early R&D by LANL LDRD $5M, FY17-19
Walt’s talk
Camelia’s talk
Jo’s talk
Yuan’s talk
Status: Ready for production
Status: Advanced CAD models
Status: Mature, following ITS
Status: Advanced CAD models
Off-project

## Slide 10: MVTX Scope – WBS Summary
Major Challenge: Mechanical System

## Slide 11: Project Management Plan
Draft PMP document completed
  Project baseline
    Physics
    Functional requirements/KPP
    Technical scope
    Cost breakdown
    Schedule
    Funding profile
    Planned BNL funding
    Baseline change control
  Management structure
    Organization and team
    Management responsibilities
    Participating institutions
  Project management and oversight
    Risk management
    Project reporting
    Engineering and technology readiness
    Quality assurance and configuration/document management
    Operation readiness plan
    ESSH plans and fabrication
    Project closeout
Project fully integrated into sPHENIX P6
  Costs, schedules and risk register

## Slide 12: MVTX Deliverables in PMP
*: The staves and RUs are from BNL contribution, no cost to MVTX project.
Detectors + Services

## Slide 13: MVTX Performance Parameters: KPPs & UPPs
UPPs from
MVTX PMP
KPPs from
MVTX PMP

## Slide 14: Baseline Change Control in PMP
MVTX
MVTX

## Slide 15: MVTX Organization Chart

## Slide 16: Collaborators & Responsibilities
22+ institutions and growing
- “MOU” through sPHENIX collaboration
- Active joint efforts with ALICE ITS group

## Slide 17: MVTX Detector, Cost & Schedule

## Slide 18: MVTX Readout, Power and Controls
Power Board
Flex PCB Filtering Capacitors
Samtec Twinax “FireFly”, ~10m
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Front End
Regulated Power
FELIX
Back End
Data (9.6 Gb/s max)
Control
Trigger
Alpide Sensors
FPC
Cold Plate
regulators
Power
GBT Optical Links
9-sensor Stave
DCS
CAN bus
CAEN Power supplies
Power
Trigger & Clock
Interaction Region
Experimental Hall
Counting House
MVTX Detector Electronics consists of three parts
Sensor-Stave (9 ALPIDE chips) | Front End-Readout Unit | Back End-FELIX/DAM
one pixel
ALPIDE pixel:
Shaping
Digitization
Zero-suppression
3x buffer
ATLAS Front-End Link eXchange (FELIX):
sPHENIX Data Aggregation Module(DAM)
Jo’s talk
(BNL provides staves and RUs, at no cost to MVTX project)

## Slide 19: MVTX Global Mechanical System Integration
L = 350.0 cm
MVTX system preliminary design, with two parts:
  Part-1: from MVTX to PP-2, all power PCB, 40cm
  Part-2: length TBD later, from PP-2 to PP-3
TPC
TPC
R= 209.6cm
INTT
MVTX
PP-1:
short signal cables
PP-3:
Signal and power cables
PP-2:
power cables
Service Barrel
Walt and Camelia’ talks

## Slide 20: Cost Drivers
Mechanical system:
Detector carbon structures
Service & integration
Electronics:
Backend
Power system
LANL LDRD for early R&D
(off-project)
$5M, FY17-19
Readout integration
Detector conceptual design
Physics & simulations
Dave’s talk

## Slide 21: Labor Profile in P6
Irina’s talk

## Slide 22: Schedules & Milestones
Schedule drivers
  Day-1 physics
  CERN production
  Carbon structures
Early R&D by LANL LDRD
“PD4-like”
Closeout 12/2023
Fully aligned with sPHENIX via external milestones
Dave & Irina’s talks

## Slide 23: Risk Register

## Slide 24: Project Status & Highlights
Tested full stave readout chain with the final electronics at Fermilab Test Beam
  Tested long SamTec readout cables recently – last key detector integration R&D
  11.4m long cables, 10m desired
MVTX mechanical design: excellent progress
  Asked for quotes from outside companies based on preliminary designs
  sPHENIX integration workfest held 7/10 @BNL, MVTX/INTT/TPC
Early R&D achieved through LANL LDRD, $5M, FY17-19
  Readout integration
  Mechanical system conceptual design
Release of early BNL R&D fund in progress
  MVTX mechanical engineering design, MIT/LBNL
Project Management
  WBS, PMP, Risk Register updated
  Fully integrated into sPHENIX P6, aligned with sPHENIX schedule
  Will deliver MVTX on time and on budget under $5M
  We are ready to start the project

## Slide 25: Very Successful Test Beam @Fermilab 5/20-25, 6/17-22, 2019
4 staves
2 RUv1.1
1 PU
1 FELIX Server + RCDAQ
sPHENIX GTM
11.4m Custom SamTec Cable
Negative pressured cooling for staves
120GeV p-beam
10kHz (30kHz)
Beam intensity:
30k ~ 120k ppp
RU-2: 1 stave
RU-1: 3 staves
FELIX
GTM
SamTec: 11.4m
(2.6m+8.8m)
5m SamTec
Data & Control
Beam Trigger
4-stave telescope
Timing & Trigger
sPHENIX
RCDAQ
Online Monitoring
- 1 fully functioning
9-chip stave;
- 3 staves with a few
broken sensors
A full system with final sensor/readout* hardware:
Multi-Stave + Multi-RU -> FELIX readout demonstrated
sPHENIX GTM integrated
Long readout SamTec cable certified
Cooling system demonstrated
* RUv1.1 identical to the final RUv2 electrically

## Slide 26: 2019 MVTX Test Beam Setup @Fermilab
From view
beam
Stave housing sits on a motion table which can be moved in (x, y) plane perpendicular to the nominal beam direction. It can also be rotated (+40, -40) degrees (see photo on right). Operation was done at counting house.

## Slide 27: Recommendations from Last April Director’s Review
Review Report posted on the agenda page

## Slide 28
Report from April BNL Director’s PD2/3 Reviews: Silicon Detectors - MVTX, INTT (1)
Yes. MVTX design is sound and will meet the requirements.
- Readout electronics is ready for production;
- Preliminary mechanical system design completed
2. Yes. MVTX project is fully integrated into sPHENIX P6.
- Cost & Schedule, WBS, Risks register.
- RLS fully aligned with sPHENIX via external milestones
See Irina’s talk
3. Yes. MVTX risk register in sPHENIX Risks registry.
See Irina’s talk
4. Yes. MVTX project is fully integrated into sPHENIX P6,
- MVTX baseline is define and PMP is completed.
- RLS fully aligned with sPHENIX via external milestones
See Dave and Irina’s talks

## Slide 29
Report from April BNL Director’s PD2/3 Reviews: Silicon Detectors - MVTX, INTT (2)
1. MVTX Risk Register is fully integrated into sPHENIX,
- Irina’s talk
1. sPHENIX follows the same ITS/IB stave QA Gold/Silver standard (about 50-50 for ITS); Latest production had higher yield of gold, ~>70%
2. MVTX is fully integrated into sPHENIX P6, a list of milestones and critical paths are identified in P6.
- Irina’s talk
3. Pre-P6 MVTX WBS Dictionary was produced based on MS Project file that is used to integrate MVTX into the sPHENIX P6. Latest MVTX WBS and Critical paths are in P6. WBS Dictionary will be updated after this review.
- Irina’s talk
4. Detailed 3-D mockup was built and used to develop the MVTX mechanical design.
- Walt’s talk
5. MVTX is fully integrated into sPHENIX P6, cost and labor profiles are in P6
- Irina’s talk
5. Yes. MVTX is fully integrated into sPHENIX P6, and PMP is completed
6. Yes. ES&H document is completed.

## Slide 30
Report from April BNL Director’s PD2/3 Reviews: Silicon Detectors - MVTX, INTT (3)
MVTX project RLS is fully integrated into sPHENIX P6.
-Dave and Irina’s talks
BNL has agreed to provide early R&D fund to MIT and LBNL to
support mechanical system early R&D design work.
4. Much of the MVTX software work is based on the common
sPHENIX online and offline frameworks, work is mostly carried out
by collaborators without cost to the project.
5. Based on current RLS, MVTX detector will be ready for installation in March 2022; MVTX is the last detector to go into IR, currently scheduled in 9/2022.
-Dave and Irina’s talks
7. MVTX reporting is defined in PMP.
“Quarterly cost and schedule reviews and report the results to the sPHENIX Project Office. We will hold monthly phone calls with DOE-NP and provide them with Quarterly progress reports.”
8. WBS, BOE and Risk Register are integrated into sPHENIX P6. Pre-P6 WBS Dictionary will be updated after this review.
- Irina’s talk
9. MVTX project is integrated into sPHENIX P6, PMP developed.
- Irina’s talk
11. Beam pipe modification is under discussion between sPHENIX Project Office and C-AD. This risk is in the MVTX/sPHENIX Risk Register.
1,2,3. MVTX is fully integrated into sPHENIX P6, same methodology will be used for MVTX
4. MVTX PMP completed, including change control and configuration control methods.

## Slide 31
Report from April BNL Director’s PD2/3 Reviews: Silicon Detectors - MVTX, INTT (4)
5. MVTX early funding request submitted, and BNL has agreed to provide R&D fund to MIT and LBNL to carry out early R&D on mechanical structures.
Institution roles are developed in the PMP. “MOU” to be established through sPHENIX collaboration.
PMP completed, BNL will own and oversee the spending of the contingency.
MVTX risk register developed, integrated into the sPHENIX Risk Registry
MVTX project will follow the same stave/sensor handling procedures developed by ITS for stave and detector assembly;
KPPs and UPPs are documented in MVTX PMP.
The MVTX science case is well documented in the MVXT full proposal.
New developments are documented through sPHENIX physics and technical notes.

## Slide 32: Issues and Concerns
Carbon structure production cost and schedule
  LBNL, other production activities/ATLAS
  Explore other production sites, Italy, France, Korea, US …
  High contingency in cost, ~40%
Actions:
  Early R&D in mechanical design and fabrication to reduce uncertainties
  Work with OSI on integration, follow up closely with C-AD on the beampipe issue
Delay in stave/RU production
  Stave and RU production delayed
  Impact on MVTX assembly schedule

## Slide 33: Summary
MVTX is ready to receive fund for the project
  Electrical system is ready for production
  Preliminary detector mechanical design completed
  Preliminary sPHENIX mechanical system integration developed
LANL LDRD support critical for early key R&D
Costs, schedules and risk register integrated into sPHENIX P6, RLS aligned with sPHENIX
Project management plan developed, total cost $3.7M, with 26%(EU+Risk), ready for installation on time for Day-1 physics
We are ready to start the project!

## Slide 34: Back Up & References

## Slide 35: Critical Path

## Slide 36: Estimate Uncertainty
Labor
L1 - Actual - 0%
L2 - Level of Effort Tasks - 5%
L3 - Advanced - 10%
L4 - Preliminary - 25%
L5 - Conceptual - 40%
L6 - Pre-conceptual - 60%
L7 - Rough Estimate - 80%
L8 - Beyond state of the art - 100%
M&S
M1 - Existing Purchase Order (Actual) - 0%
M2 - Travel, supplies, software - 5%
M3 - Advanced, Quote or Catalog Price - 10%
M4 - Preliminary Engineering Judgment - 25%
M5 - Conceptual Design - 40%
M6 - Pre-conceptual Design - 60%
M7 - Pre-conceptual - Uncommon work - 80%
M8 - Beyond state of the art - 100%
EU tables are identical to those used by sPHENIX for establishing baseline cost

## Slide 37: Estimate Uncertainty by WBS

## Slide 38: Staves – QA plan
Tests run on sensors / staves
Example for building ML/OL modules but the tests run are the same for all sensors

## Slide 39: Engineering & Technology Readiness
Stave modification and system integration - done
  MVTX & INTT integration
Readout Electronics - done
  RU, PU, FELIX, Readout cable
  Power system
Mechanical system – preliminary design available
  Detector design
  Service & integration
Detector assembly and installation – plan developed
  Follow ALICE ITS procedures

## Slide 40: Long Custom MVTX Readout Cables Tested
sPHENIX MVTX: 7.9+m
  Cable-A: 1.4 m
  Cable-B: 6.5+ m
  Power cable:4.7+ m
PWR
RU
PU
Desired <~10m;
Tested 11.4m
BNL has approved “non-halogen free” cables for sPHENIX

## Slide 41: Detector Misalignment & Hit Spatial Resolution Study
Typically staves offset by,
Horizontally: 20 x 30um = 600 um
Vertically: 5 x 30 um = 150 um
Hit spatial resolution: (w/o clustering)
Peak_sigma_core = 0.55 (pixel size ) =15 um
Chip spatial resolution = 15/sqrt(2) = 11 um
(same as 2018 TB results)
Ref. Plane
Delta_X/Y
120GeV proton beam

## Slide 42: B-Hadron & b-Jet Tagging
Physics Reminder
Detected using the long lifetime of bottom quark hadrons:
  Displaced tracks
  Large 2nd vertex invariant mass
Need high precision tracking and vertex determination – MVTX!
Need excellent jet detection capabilities – sPHENIX!

## Slide 43: ALPIDE/MAPS Operation
Well fit sPHENIX/RHIC environment, 10MHz Clock (LHC 40MHz)
DV=Q/C
v
t
PIX_IN
tr> 100 μs
tf~= 10 ns
OUT_D
STROBE
~5-6 ms
~5-6 μs
v
t
OUT_A
threshold
sPHENIX trigger latency: ~4 μs
shaping time: 2, 5, 10 … μs

## Slide 44: Staves - General layout
Staves: detector modules consisting of a Hybrid Integrated Circuit (HIC) mounted on carbon fiber mechanical support structure
HIC: a row of 9 ALPIDE sensors wire-bonded to a Flexible Printed Circuit (FPC). Area covered by the chips: 15x271.2 mm2, including a gap of 150 μm between adjacent chips.
Mechanical support: single light structure composed of a Space Frame, providing the required stiffness, and a Cold Plate, high-thermal conductivity carbon fiber sheet with embedded polyamide cooling pipes.
Heat Dissipation – The ALPIDE sensors dissipate only 40 mW/cm2.
FPC
9 sensors
Space frame
Cold plate
Stave prototype
Stave design developed by ALICE at no cost for MVTX project
Possible modifications (see Walter’s talk)

## Slide 45: sPHENIX DAQ Architecture
DCM
DCM
DCM
DCM2
SEB
SEB
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Buffer Box
Rack Room
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
DCM2
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
DCM
DCM
DCM
FEM
Event Builder
SEB
EBDC
FELIX
EBDC
FELIX
EBDC
FELIX
Network
Switch
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
ATP
Buffer Box
Buffer Box
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
DCM
DCM
DCM
FEE
To the
RACF/HPSS
Calorimeters,
INTT, MBD
TPC, MVTX
SEB Sub-Event Buffer
EBDC Event Buffer and Data Compressor
ATP Assembles events and compresses data
Buffer Box data interim storage before sending data to the computing center