## Slide 1: sPHENIX MVTX Cost and Schedule Review Summary
Ming Liu, LANL
July 29-30, 2019
BNL

## Slide 2: Presentation Summary
Overview of the MVTX's Place in sPHENIX- Ed
MVTX Overview – Ming, #1-4
Cost & Schedule – Dave, #1-4
MVTX in sPHENIX P6 and Risk Registry – Irina, #2-4
MVTX mechanical design – Walt, #1-3
MVTX Service Barrel and Integration – Camelia, #1-3
MVTX Detector QA and Assembly – Yuan, #1-3
MVTX Readout – Jo, #1-3
R&D and Beam Test Results – Cameron, #1,2
Summary – Ming, #4

## Slide 3: MVTX Enables the 3rd Science Pillar
Open heavy flavor hadron & jet modification
Open heavy flavor hadron & jet flow
From measurements to
physics understandings

## Slide 4: MVTX Performance Parameters: KPPs & UPPs
UPPs from
MVTX PMP
KPPs from
MVTX PMP

## Slide 5: Very Successful R&D
MVTX sensor/stave & readout integration
  Full stave readout chain demonstrated with final electronics RU, PU, FELIX
  Stave modified for better MVTX/INTT integration; MVTX-INTT space-conflict resolved
  Long readout cables tested
  Verify MVTX KPP
MVTX mechanical design & system integration
  Preliminary detector design completed, 3D mockup demonstrated
  MVTX + INTT/sPHENIX integration design developed
  Assembly and installation plan developed
Jo, Cameron, Walt,
Camelia, Yuan et al.

## Slide 6: MVTX Deliverables in PMP
*: The staves and RUs are from BNL contribution, no cost to MVTX project.
Detectors + Services

## Slide 7: Review Charge

## Slide 8
Yes.
Based on R&D, quotes and experience
M&S and labor cost profile in P6
  Electrical system
  Detector mechanical system
  MVTX mechanical system integration
All previous talks

## Slide 9
Yes.
Based on R&D and experience
Milestones defined in PMP
Critical path identified
See Dave and Irina’s talks;
and all technical presentations
“PD4-like”
Closeout 12/2023

## Slide 10
Yes.
MVTX risk register in sPHENIX
Major risks identified and mitigation strategies developed
MVTX Risk Register in sPHENIX
See Dave and Irina’s talks;
and all technical presentations

## Slide 11
Yes.
PMP document completed
  Project baseline
    Physics
    Functional requirements/KPP/UPP
    Technical scope
    Cost breakdown
    Schedule
    Funding profile
    Planned BNL funding
    Baseline change control
  Management structure
    Organization and team
    Management responsibilities
    Participating institutions
  Project management and oversight
    Risk management
    Project reporting
    Engineering and technology readiness
    Quality assurance and configuration/document management
    Operation readiness plan
    ESSH plans and fabrication
    Project closeout
Project fully integrated into sPHENIX P6
  Costs, schedules and risk register
Ming and Dave’s talks
Ready to deliver MVTX on schedule and on budget!

## Slide 12: Summary
MVTX is ready to receive fund for the project
  Electrical system is ready for production
  Preliminary detector mechanical design completed
  Preliminary sPHENIX mechanical system integration developed
LANL LDRD support critical for early key R&D
Costs, schedules and risk register integrated into sPHENIX P6, RLS aligned with sPHENIX
Project management plan developed, TPC $4.6M, ready for installation on time for Day-1 physics
We are ready to start the project!

## Slide 13: Yes, we are ready!

## Slide 14: Back Up

## Slide 15: MVTX WBS

## Slide 16: Critical Path

## Slide 17: Estimate Uncertainty
Labor
L1 - Actual - 0%
L2 - Level of Effort Tasks - 5%
L3 - Advanced - 10%
L4 - Preliminary - 25%
L5 - Conceptual - 40%
L6 - Pre-conceptual - 60%
L7 - Rough Estimate - 80%
L8 - Beyond state of the art - 100%
M&S
M1 - Existing Purchase Order (Actual) - 0%
M2 - Travel, supplies, software - 5%
M3 - Advanced, Quote or Catalog Price - 10%
M4 - Preliminary Engineering Judgment - 25%
M5 - Conceptual Design - 40%
M6 - Pre-conceptual Design - 60%
M7 - Pre-conceptual - Uncommon work - 80%
M8 - Beyond state of the art - 100%
EU tables are identical to those used by sPHENIX for establishing baseline cost

## Slide 18: Estimate Uncertainty by WBS

## Slide 19: Risk Register