## Slide 1: MVTX Overview
Ming Liu
Los Alamos National Laboratory
For the sPHENIX MVTX Upgrade Group
BNL Director’s Review
August 2-4, 2017

## Slide 2: MVTX: MAPS-based Vertex Detector for sPHENIX
A separate upgrade project for the baseline sPHENIX experiment, with
Compelling Science
Feasible Cost & Schedule
Parallel Activities
MAPS-based Vertex Detector (MVTX)
Intermediate Silicon Strip Tracker (INTT)
MVTX BNL Director’s Review: July 10-11, 2017

## Slide 3: Outline
Science of MVTX detector
Scope of MVTX project
  Readout
  Integration
  Cost & schedule
Organization & plan

## Slide 4: Exciting Science
sPHENIX is the next flagship heavy ion physics experiment in the US (NSAC LRP2015)
  Jets
  Upsilons
  B-jets and B hadrons
MVTX will complete QGP heavy flavor physics
  Precision study of the “inner workings of QGP”(LRP15)
  Unambiguous determination of key parameters of QGP properties and interactions
complement & extend current and future RHIC and LHC QGP programs
sPHENIX 3 Physics Pillars
Jets
Upsilons
B
D
PRL 108 (2012) 022301
http://arxiv.org/pdf/1501.06197v1.pdf

## Slide 5: MVTX – Bring sPHENIX to a New Horizon
Unambiguously determine quark energy loss mechanisms, particularly over the interesting transition region, pT ~ M
  Radiative dE/dX
  Collisional dE/dX
  Other effects
Expectations @sPHENIX
Learned @CERN
B-hadron
sPH-HF-2017-002
sPHENIX
B-jet
sPH-HF-2017-001
QM’17
pT >> M
pT << M
sPHENIX

## Slide 6: Our Approach: MVTX
ALICE ITS Upgrade:
Inner Barrel Tracker
sPHENIX Inner Tracking
Adapt ITS/IB:
- Min. Risks
- Max. Phys.
Major challenges:
- Readout
- Mechanics
R = 23/32/39 mm
Z = 271 mm
J. Phys. G 41 (2014) 087002

## Slide 7: Monolithic-Active-Pixel-Sensors (MAPS) The next Generation State of the Art Pixel Tracker
Advantages of ALICE MAPS/ALPIDE:
  Very fine pitch (28x28 μm)
  High efficiency (>99%) and low noise (<10-6)
  Time resolution, as high as ~5 μs
  Ultra-thin/low mass, 50μm (~0.3% X0)
  On-pixel digitization, low power dissipation
An ideal detector for QGP physics!
50 μm
28 μm
ALPIDE design
FPC
9 Chips
Cooling plate
A 9-chip MAPS stave, 1.5 x 27cm2

## Slide 8: sPHENIX MVTX vs ALICE ITS/IB
 | ALICE (Run3) | sPHENIX (Max Collis.)
Pb+Pb / Au+Au | 100 kHz (50kHz) | 200 kHz
p+p | 400 kHz (200kHz) | 13 MHz
Trigger/Readout | >50 kHz | 15 kHz
sPHENIX
ALICE
Event track multiplicity dN/dη: sPHENIX = 1/3 ALICE (pp), 1/5 ALICE(AA)

## Slide 9: MVTX Readout and Control System
Power Board
Filtering
Capacitors
Samtec Twinax “FireFly”
9 Data (1.2Gbps)
1 Clock, 1 Control/Trigger
Readout Unit
Regulated Power
FELIX
Data (9.6 Gb/s max)
Control
Trigger
9 ALPIDE Sensors
FPC
Cold Plate
regulators
Power
5~10 m
GBT Optical Links
9-sensor Stave
sPHENIX GL-1 & GTM
DCS
CAN bus
Power supplies
Power
Trigger & Clock
LANL, UT-Austin, LBNL, BNL, ALICE/ITS …
ALPIDE Sensor

## Slide 10: MVTX Pre-proposal Submitted!
Pre-proposal submitted to DOE, 2/2017
  Follow-up discussions with DOE and BNL managers
  Weekly proj. leaders’ meeting, BNL/LANL/LBNL/MIT
Plan to update proposal to DOE, late 2017
  Expanded science + Cost & Schedule
  Assumed funding starts in FY18
  BNL Director’s Review, 7/10-11, 2017
A growing collaboration
  15+ institutions from US and abroad
Adapt ALICE ITS Upgrade Inner Barrel 3-layer MAPS detector
  Mini. risk, Max. Physics
Precision vertexing for b-jet/B-hadron tagging in HI with high efficiency and high purity
B-jet modification in QGP at low-medium pT to determine QGP properties, study mass-dependence on collisional vs radiative energy loss, flow etc.
Early R&D by LANL LDRD, $5M, FY17-19, readout, mechanical design and physics; established LANL-ALICE MoU for joint R&D and training

## Slide 11: Scope of the MVTX Project
MAPS Staves & Electronics
  Produce 68 ITS inner Barrel Staves
    No modification
  Readout Electronics R&D (LANL LDRD)
    Frontend: ALICE/ITS, RU
    Backend: ATLAS FELIX
    Modify/reprogram RU & FELIX for sPHENIX
  Production:
    Extend ALICE/ITS MAPS stave production
      WBS 1.5.3.1, LANL
      sPHENIX personnel help at CERN
    Reproduce additional ALICE/RU & ATLAS/FELIX
      WBS 1.5.2.1, UT-Austin
      WBS 1.5.2.2 , LANL
    Final assembly and test in US
      WBS 1.5.3, LBNL
  Ancillary systems, “adopt” ALICE system
    Power distribution, cables, crates, racks etc.,
      WBS 1.5.2.3, LBNL
    Slow control, safety and monitoring
Mechanics & Cooling
  Some changes to ALICE/ITS inner tracker mechanical structures, WBS 1.5.3
    End Wheels
    Cylindrical structure shells
    Detector half barrels
    Detector and Service half barrels
  Mechanical Integration, WBS 1.5.4
    Conceptual design by LANL LDRD
    Prototype by sPHENIX R&D, MIT/LANL
    Design integration frames
    Carbon frames etc., LBNL
    Installation tooling etc.
  Adopt ALICE cooling plant design
    Minor modification to fit sPHENIX
    Smaller heat load than ALICE ITS
  Metrology and Survey

## Slide 12: LDRD – MVTX Key Tasks/Milestones
RUv1.0/FELIX1.5 Integration
40MHz, 7/17-12/17
RUv1.x/FELIX2.0, 10MHz,
10/17 – 6/18
MVTX Design Review 7/2018
System test, cosmic & source
6/18 - 1/19
LDRD
MVTX: 2018 – 2021
Stave Production, procure FPGA, GBT etc.
8/18-4/19
7/17
10/17
10/18
10/19
Electronics Production
1/19-6/19
Test Beam, tracking performance
analysis, physics sim, NIM paper etc.
1/19 – 9/19
Today
BNL Director Review
7/10-11, 2017

## Slide 13: LANL LDRD Progress Highlights
LDRD Goals:
Complete MVTX readout design and development
Preliminary conceptual design of mechanical system integration
R&D status:
MOSAIC test bench in operation
  Single MAPS chip high-speed readout
  9-chip HIC/”stave” readout
  External trigger, cosmic and source
  Test data readout performance
    0.4, 0.6, 1.2Gb/sec
Firefly cable performance test
  5m (ALICE default)
  7m, 10m (favored for sPHENIX)
  Short extension cables, 20~30cm (share space with INTT), for mechanical system integration
Back end FELIX board installed & being tested
Front end Readout Unit boards available soon
FireFly cables
A MAPS
chip
MOSAIC test bench
9-chip
stave

## Slide 14: System Integration
MVTX+INTT

## Slide 15: Cost Basis – Major Items
Electronics (WBS 1.5.2): $1,285K
  ALICE ITS RU & PS
  ATLAS FELIX
  Power system and controls
  PHENIX/STAR/ALICE experience
MAPS and Detector (WBS 1.5.3): $2,900K
  ALICE ITS/IB production
  PHENIX/ALICE/STAR experience
Mechanical integration (WBS 1.5.4): $910K
  ALICE ITS inner tracker design modification
  FVTX/PHENIX, HFT/STAR experience
Total project cost: $5.7M, w/ 35% Cont.
x48
Updated material and labor cost and contingency from pre-proposal
- latest quotes on electronics and other R&D items

## Slide 16
Electronics
LANL
WBS - 1.5.2
Readout Units
UT Austin WBS 1.5.2.1
Back-end
LANL WBS 1.5.2.2
Power systems
LBNL WBS 1.5.2.3
Mechanics & Detector Assembly
LBNL - WBS 1.5.3
Staves
LANL WBS 1.5.3.1
Carbon Structures
LBNL WBS 1.5.3.2
Barrel Assembly
LBNL WBS 1.5.3.3
Integration & Infrastructures
MIT - WBS 1.5.4
Cooling
MIT WBS 1.5.4.2
Safety System
MIT WBS 1.5.4.3
Global Support
MIT WBS 1.5.4.4
MVTX
Principal Investigator: M. Liu (LANL)
Lead Coordinator: M. Chamizo-Llatas (BNL)
Co-investigators: G. Odyniec (LBNL),R. Redwine(MIT)
ES&H Liason: W. Sondheim (LANL)
Installation & Commissioning
LBNL/BNL WBS 1.5.4.6
sPHENIX integration
sPHENIX DAQ
Major institutions lead key tasks

## Slide 17
A growing collaboration!
new sPHENIX/MVTX members:
Czech groups: Charles Univ. and Inst. of Phys. of the Czech Academy of Sciences
  Stave production at CERN
CCNU – MAPS lab
  HICs assembly and test
  Mechanic integration
Potential collaborators:
USTC
  Physics simulations w/ LBNL
Peking Univ.
  Physics and detector simulations w/LANL
NCU, Taiwan
From MVTX pre-proposal

## Slide 18: Status, Plans and Issues
LANL- ALICE MoU
  Associate member of ALICE ITS Upgrade project
  Obtained ALICE readout test stand, MAPS sensors, staves and electronics for early R&D
  Obtained design files, electronics and mechanics
  Training sPHENIX personnel
High Level Agreement with ALICE – on going discussions
  Produce 68 staves for sPHENIX using ALICE/CERN facilities
Potential schedule/funding gap of stave production
  ITS/IB production: 7/2017 - 6/2018
  If funding significantly delayed, concerns over the availability of CERN facilities
  Risk Mitigation:
    Early training through LDRD effort, maintain activity at low level
    External foreign funding, CCNU Pixel Lab etc.
    Possible “mortgage” for sPHENIX production from ALICE/CERN with “Agreement”
sPHENIX readout and mechanical integration R&D
  Schedule risks due to unavailability of key R&D elements like staves and readout electronics
  MVTX/INTT integration
  Risk mitigation:
    Early joint R&D with ALICE as associate members
    Early R&D with prototype staves, RU and FELIX
    Early mechanical system integration R&D

## Slide 19: Project Tasks and Timeline
  Readout R&D
  Mech. design
  @LANL/ALICE/UT-A
Mech. Integr.
& Prototype
@LANL/MIT/LBNL
Key R&D
LDRD@LANL
FY2017
FY2018
FY2019
FY2020
FY2021
FY2016
CD-1?
CD-0
9/2016
Ready for
Beam, 2022?
Det. Install.
@BNL
Production
Detector Assembly
& Test @LBNL
MAPS Prod. & QA
@ALICE
Stave prod.&test @CERN;
C-Stru. Prod. @LBNL
“RU” & “FELIX”
Prod. @US
A schedule driven project!
ALICE ITS/IB
prod. ends
sPHENIX
baseline

## Slide 20: Summary from July 2017 MVTX BNL Directors Review
Exciting science - Xin
  New B-physics program @RHIC
Early ALICE & ATLAS R&D investment
  Reduce technical risk and R&D cost
LANL LDRD critical - Cesar
  mitigate risks and minimize contingency
No high risk R&D – Mark, Giacomo, Walt
  Readout
  Mechanics
  MVTX integration
Ready for sPHENIX Day-1 – Ed, Dave
  sPHENIX integration
  Cost & Schedule

## Slide 21: Backup

## Slide 22: A Multi-Year Plan: sPHENIX 2022-2026
Projected maximum collision rates:
  Au+Au: 200 kHz ( ~50 kHz, |Z|<10cm)
  p+p: 13 MHz ( ~3 MHz, |Z|<10cm)
  p+A: 2.8 MHz ( ~0.7 MHz,|Z|<10cm)
  sPHENIX DAQ: 15kHz
Precision vertexing for B-tagging w/ MVTX:
  Tracking resolution better than 60um @pT=1GeV
  High multiplicity HI collisions
  Low multiplicity but high rate p+p collisions
  Tag B w/ high efficiency and high purity
B hadrons/pT<15GeV: O(1M)
b-jets/pT>15GeV: O(100K)

## Slide 23: Assumptions about Funding & Schedule
Tied to sPHENIX and ALICE schedule
  Stave production
  Readout electronics
  To minimize technical risk and cost
Funding available when needed, no manpower smoothing
Cost based on ALICE/ITS and recent STAR & PHENIX upgrade projects at RHIC
  STAR HFT
  PHENIX FVTX

## Slide 24
Sensor Series Production
Stave Develop
2016
2017
2018
2019
2020
Commissioning @ Surface
Installation
Commissioning in ALICE
Stave Mechanics
HIC Production
CMOS processing, thinning & dicing, test
HIC and Stave
Stave Production
Mechanical Support Structures
Design & Prototyping
Design & Prototyping
Production & Test
PRR
PRR
Global Assembly
EDR
PRR
Development
Production
2016
2017
2018
2019
2020
EDR
PRR
Readout Electronics
Commissioning
11 months
Dry Assembly Test
ALICE ITS Upgrade
Overall ITS Planning (Simplified Global View)
From L. Musa, 4/27/2017
Stave PRR Presentation

## Slide 25
  Pixel Sensor Chip - EDR (Oct’ 15)
  Stave - EDR (May’ 16)
  Detector Barrel Mechanics - EDR (Jul ’16)
  Cooling – EDR (Jul ’16)
  Pixel Sensor Chip - PRR (Nov ’16)
  Detector Barrel Mechanics - PRR (Dec ’16)
  Service Barrel Mechanics - EDR (Dec ‘16): done
  Cooling – PRR (Dec ’16): done
  Readout Electronics – EDR (Jan ‘17): done
  Stave - PRR (Apr ‘17)
  Service Barrel Mechanics – PRR (May ‘17)
  Readout Electronics – PRR (Dec ’17)
Project Review Milestones
ALICE ITS Upgrade
Stave Production Readiness Review:
4/27/2017
Stave production starts ~May/June;
1st set of IB by Jan 2018;
2nd set of IB by July 2018
LANL people + others/MVTX work on stave production from May 2017 at CERN, prototype available soon at LANL
Fully working staves for R&D available ~Jan 2018;
Near final readout RU/CRU: ~12/2017
From L. Musa, 4/27/2017

## Slide 26: ALPIDE/MAPS Timing & Operation
Well fit sPHENIX/RHIC environment, 10MHz Clock (LHC 40MHz)
DV=Q/C
v
t
PIX_IN
tr> 100 μs
tf~= 10 ns
OUT_D
STROBE
~5-6 ms
~5-6 μs
v
t
OUT_A
threshold
sPHENIX trigger latency: ~4 μs
shaping time: 2, 5, 10 … μs

## Slide 27: Detector Assembly
Precision positioning and installation of staves on end-wheels
IB CYSS
Layer 0
Layer 1
Layer 2
Assembly of layers and carbon fiber structure into half-detector
Stave testing at each step
Metrology survey

## Slide 28: INTT-MVTX Conflict
INTT 4-layers
Currently a clear conflict between the INTT and MVTX
  INTT only includes ladder, no connectors, cooling barbs, etc
R&D items: 1) Extend cables to move the conical structure further out in z-direction; 2) Design/optimize INTT layers to fit current MVTX geometry;
  FPC data cable is the HDI and can’t be easily extended, short “firefly” cables possible?
  Reduce angle of cone – redesign C-structures and connectors
|η|<0.95
|η|<1.09
|η|<1.28
|η|<1.12
INTT Acceptance
@ |z|=10

## Slide 29: INTT-MVTX Conflict
INTT 4-layers
Extend cables to move the conical structure further out in z-direction
  FPC data cable is the HDI and can’t be easily extended
  Possibly add short “firefly” cables to hook up to patch panel, R&D needed
Reduce angle of cone – redesign

## Slide 30: MVTX/INTT Integration Extend MVTX Service Cables?
506.2 mm
16 mm
41.9 mm
16.15 mm
The 9 silicon chips are read out in parallel: each chip sends its data stream to the end of Stave by a dedicated differential pair, 100 mm wide. Two additional differential pairs distribute the clock and configuration signals.
CHIP 1
CHIP 9
……
CHIP 2

## Slide 32: Expected Luminosities and Collision Rates

## Slide 34: dN/dη in p+p collisions
With |η|<2.0 region, dN(ALICE) ~2.9*dN(sPHENIX).
sPHENIX
ALICE

## Slide 35: dN/dη in 0-10% Au+Au/Pb+Pb collisions
With |η|<2.0 region, dN(ALICE) ~5.1*dN(sPHENIX).
Ncoll(Au+Au)=962, Ncoll(Pb+Pb)=1670.
sPHENIX
ALICE

## Slide 36: dN/dη in MB Au+Au/Pb+Pb collisions
With |η|<2.0 region, dN(ALICE) ~4.6*dN(sPHENIX).
Ncoll(Au+Au)=258, Ncoll(Pb+Pb)=401.
sPHENIX
ALICE

## Slide 37: Hit Density on STAR PXL at RHIC Environment
 | PXL inner | PXL outer
Radius (cm) | 2.8 | 8
MB pileup hits (cm-2) | 13 | ~3
UPC electrons (cm-2) | 33 | ~3
Total bkgd hits (cm-2) | 46 | ~6
MB signal Au+Au (cm-2) | ~8 | ~1
Simulation@50kHz
Signal hits fraction in MB (Central) events:
~15% (~30%) at PXL inner
Increasing fake matches in low pT
Technology chosen considering both physics and technology readiness
Au+Au MB real data (cm-2) | ~50 | ~5
Simulation
Xin’s talk
- Ming’s note:
With ~5uS integration time, BG rate can be reduced by a factor of,
5/200 = 1/40
S/B ~ 8/1 for sPHENIX

## Slide 38: Hits and Event Data Rate
Event size: sPHENIX = 1/3 ALICE
Identical geometry for MVTX and ITS/IB(layer 0-2)
sPHENIX integration time ~5uS, less noise compared with ALICE with 10~20uS.

## Slide 39
48 inner staves;
48 RU boards;
6 FELIX boards;
- 8RU ->1 FELIX
Readout Units Required for ITS & sPHENIX

## Slide 40: MVTX options: 6x (PCIe card + server)
Event Buffering and Data Compressor (EBDC): Rack server that can host at 1x PCIex16 cards + 2x 10 Gbps Ethernet port
Data Aggregation Module (DAM):
PCIex8 or x16 card with multiple (48x) GBT fiber IO
Example: Dell PowerEdge R830
2x12 cores, 2x10 GBps, ~ 10k$
Option 1: ATLAS FELIX
Option 2: LHCb/ALICE CRU
Option 3: build our own based on ALICE/ATLAS exp.
MVTX/TPC
Buffer box
MVTX

## Slide 41
ALPIDE Modes of Operation
The ITS is planned to be operated in two modes:
  Triggered mode: Pixels are latched with a short strobe window and read out based on an external trigger.
  Continuous mode: Pixels are latched using a long, periodic strobe window and read out.

## Slide 42: Multi-Event buffering
This is what makes the DAQ as fast as it is
Or, in other words: that keeps the dead time in the low 90%’s
Comes down to dealing with your data from various events in parallel
Our hardware is designed to deal with 5-event buffering
More is a diminishing return for $$$
We actually mostly ran 4-event buffering in PHENIX

## Slide 43: ALICE Data Rate and Dead Time

## Slide 44: ITS Readout - Radiation Load
Position respect to beam |  |  | Radiation levels (total) |  |  | 
r | z | Name | TID | 1 MeV neq fluence | High energy hadron flux* | Charged particle flux
[cm] | [cm] |  | [krad] | [cm-2] | [kHz cm-2] | [kHz cm-2]
2.2 | [-13.5 ÷ 13.5] | ITS L0 | 2734 | 1.7 × 1013 | 765 (770) | 890 (910)
43 | [-73.7 ÷ 73.7] | ITS L6 | 20 | 8.1 × 1011 | 3.4 (4.9) | 4.5 (6.7)
79 | [-260 ÷ 260] | TPC In | 5.6 | 7.0 × 1011 | 1.35 (1.8) | 1.7 (3.45)
100 | 330 | RE | ≈ 5 | ≈ 1.6 × 1011 | 0.86 | 1.7
258 | [-260 ÷ 260] | TPC Out | 0.86 | 1.4 × 1011 | 0.27 (0.37) | 0.2 (0.3)
290 | [-290 ÷ 290] | TRD | 0.6 | 1.2 × 1011 | 0.23 (0.31) | 0.15 (0.23)
TID & fluence = (table 1 × 1.3data taking efficiency + Table 2 / 10better vacuum) × 10safety factor
Safety factor of 10 on top of TID and fluence calculated as in the above line.
Hadrons and charged particles as for 50 kHz Pb-Pb collisions (table 1, worst case scenario).
The average value within the z span is reported first, in brackets the peak value within the z interval.
* Momentum > 20 MeV.